## Cover
[DOCUMENT TITLE]
Level of Effort
MICROSOFT - Modern-Workspace - M365 Deployment
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
User Base | Total Users | 500 M365 E5 users | 500 users | 1000-2000 users | 3000+ users | Users requiring Microsoft 365 E5 licenses
User Base | User Roles | 5 roles (employee manager admin executive guest) | 2-3 standard roles | 4-6 roles | 8+ roles with complex permissions | Employee manager admin executive guest roles
M365 Services | M365 Services | Exchange SharePoint Teams OneDrive | Core services | Core + advanced | Full suite + custom | Microsoft 365 services and features enabled
M365 Services | M365 License | E5 (security compliance productivity) | E5 basic | E5 advanced | E5 + add-ons | Microsoft 365 licensing tier and features
M365 Services | Email Migration Volume | 250 GB total mailbox data | 250 GB | 1 TB | 5+ TB | Email migration from on-premises Exchange
M365 Services | File Migration Volume | 5 TB SharePoint and OneDrive | 5 TB | 20 TB | 100+ TB | File migration from on-premises file servers
M365 Services | Teams Phone Users | 150 users with PSTN calling | 150 users | 300 users | 1000+ users | Teams Phone System with PSTN connectivity
M365 Services | Audio Conferencing | 200 users dial-in access | 200 users | 500 users | 2000+ users | Teams audio conferencing dial-in capability
M365 Services | External Sharing | Controlled external collaboration | Basic external sharing | Standard guest access | Advanced B2B collaboration | External collaboration and guest access complexity
M365 Services | Support Coverage | 24x7 user helpdesk support | Basic 8x5 support | Standard 24x5 support | Premium 24x7 support | User support coverage and SLA
Security & Compliance | Security Requirements | Zero-trust Conditional Access MFA | Basic security | Standard zero-trust | Advanced threat protection | Security architecture and controls complexity
Security & Compliance | Compliance Frameworks | SOC 2 GDPR HIPAA | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Regulatory compliance requirements
Security & Compliance | Authentication | Azure AD Connect SSO with MFA | Azure AD basic | Azure AD standard | Federated multi-forest | Identity and access management complexity
Security & Compliance | Device Management | Intune MDM for 500 endpoints | Basic MDM | Standard MDM | Advanced endpoint protection | Mobile device and endpoint management
Technical Environment | Availability Requirements | 99.9% (M365 SLA) | 99.9% standard | 99.95% high availability | 99.99% mission critical | Microsoft 365 service level agreement
Technical Environment | Infrastructure Complexity | Hybrid Exchange during migration | Basic hybrid | Standard hybrid | Complex multi-forest | Hybrid cloud architecture complexity
Technical Environment | Deployment Timeline | 4 months pilot to production | 4 months | 6 months | 12+ months | Migration timeline and deployment complexity
Environment | Deployment Environments | 2 environments (pilot production) | 2 environments (pilot production) | 3 environments (dev staging prod) | 4+ environments with pipelines | Environment management for Microsoft 365

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Foundation Setup, Pilot Deployment, Azure AD Connect)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Email Migration, SharePoint Deployment, Teams Deployment)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Teams Phone, Security Hardening, Compliance Implementation)
Testing | TESTING_MX | 1 | All Testing phase tasks (Migration Testing, Security Testing, User Acceptance Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Cutover, Hypercare Support, Optimization)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Helpdesk Training, Champions Program)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Exchange Decommissioning)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | M365 Tenant Provisioning | Provision Microsoft 365 E5 tenant and domain verification | EO Engineer | 16 |  |  | 150 |  |  | Tenant setup licensing and domain configuration
Discovery | Azure AD Connect Deployment | Deploy Azure AD Connect for identity synchronization and SSO | EO Engineer | 32 |  |  | 180 |  |  | Identity sync SSO and MFA configuration
Discovery | Hybrid Exchange Configuration | Configure hybrid Exchange for mailbox coexistence | EO Engineer | 24 |  |  | 175 |  | Azure AD Connect Deployment | Hybrid setup enabling email migration
Discovery | Pilot Migration Planning | Plan pilot migration with 50 users across departments | EO Engineer | 16 |  |  | 150 |  | Hybrid Exchange Configuration | Pilot user selection and migration planning
Planning | Pilot Email Migration | Migrate 50 pilot users to Exchange Online | EO Engineer | 32 |  |  | 160 |  | Pilot Migration Planning | Pilot mailbox migration with validation
Planning | Pilot SharePoint Deployment | Deploy pilot SharePoint sites and file collaboration | EO Engineer | 24 |  |  | 155 |  | Pilot Email Migration | SharePoint site structure and pilot deployment
Planning | Pilot Teams Deployment | Deploy Microsoft Teams for pilot users with collaboration | EO Engineer | 16 |  |  | 150 |  | Pilot SharePoint Deployment | Teams channels chat and meetings for pilot
Planning | Pilot Validation | Validate pilot migration and gather user feedback | EO Engineer | 16 |  |  | 140 |  | Pilot Teams Deployment | Pilot user acceptance and lessons learned
Development | Production Email Migration | Migrate remaining 450 users to Exchange Online in waves | EO Engineer | 80 |  |  | 160 |  | Pilot Validation | 5 departmental waves with 90 users each
Development | SharePoint Online Deployment | Deploy SharePoint sites for all departments and projects | EO Engineer | 40 |  |  | 155 |  | Production Email Migration | Department and project site provisioning
Development | OneDrive Deployment | Deploy OneDrive for Business with Known Folder Move | EO Engineer | 24 |  |  | 150 |  | SharePoint Online Deployment | OneDrive sync and file migration
Development | File Migration | Migrate 5TB files from on-premises to SharePoint and OneDrive | EO Engineer | 40 |  |  | 150 |  | OneDrive Deployment | File server to SharePoint/OneDrive migration
Development | Teams Company Deployment | Deploy Teams company-wide with channels and governance | EO Engineer | 32 |  |  | 155 |  | File Migration | Company-wide Teams collaboration deployment
Development | Teams Phone System | Deploy Teams Phone for 150 users with PSTN calling | EO Engineer | 40 |  |  | 170 |  | Teams Company Deployment | Teams calling with Direct Routing or Calling Plan
Development | Audio Conferencing | Configure audio conferencing for 200 users with dial-in | EO Engineer | 16 |  |  | 150 |  | Teams Phone System | Teams meeting dial-in access configuration
Development | Conditional Access | Implement Conditional Access policies with MFA and device compliance | EO Engineer | 24 |  |  | 175 |  | Audio Conferencing | Zero-trust security policy implementation
Development | Defender for Office 365 | Deploy Defender with anti-phishing and anti-malware protection | EO Engineer | 24 |  |  | 170 |  | Conditional Access | Threat protection and Safe Links/Attachments
Development | Microsoft Purview | Implement Purview for DLP information protection and retention | EO Engineer | 32 |  |  | 165 |  | Defender for Office 365 | Data loss prevention and compliance policies
Development | Intune MDM | Deploy Intune for 500 endpoints with device compliance | EO Engineer | 24 |  |  | 160 |  | Microsoft Purview | Mobile device management and app protection
Testing | Migration Validation | Validate email and file migration with zero data loss | EO Engineer | 24 |  |  | 140 |  | Intune MDM | Migration accuracy and data integrity validation
Testing | Security Testing | Test Conditional Access Defender and DLP policies | EO Engineer | 24 |  |  | 165 |  | Migration Validation | Security control effectiveness testing
Testing | Teams Quality Testing | Test Teams collaboration calling and meeting quality | EO Engineer | 16 |  |  | 150 |  | Security Testing | Call quality and user experience validation
Testing | User Acceptance Testing | Coordinate UAT with business users and stakeholders | EO Engineer | 24 |  |  | 140 |  | Teams Quality Testing | Business user validation and sign-off
Deployment | Production Cutover | Final cutover to Microsoft 365 with decommissioning planning | EO Engineer | 16 |  |  | 160 |  | User Acceptance Testing | Production go-live and Exchange decommissioning plan
Deployment | Hypercare Support | Provide 30-day hypercare support post-production | EO Engineer | 40 |  |  | 130 |  | Production Cutover | Post-migration issue resolution and optimization
Training | Administrator Training | Train IT administrators on M365 Exchange SharePoint Teams | EO Engineer | 24 |  |  | 150 |  | Production Cutover | Admin training for ongoing operations
Training | Helpdesk Training | Train helpdesk on Microsoft 365 user support | EO Engineer | 16 |  |  | 130 |  | Administrator Training | Helpdesk support training and procedures
Training | Champions Program | Establish Champions program with department representatives | EO Engineer | 16 |  |  | 140 |  | Helpdesk Training | Champions training for user adoption
Training | Documentation | Create operations runbook and user guides | EO Engineer | 24 |  |  | 130 |  | Champions Program | Technical and user documentation
Closeout | Knowledge Transfer | Transfer Microsoft 365 operations ownership to client team | EO Engineer | 16 |  |  | 140 |  | Documentation | Comprehensive handover of M365 operations
Closeout | Performance Optimization | Optimize network connectivity Teams QoS and user experience | EO Engineer | 16 |  |  | 150 |  | Knowledge Transfer | Performance tuning and optimization recommendations
Management | Technical Leadership | Quarterback technical oversight and M365 architecture review | EO Quarterback |  |  |  | 200 |  |  | M365 architecture and migration coordination
Management | Project Management | Project coordination and migration management | EO Project Manager |  |  |  | 150 |  |  | Stakeholder coordination and timeline management
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers based on M365 migration complexity

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Microsoft Partner Services Credit | 0 | No Microsoft partner credits available for commercial M365 licensing
FastTrack Assistance | 0 | Microsoft FastTrack assistance is free for 500+ seat organizations
TOTAL |  | Total Cost - no partner credits for commercial Microsoft 365