## Cover
[DOCUMENT TITLE]
Level of Effort
DELL - Cyber-Security - Safeid Authentication
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Number of Workstations | 10 Dell Precision 7960 units | 3 workstations | 10 workstations | 25+ workstations | AI/ML workstation deployment scale
Solution Scope | GPU Configuration | NVIDIA RTX A6000 48GB | RTX A5000 24GB | RTX A6000 48GB | RTX A6000 or A100 80GB | GPU memory and compute requirements
Integration | Data Science Tools | Standard stack (PyTorch TensorFlow) | Jupyter only | Full stack (Jupyter VS Code TensorBoard) | Advanced MLOps platform | AI/ML framework and tooling complexity
Integration | Shared Storage | Dell PowerScale F600 100TB NAS | Local storage only | Shared NAS 50-100TB | Enterprise NAS 200TB+ with replication | Centralized dataset and model storage
User Base | Data Scientists | 10 concurrent users | 3 users | 10 users | 25+ users | Active data science team size
User Base | User Roles | 2 roles (data scientist admin) | Single role | 2-3 roles | Complex role-based access | RBAC and storage permissions
Data Volume | Dataset Size per Project | 5TB average dataset size | 1-2TB datasets | 5TB datasets | 10TB+ datasets | Training data volume requirements
Data Volume | Model Checkpoint Storage | 2TB model storage requirements | 500GB checkpoints | 2TB checkpoints | 5TB+ model versioning | Saved model and checkpoint capacity
Technical Environment | Network Connectivity | 10GbE to shared storage | 1GbE standard | 10GbE recommended | 25GbE or higher | Network bandwidth for data loading
Technical Environment | Workstation Performance | Dell Precision 7960 dual Xeon Gold | Standard config | High-performance config | Maximum performance with liquid cooling | CPU and system performance tier
Technical Environment | Operating System | Ubuntu 22.04 LTS with CUDA | Windows only | Ubuntu or CentOS | Multi-OS with custom kernels | OS standardization and support
Security & Compliance | Access Control | Standard file permissions and SSH | Basic access | LDAP/AD integration | Advanced PAM and audit logging | Authentication and authorization
Security & Compliance | Data Classification | Unclassified research data | Public data | Sensitive research | Regulated data (HIPAA ITAR) | Data sensitivity and compliance
Performance | Training Performance | Target: 80% GPU utilization average | Best effort | 80% utilization | 90%+ with job scheduling | GPU efficiency and workload optimization
Performance | Storage Performance | 7000 MB/s NVMe read per workstation | Standard SSD | High-speed NVMe | NVMe RAID arrays | Local storage I/O performance
Environment | Deployment Environments | Production only | Single environment | Production + dev | Multi-tenant with quotas | Environment separation and management

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Assessment Hardware Planning Dataset Analysis)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Infrastructure Design Storage Architecture Network Design)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Workstation Deployment GPU Configuration Storage Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Performance Testing GPU Benchmarking Storage Validation)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Rollout User Onboarding)
Training | TRAINING_MX | 1 | All Training phase tasks (User Training Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer Performance Baseline)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Assessment | Assess AI/ML workload requirements and user workflows | EO Engineer | 40 | 1 |  | 150 |  |  | Includes dataset analysis and GPU sizing for PyTorch/TensorFlow
Discovery | Hardware Planning | Evaluate Dell Precision and GPU configuration options | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide representative training workloads for benchmarking
Discovery | Dataset Analysis | Analyze dataset sizes access patterns and storage needs | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide dataset inventory and growth projections
Discovery | Network Assessment | Evaluate network infrastructure for 10GbE connectivity | EO Engineer | 16 |  |  | 175 |  |  | Identifies network upgrades needed for shared storage access
Planning | Infrastructure Design | Design Dell Precision workstation and GPU architecture | EO Engineer | 40 |  |  | 200 |  | Requirements Assessment | Deliverable: Hardware architecture with GPU and storage design
Planning | Storage Architecture | Design PowerScale NAS storage and dataset organization | EO Engineer | 24 |  |  | 180 |  | Dataset Analysis | Deliverable: Storage capacity plan and NFS/SMB share design
Planning | Network Design | Design 10GbE network connectivity and switch topology | EO Engineer | 24 |  |  | 175 |  | Network Assessment | Network diagram with workstation-to-storage connectivity
Planning | Project Planning | Develop implementation timeline and procurement schedule | EO Engineer | 24 |  |  | 140 |  | Infrastructure Design | Deliverable: Project plan with hardware lead times
Development | Workstation Procurement | Order Dell Precision 7960 workstations and components | EO Engineer | 16 |  |  | 160 |  | Infrastructure Design | Coordinate with Dell sales and track delivery schedule
Development | GPU Configuration | Install and configure NVIDIA RTX A6000 GPUs with drivers | EO Engineer | 40 |  |  | 160 |  | Workstation Procurement | Includes CUDA cuDNN installation and GPU burn-in testing
Development | Storage Deployment | Deploy Dell PowerScale F600 NAS and configure shares | EO Engineer | 48 |  |  | 170 |  | Storage Architecture | Configure NFS/SMB shares with user permissions and quotas
Development | Operating System Setup | Install Ubuntu 22.04 LTS and AI/ML software stack | EO Engineer | 32 |  |  | 130 |  | GPU Configuration | Install PyTorch TensorFlow Jupyter and development tools
Development | Network Configuration | Configure 10GbE network and storage connectivity | EO Engineer | 24 |  |  | 140 |  | Network Design | Includes switch configuration VLAN setup and network validation
Development | Monitoring Setup | Deploy Datadog for GPU metrics and utilization tracking | EO Engineer | 24 |  |  | 130 |  | Operating System Setup | Configure GPU monitoring dashboards and alerting
Testing | Performance Testing | Benchmark GPU performance with PyTorch/TensorFlow | EO Engineer | 24 |  |  | 140 |  | Operating System Setup | Validate GPU utilization and training throughput
Testing | Storage Performance | Test NAS storage throughput and dataset loading speeds | EO Engineer | 16 |  |  | 120 |  | Storage Deployment | Measure read/write performance with large datasets
Testing | Network Validation | Validate 10GbE network performance and bandwidth | EO Engineer | 16 |  |  | 120 |  | Network Configuration | Network throughput testing between workstations and storage
Testing | End-to-End Testing | Run representative training workloads end-to-end | EO Engineer | 24 |  |  | 130 |  | Performance Testing | Customer must provide sample training scripts for validation
Deployment | Production Rollout | Deploy remaining workstations to production | EO Engineer | 24 |  |  | 160 |  | End-to-End Testing | Phased rollout with monitoring and issue tracking
Deployment | User Onboarding | Onboard data scientists to new workstation environment | EO Engineer | 16 |  |  | 110 |  | Production Rollout | Assist with workspace setup and first training runs
Deployment | Go-Live Support | Provide hypercare support during initial production use | EO Engineer | 40 |  |  | 110 |  | User Onboarding | Daily monitoring and rapid issue response
Training | Data Scientist Training | Train users on GPU workstation usage and best practices | EO Engineer | 16 |  |  | 130 |  | Production Rollout | Includes PyTorch/TensorFlow optimization and GPU profiling
Training | Administrator Training | Train IT staff on workstation and storage management | EO Engineer | 16 |  |  | 120 |  | Data Scientist Training | Includes GPU monitoring Datadog and PowerScale administration
Training | Documentation | Create user guides and operational runbooks | EO Engineer | 24 |  |  | 110 |  | Administrator Training | Deliverable: User guides troubleshooting procedures GPU optimization
Closeout | Knowledge Transfer | Transfer solution ownership to IT operations | EO Engineer | 16 |  |  | 140 |  | Documentation | Comprehensive handover including hardware specs and procedures
Closeout | Performance Baseline | Establish GPU utilization and performance baselines | EO Engineer | 8 |  |  | 130 |  | Knowledge Transfer | Establishes GPU efficiency metrics and cost tracking
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | Dell Precision architecture review and GPU optimization guidance
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes status reporting risk management and vendor coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers in Estimate Settings based on deployment scale

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Dell Partner Discount | -15000 | Dell Titanium Partner discount on hardware procurement (negotiate 5-10% on volume orders)
Implementation Discount | 0 | No implementation discount applicable
TOTAL