## Cover
[DOCUMENT TITLE]
Level of Effort
SAMPLE-PROVIDER - Sample-Category - Sample Solution
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Primary Features/Capabilities | 3-5 core features | 3-5 core features | 6-10 features | 10+ features or advanced capabilities | Standard feature set for solution type
Solution Scope | Customization Level | Minimal configuration | Minimal configuration | Moderate customization | Extensive custom development | Configuration vs custom code
Integration | External System Integrations | 2 REST APIs | 2 REST APIs | 4-6 systems | 8+ systems or complex protocols | Standard REST/API integrations
Integration | Data Sources | 2-3 data sources | 2-3 data sources | 4-6 data sources | 8+ data sources or complex formats | Structured data sources
User Base | Total Users | 50 users | 50 users | 100-250 users | 500+ users | Across all user types and roles
User Base | User Roles | 2-3 standard roles | 2-3 standard roles | 4-6 roles | 8+ roles with complex permissions | Role-based access control
Data Volume | Data Processing Volume | Small scale standard volume | Small scale standard volume | Medium scale increased volume | Large scale high volume | Varies by solution type (transactions docs etc)
Data Volume | Data Storage Requirements | 100 GB | 100 GB | 500 GB - 1 TB | 2+ TB | Includes retention and backup
Technical Environment | Deployment Regions | Single region | Single region | 2-3 regions | Global multi-region | Geographic distribution
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | SLA and uptime requirements
Technical Environment | Infrastructure Complexity | Basic single-tier | Basic single-tier | Multi-tier standard | Complex distributed architecture | Architecture complexity level
Security & Compliance | Security Requirements | Basic authentication and encryption | Basic authentication and encryption | Industry standard (SOC2 HIPAA) | Advanced (FedRAMP multi-jurisdiction) | Security controls and compliance
Security & Compliance | Compliance Frameworks | 1-2 basic standards | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Regulatory compliance requirements
Performance | Performance Requirements | Standard performance | Standard performance | Enhanced performance | High performance low latency | Response time and throughput needs
Environment | Deployment Environments | 2 environments (dev prod) | 2 environments (dev prod) | 3 environments (dev staging prod) | 4+ environments with automation | Environment management complexity

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Technical Assessment, Security Review, Integration Assessment)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Solution Design, Security Architecture, Data Architecture, Implementation Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Infrastructure Setup, Core Development, Database Development, Integration Development, UI Development, Security Implementation)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Integration Testing, Performance Testing, Security Testing, UAT)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Pre-Production Validation, Production Deployment, Data Migration, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, End User Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline, Project Retrospective)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews and discovery workshops | EO Engineer | 40 |  |  | 150 |  |  | Includes stakeholder interviews and requirements documentation deliverable
Discovery | Technical Assessment | Evaluate current infrastructure and technical environment | EO Engineer | 32 |  |  | 175 |  |  | Customer must provide access to current infrastructure for evaluation
Discovery | Security & Compliance Review | Assess security requirements and compliance standards | EO Engineer | 16 |  |  | 175 |  |  | Identifies compliance gaps and remediation requirements
Discovery | Integration Assessment | Identify integration points and data flow requirements | EO Engineer | 24 |  |  | 160 |  |  | Customer must provide API documentation and integration endpoints
Planning | Security Architecture | Design security controls and compliance framework | EO Engineer | 24 |  |  | 175 |  | Security & Compliance Review | Deliverable: Security design document with controls and compliance mapping
Planning | Data Architecture | Design data models schemas and data flow | EO Engineer | 32 |  |  | 165 |  | Integration Assessment | Deliverable: Data model diagrams and migration strategy
Development | Infrastructure Setup | Provision and configure infrastructure environment | EO Engineer | 40 |  |  | 160 |  |  | Includes environment provisioning and configuration baseline
Development | Core Application Development | Build primary application functionality and services | EO Engineer | 120 |  |  | 150 |  | Infrastructure Setup | Largest effort item - varies significantly based on feature complexity
Development | Database Development | Implement database schema stored procedures and queries | EO Engineer | 40 |  |  | 155 |  | Data Architecture | Includes schema design stored procedures and initial data seeding
Development | Integration Development | Build API integrations data connectors and workflows | EO Engineer | 64 |  |  | 155 |  | Core Application Development | Customer integration endpoints must be available for testing
Development | User Interface Development | Create user interface and user experience components | EO Engineer | 48 |  |  | 140 |  | Core Application Development | Includes responsive design for desktop and mobile devices
Development | Security Implementation | Implement authentication authorization and security controls | EO Engineer | 32 |  |  | 165 |  | Security Architecture | Deliverable: Functional authentication authorization and audit logging
Testing | Unit Testing | Develop and execute unit tests for all components | EO Engineer | 32 |  |  | 140 |  | Core Application Development | Automated test suite for regression testing
Testing | Integration Testing | Test system integrations data flows and API endpoints | EO Engineer | 40 |  |  | 140 |  | Integration Development | Requires access to customer test environments and systems
Testing | Performance Testing | Conduct load performance and scalability testing | EO Engineer | 24 |  |  | 150 |  | Integration Testing | Load testing with expected concurrent user volumes
Testing | Security Testing | Perform security assessments and vulnerability testing | EO Engineer | 16 |  |  | 175 |  | Security Implementation | Third-party security assessment may require additional budget
Testing | User Acceptance Testing | Coordinate and support UAT with business users | EO Engineer | 32 |  |  | 150 |  | Performance Testing | Customer business users must be available for UAT period
Deployment | Pre-Production Validation | Validate solution in pre-production environment | EO Engineer | 16 |  |  | 150 |  | User Acceptance Testing | Final checks before production deployment
Deployment | Production Deployment | Deploy solution to production environment | EO Engineer | 24 |  |  | 160 |  | Pre-Production Validation | Includes deployment runbook and rollback procedures
Deployment | Data Migration | Migrate existing data to new system | EO Engineer | 32 |  |  | 155 |  | Production Deployment | Customer responsible for data quality and validation
Deployment | Go-Live Support | Provide support during initial production rollout | EO Engineer | 40 |  |  | 130 |  | Data Migration | Includes daily monitoring and rapid issue response during hypercare
Training | Administrator Training | Train system administrators and technical users | EO Engineer | 16 |  |  | 140 |  | Production Deployment | Includes system administration and troubleshooting procedures
Training | End User Training | Train business users on system functionality | EO Engineer | 24 |  |  | 130 |  | Administrator Training | Role-based training sessions - customer provides training space
Training | Documentation | Create user manuals technical documentation and runbooks | EO Engineer | 32 |  |  | 120 |  | End User Training | Deliverable: User guides administrator guides and runbooks
Closeout | Knowledge Transfer | Transfer ownership to operations and support teams | EO Engineer | 16 |  |  | 140 |  | Documentation | Comprehensive handover to customer operations team
Closeout | Performance Baseline | Establish performance metrics and monitoring baselines | EO Engineer | 8 |  |  | 130 |  | Knowledge Transfer | Establishes SLA metrics and monitoring thresholds
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | Solution architecture review and technical escalation support
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes weekly status reporting and risk management
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase-based multipliers in Estimate Settings sheet based on customer scope

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Partner Program Credit | -5000 | Partner program services credit applied to professional services
Volume Discount | 0 | No volume discount applicable
TOTAL