## Cover
[DOCUMENT TITLE]
Level of Effort
AZURE - Cyber-Security - Sentinel Siem
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Data Connectors | 10-15 connectors | 10-15 connectors | Enhanced data connectors | Enterprise-scale data connectors | Sizing parameter for Data Connectors
Solution Scope | Analytics Rules | 50 custom detection rules | 50 custom detection rules | Enhanced analytics rules | Enterprise-scale analytics rules | Sizing parameter for Analytics Rules
Integration | Log Sources | Azure AD Office365 Firewall Endpoints | Azure AD Office365 Firewall Endpoints | Enhanced log sources | Enterprise-scale log sources | Sizing parameter for Log Sources
Integration | SOAR Playbooks | 10 automated playbooks | 10 automated playbooks | Enhanced soar playbooks | Enterprise-scale soar playbooks | Sizing parameter for SOAR Playbooks
User Base | Total Users | 10 SOC analysts | 10 SOC analysts | Enhanced total users | Enterprise-scale total users | Sizing parameter for Total Users
User Base | User Roles | 3 roles (analyst engineer admin) | 3 roles (analyst engineer admin) | Enhanced user roles | Enterprise-scale user roles | Sizing parameter for User Roles
Data Volume | Daily Log Ingestion | 50 GB/day | 50 GB/day | Enhanced daily log ingestion | Enterprise-scale daily log ingestion | Sizing parameter for Daily Log Ingestion
Data Volume | Retention Period | 90 days hot 2 years archive | 90 days hot 2 years archive | Enhanced retention period | Enterprise-scale retention period | Sizing parameter for Retention Period
Technical Environment | Deployment Regions | Single Azure region (East US) | Single Azure region (East US) | Enhanced deployment regions | Enterprise-scale deployment regions | Sizing parameter for Deployment Regions
Technical Environment | Availability Requirements | 24/7 monitoring | 24/7 monitoring | Enhanced availability requirements | Enterprise-scale availability requirements | Sizing parameter for Availability Requirements
Technical Environment | Infrastructure Complexity | Log Analytics + Sentinel workspace | Log Analytics + Sentinel workspace | Enhanced infrastructure complexity | Enterprise-scale infrastructure complexity | Sizing parameter for Infrastructure Complexity
Security & Compliance | Security Requirements | RBAC MFA audit logging | RBAC MFA audit logging | Enhanced security requirements | Enterprise-scale security requirements | Sizing parameter for Security Requirements
Security & Compliance | Compliance Frameworks | SOC2 NIST CSF | SOC2 NIST CSF | Enhanced compliance frameworks | Enterprise-scale compliance frameworks | Sizing parameter for Compliance Frameworks
Performance | Detection Response | MTTR <1 hour | MTTR <1 hour | Enhanced detection response | Enterprise-scale detection response | Sizing parameter for Detection Response
Performance | Query Performance | Standard KQL queries | Standard KQL queries | Enhanced query performance | Enterprise-scale query performance | Sizing parameter for Query Performance
Environment | Deployment Environments | 2 environments (dev prod) | 2 environments (dev prod) | Enhanced deployment environments | Enterprise-scale deployment environments | Sizing parameter for Deployment Environments

## Estimate Settings
ESTIMATE SETTINGS - EO Sales Engineer Updates Multipliers Based on Customer Scope
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks
Planning | PLANNING_MX | 1 | All Planning phase tasks
Development | DEVELOPMENT_MX | 1 | All Development phase tasks
Testing | TESTING_MX | 1 | All Testing phase tasks
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks
Training | TRAINING_MX | 1 | All Training phase tasks
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks
Management | MANAGEMENT_MX | 1.5 | Project Management overhead
Leadership | LEADERSHIP_MX | 1.5 | Technical Leadership overhead
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Security Requirements Gathering | Conduct security stakeholder interviews and threat modeling | EO Engineer | 40 |  |  | 150 |  | $# | ##0"")
Discovery | Current Security Assessment | Analyze existing security tools logs and incident response | EO Engineer | 32 |  |  | 200 |  | $# | ##0"")
Discovery | Azure Security Assessment | Evaluate Azure security services (Sentinel Defender Security Center) | EO Engineer | 24 |  |  | 200 |  | $# | ##0"")
Discovery | Compliance Review | Assess regulatory requirements and security frameworks | EO Engineer | 16 |  |  | 175 |  | $# | ##0"")
Planning | SIEM Architecture Design | Design Azure Sentinel architecture and data connectors | EO Engineer | 48 |  |  | 200 |  | $# | ##0"")
Planning | Security Playbook Design | Design incident response playbooks and automation workflows | EO Engineer | 32 |  |  | 180 |  | $# | ##0"")
Planning | Security Governance | Design security policies roles and access controls | EO Engineer | 24 |  |  | 175 |  | $# | ##0"")
Planning | Project Planning | Develop security implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | $# | ##0"")
Development | Azure Sentinel Deployment | Deploy and configure Azure Sentinel workspace and connectors | EO Engineer | 40 |  |  | 160 |  | $# | ##0"")
Development | Log Analytics Configuration | Configure log collection parsing normalization and enrichment | EO Engineer | 60 |  |  | 145 |  | $# | ##0"")
Development | Security Rules and Detection | Build detection rules alerts and threat hunting queries | EO Engineer | 80 |  |  | 170 |  | $# | ##0"")
Development | Incident Response Automation | Build automated response playbooks and SOAR workflows | EO Engineer | 48 |  |  | 165 |  | $# | ##0"")
Development | Security Dashboard and Reporting | Create SOC dashboards executive reporting and metrics | EO Engineer | 40 |  |  | 130 |  | $# | ##0"")
Development | Integration Development | Build integrations with existing security tools and ITSM | EO Engineer | 32 |  |  | 155 |  | $# | ##0"")
Testing | Unit Testing | Develop automated tests for all solution components | EO Engineer | 32 |  |  | 120 |  | $# | ##0"")
Testing | Integration Testing | Test system integrations data flows and external dependencies | EO Engineer | 40 |  |  | 120 |  | $# | ##0"")
Testing | Performance Testing | Conduct load performance and scalability testing | EO Engineer | 24 |  |  | 140 |  | $# | ##0"")
Testing | Security Testing | Perform security assessments penetration testing and compliance validation | EO Engineer | 16 |  |  | 175 |  | $# | ##0"")
Testing | User Acceptance Testing | Coordinate UAT with business users and stakeholders | EO Engineer | 32 |  |  | 150 |  | $# | ##0"")
Deployment | Production Deployment | Deploy solution to production environment with monitoring | EO Engineer | 24 |  |  | 160 |  | $# | ##0"")
Deployment | Go-Live Support | Provide comprehensive support during initial production rollout | EO Engineer | 48 |  |  | 110 |  | $# | ##0"")
Training | Administrator Training | Train system administrators and technical support teams | EO Engineer | 16 |  |  | 130 |  | $# | ##0"")
Training | End User Training | Train business users on solution functionality and workflows | EO Engineer | 24 |  |  | 120 |  | $# | ##0"")
Training | Documentation | Create comprehensive technical and user documentation | EO Engineer | 32 |  |  | 110 |  | $# | ##0"")
Closeout | Knowledge Transfer | Transfer solution ownership to operations and support teams | EO Engineer | 16 |  |  | 140 |  | $# | ##0"")
Closeout | Performance Baseline | Establish performance metrics monitoring baselines and SLAs | EO Engineer | 8 |  |  | 130 |  | $# | ##0"")
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  | $# | ##0"")
Management | Project Management | Project coordination and management activities | EO Project Manager |  |  | $# | ##0"")
[5 empty] | TOTAL HOURS |  | TOTAL COST |  | $H$33:$H$60) | $#

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Microsoft Partner Services Credit | 0 | No partner credits available
Implementation Discount | 0 | No implementation discount applicable
TOTAL |  | Total Cost