# Statement of Work

Cisco Systems - Cisco SD-WAN Enterprise

| Client: | [Client Name] |
| --- | --- |
| Date: | [Month DD] |
| Consulting Company: | [Consulting Company Name] |
| Submitted By: | [Contact Name ¦ Email ¦ Phone] |
| Opportunity No: | [OPP-YYYY-###] |
| Version: | [1.0] |

# Table of Contents

1 Introduction
    1.1 Purpose
        1.1.1 Scope
2 Table Content
3 Image Section
4 Additional Content
5 Sign-Off

# List of Figures

Figure 1: Sample Architecture Diagram

# List of Tables

Table 1: Sample Deliverables Table

# 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for the Cisco SD-WAN Enterprise project for [Client Name]. This engagement will transform WAN operations by replacing expensive MPLS circuits with cloud-ready SD-WAN, reducing WAN costs by 60% and enabling 95% faster site deployment through zero-touch provisioning.

Project Duration: 16 weeks

# 2 Background & Objectives

## 2.1 Current State

[Client Name] currently operates a traditional MPLS-based WAN with 25 branch offices. Key challenges include:

• High WAN Costs: $300K annual MPLS circuit costs with limited bandwidth and long-term contracts

• Slow Site Deployment: New branch offices take 8 weeks to provision MPLS circuits

• Poor Cloud Performance: Cloud applications (Office 365, Salesforce) backhauled through data center

• Limited Bandwidth: MPLS provides only 10-50 Mbps per site constraining business growth

• Complex Management: Separate management for MPLS, internet, and routing policies

## 2.2 Business Objectives

• Reduce WAN Costs: Achieve 60% cost reduction by replacing $300K MPLS with $176K SD-WAN (broadband + LTE)

• Accelerate Site Deployment: Enable 95% faster provisioning (2 hours vs 8 weeks) with zero-touch router deployment

• Optimize Cloud Access: Direct internet breakout improving Office 365 performance by 50%

• Increase Bandwidth: 10x bandwidth increase (10-50 Mbps MPLS → 100 Mbps broadband) at lower cost

• Simplify Management: Centralized vManage dashboard replacing CLI on 27 routers

• Enable Flexibility: Agile WAN with dual circuits (broadband + LTE) and automatic failover

## 2.3 Success Metrics

• 60% WAN cost reduction ($300K → $176K annually)

• 95% faster site deployment (8 weeks → 2 hours)

• 50% improvement in cloud application performance

• 99.9% WAN uptime with dual circuits and LTE backup

• ROI realization within 18 months

# 3 Scope of Work

## 3.1 In Scope

• Current WAN assessment (MPLS circuits, bandwidth, application analysis)

• SD-WAN architecture design with hub-spoke topology

• Circuit availability analysis (broadband and LTE at 25 sites)

• Application-aware routing policy design for SaaS and business apps

• vManage, vSmart, vBond controller deployment

• Hub router configuration (2x ISR 4451 at data centers)

• Branch router deployment (25x ISR 4331 with zero-touch provisioning)

• Application routing and SLA policy configuration

• Security policy setup (firewall, VPN, cloud integration)

• Lab validation (GNS3 or CML testing)

• Pilot deployment (3 sites for validation)

• Production rollout (22 sites in 2 waves)

• MPLS circuit decommissioning after validation

• Team training on vManage operations (24 hours)

• 4-week hypercare support period

### 3.1.1 Scope Parameters

This engagement is sized based on the following parameters:

| Category | Parameter | Scope |
| --- | --- | --- |
| Solution Scope | Primary Features/Capabilities | SD-WAN for 25 branch offices |
| Solution Scope | Customization Level | Standard SD-WAN deployment |
| Integration | External System Integrations | 2 systems (cloud + monitoring) |
| Integration | Data Sources | WAN telemetry only |
| User Base | Total Users | 5 network engineers |
| User Base | User Roles | 2 roles (admin + operator) |
| Data Volume | Data Processing Volume | 25 sites WAN traffic |
| Data Volume | Data Storage Requirements | 200 GB (90-day logs) |
| Technical Environment | Deployment Regions | Single region |
| Technical Environment | Availability Requirements | Standard (99.5%) |
| Technical Environment | Infrastructure Complexity | Basic hub-spoke WAN |
| Security & Compliance | Security Requirements | Basic VPN encryption |
| Security & Compliance | Compliance Frameworks | Basic logging |
| Performance | Performance Requirements | Standard application routing |
| Environment | Deployment Environments | Production only |

Table 1: Engagement Scope Parameters

Table: Engagement Scope Parameters

Note: Changes to these parameters may require scope adjustment and additional investment.

## 3.2 Out of Scope

These items are not in scope unless added via change control:

• Hardware procurement beyond ISR routers and controllers

• WAN circuit procurement (client responsibility)

• Legacy router decommissioning and disposal

• Application optimization beyond routing policies

• Managed services post-hypercare period

• SD-WAN security advanced features (Umbrella, ThousandEyes)

## 3.3 Activities

### 3.3.1 Phase 1 – Design & Planning (Weeks 1-4)

Current WAN is assessed and SD-WAN solution designed.

Key activities:

• WAN assessment: MPLS circuits, bandwidth, costs, application analysis (80 hours)

• SD-WAN architecture design with hub-spoke topology and redundancy

• Circuit availability analysis: broadband and LTE feasibility at 25 sites

• Application-aware routing policy design for SaaS and business-critical apps

• Migration strategy with pilot sites and phased rollout plan

Deliverable: WAN Assessment Report and SD-WAN Architecture Design

### 3.3.2 Phase 2 – Infrastructure Deployment (Weeks 5-8)

SD-WAN controllers and hub routers are deployed.

Key activities:

• vManage, vSmart, vBond controller deployment (data center or cloud) (40 hours)

• Hub router configuration: 2x ISR 4451 with HA at data centers (40 hours)

• Application routing and SLA policy configuration (60 hours)

• Security policy setup: firewall rules, VPN, cloud integration (40 hours)

• Lab validation with GNS3 or CML testing (32 hours)

Deliverable: SD-WAN Controllers and Hub Router Configuration

### 3.3.3 Phase 3 – Site Deployment (Weeks 9-12)

Branch sites are deployed in pilot and production waves.

Key activities:

• Pilot deployment: 3 low-risk sites for validation (60 hours)

• Performance testing: application SLA compliance and failover scenarios (40 hours)

• Production Wave 1: deploy 10 sites with zero-touch provisioning (60 hours)

• Production Wave 2: deploy remaining 12 sites (60 hours)

• MPLS dual-run period with gradual traffic migration

Deliverable: Deployed SD-WAN Sites with Performance Test Results

### 3.3.4 Phase 4 – Optimization (Weeks 13-16)

MPLS is decommissioned and operations team trained.

Key activities:

• MPLS circuit decommissioning after SD-WAN validation (40 hours)

• Performance optimization and policy fine-tuning (24 hours)

• Team training on vManage operations and troubleshooting (24 hours)

• Documentation and knowledge transfer

• Hypercare support activation (60 hours over 4 weeks)

Deliverable: As-Built Documentation and Operational Runbooks

# 4 Deliverables & Timeline

This section outlines the key deliverables, project milestones, and timeline for the SD-WAN Enterprise implementation. All deliverables are subject to formal acceptance by designated client stakeholders before proceeding to subsequent phases.

## 4.1 Deliverables

The following deliverables will be produced throughout the project lifecycle, with formal acceptance required from designated client stakeholders:

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | WAN Assessment Report | Document | Week 4 | Client IT Lead |
| 2 | SD-WAN Architecture Design | Document | Week 4 | Network Lead |
| 3 | Hub Router Configuration | Infrastructure | Week 8 | Infrastructure Lead |
| 4 | Deployed SD-WAN Sites | Infrastructure | Week 12 | Operations Lead |
| 5 | As-Built Documentation | Document | Week 16 | Client IT Lead |

Table 2: Project Deliverables and Acceptance Criteria

## 4.2 Project Milestones

The project will be tracked against the following key milestones, representing major completion points and readiness gates for the next phase:

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 - Design Complete | SD-WAN architecture approved | Week 4 |
| M2 - Controllers Deployed | vManage vSmart vBond operational | Week 8 |
| M3 - Pilot Success | 3 sites validated on SD-WAN | Week 10 |
| M4 - Deployment Complete | All 25 sites on SD-WAN | Week 12 |
| M5 - MPLS Decommissioned | Legacy circuits disconnected | Week 16 |
| Hypercare End | Support period complete | Week 20 |

Table 3: Project Milestones and Timeline

# 5 Roles & Responsibilities

This section defines the roles, responsibilities, and accountabilities for both Vendor and Client teams throughout the project lifecycle using a RACI matrix framework.

## 5.1 RACI Matrix

The following RACI matrix defines responsibility assignments for key project activities across Vendor and Client roles:

| Task/Role | EO PM | EO Quarterback | EO WAN Eng | EO SD-WAN | Client Net | Client Ops | SME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Discovery & Requirements | A | R | R | C | C | I | C |
| SD-WAN Architecture | C | A | R | R | C | I | I |
| Controller Deployment | C | A | C | R | C | I | I |
| Hub Router Config | C | R | A | R | C | I | I |
| Site Deployment | C | R | C | A | A | C | I |
| Testing & Validation | R | R | C | R | A | C | I |
| Knowledge Transfer | A | R | R | R | C | I | I |

Table 4: Roles And Responsibilities

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

## 5.2 Key Personnel

Vendor Team:

• EO Project Manager: Overall delivery accountability

• EO Quarterback: Technical design and architecture oversight

• EO WAN Engineer: WAN assessment and architecture design

• EO SD-WAN Engineer: Controller and router deployment

Client Team:

• Network Lead: Primary technical contact and WAN coordination

• Operations Lead: Site coordination and circuit procurement

• Application SME: Application performance requirements

• Telecom Lead: Circuit orders and MPLS decommissioning

# 6 Architecture & Design

## 6.1 Architecture Overview

Figure 1: Solution Architecture

Figure 1: SD-WAN Enterprise Architecture - Cloud-optimized WAN with zero-touch provisioning

The proposed architecture replaces MPLS with a flexible SD-WAN overlay. Key components include:

• Control Plane: vManage (management), vSmart (control), vBond (orchestration)

• Hub Routers: 2x ISR 4451 at data centers with redundant WAN circuits

• Branch Routers: 25x ISR 4331 with dual circuits (broadband + LTE)

• Transport: Dual broadband (100 Mbps) + LTE backup per site

## 6.2 Architecture Type

This solution follows a hub-and-spoke SD-WAN architecture pattern. Key characteristics:

• Deployment Model: Overlay SD-WAN with encrypted IPsec tunnels

• Routing: Application-aware routing with SLA policies

• Transport: Multi-circuit with automatic failover

• Management: Centralized vManage orchestration

The architecture supports 25 sites with scalability to 100+ sites.

## 6.3 Technical Implementation Strategy

The deployment follows a conservative phased approach:

Pilot Phase (Week 10):

• Deploy 3 low-risk branch sites (small offices, non-critical apps)

• Validate zero-touch provisioning workflow

• Test application performance and SLA compliance

• Validate circuit failover (broadband → LTE)

Production Waves (Weeks 11-12):

• Wave 1: 10 medium-sized branches

• Wave 2: 12 remaining branches including critical sites

• Dual-run period with MPLS and SD-WAN

• Gradual traffic migration to SD-WAN

• Performance validation before MPLS disconnect

MPLS Decommission (Weeks 13-16):

• Site-by-site MPLS disconnection after SD-WAN validation

• Circuit contract termination coordination

• Cost savings realization

# 7 Security & Compliance

## 7.1 Identity & Access Management

• Role-based access control (RBAC) for vManage administrators

• Multi-factor authentication (MFA) for privileged access

• Integration with Active Directory/LDAP (optional)

• Audit logging for all configuration changes

## 7.2 WAN Security

• IPsec encryption for all SD-WAN tunnels

• Zone-based firewall on branch routers

• Application visibility and control

• Umbrella DNS security (optional add-on)

## 7.3 Compliance & Auditing

• Configuration change tracking via vManage

• Template-based deployment ensuring consistency

• Audit trails for all policy changes

• Compliance reporting for change management

# 8 Testing & Validation

## 8.1 Functional Validation

Comprehensive testing ensures SD-WAN works correctly:

Controller Testing:

• vManage orchestration and zero-touch provisioning

• vSmart routing policy distribution

• vBond device authentication and onboarding

Routing Testing:

• Application-aware routing (Office 365, VoIP, ERP)

• SLA policy enforcement and path selection

• Traffic steering and load balancing

• Automatic failover (broadband → LTE)

## 8.2 Performance Testing

Performance validation ensures SLA requirements:

Load Testing:

• Application performance benchmarking (before/after)

• Office 365 latency and throughput testing

• VoIP call quality and jitter validation

• ERP application response time

Failover Testing:

• Primary circuit failure and LTE failover

• Failover time validation (target: < 1 second)

• Application session continuity during failover

## 8.3 User Acceptance Testing (UAT)

UAT performed with pilot sites:

UAT Approach:

• Pilot sites: 3 low-risk branches

• Application performance validation

• User experience feedback

• Circuit failover validation

Acceptance Criteria:

• Application performance meets or exceeds MPLS baseline

• Failover occurs automatically without user impact

• Zero-touch provisioning works for new sites

# 9 Handover & Support

## 9.1 Handover Artifacts

Upon successful implementation:

Documentation Deliverables:

• As-built architecture diagrams

• SD-WAN controller configuration documentation

• Router templates and policy configurations

• Application routing policy documentation

• Circuit and connectivity documentation

Operational Deliverables:

• Operations runbooks for daily tasks

• Troubleshooting guides for common issues

• vManage dashboard and monitoring guide

• Incident response and escalation procedures

• Performance monitoring and capacity planning

Knowledge Assets:

• Recorded training sessions (24 hours)

• vManage administrator credentials

• Router access and management procedures

• Vendor support contacts

## 9.2 Knowledge Transfer

Training Sessions:

• 24 hours of hands-on training

• vManage operations and monitoring

• Application-aware routing policies

• Troubleshooting and diagnostics

• Zero-touch provisioning for new sites

• Circuit failover and performance monitoring

Documentation Package:

• As-built architecture documentation

• Configuration management guide

• Operational runbooks and SOPs

• Troubleshooting guide

## 9.3 Hypercare Support

Duration: 4 weeks post-go-live

Coverage:

• Business hours support (8 AM - 6 PM local time)

• 4-hour response time for critical issues

• Daily check-ins (first 2 weeks)

• Weekly status meetings

Scope:

• Issue investigation and resolution

• Performance tuning and optimization

• Policy adjustments and fine-tuning

• Knowledge transfer continuation

## 9.4 Assumptions

### 9.4.1 General Assumptions

Client Responsibilities:

• Client will order broadband and LTE circuits for all 25 sites (8-12 week lead time)

• Client will provide data center rack space and power for controllers

• Client network team available for validation and testing

• Client will coordinate MPLS circuit disconnections and contract terminations

Technical Environment:

• Broadband and LTE circuits available at all 25 branch locations

• Data center network connectivity available for hub routers and controllers

• Application SLA requirements documented

• No major application changes during deployment

Project Execution:

• Project scope and requirements remain stable

• Resources available per project plan

• Circuit orders placed within 2 weeks of project start

• Security and compliance approvals timely

## 9.5 Dependencies

### 9.5.1 Project Dependencies

Access & Infrastructure:

• Data center rack space and power for controllers and hub routers (Week 1)

• Broadband circuits installed at all 25 sites (by Week 9)

• LTE circuits provisioned with SIMs (by Week 9)

• Remote hands at branch sites for router installation

Circuits & Connectivity:

• Broadband circuit orders placed by Week 2 (8-12 week lead time)

• LTE SIM cards ordered and activated by Week 8

• MPLS circuits maintained until SD-WAN validation complete

• Circuit provider coordination for installation and cutover

# 10 Investment Summary

This section provides a comprehensive breakdown of the total investment required for the SD-WAN Enterprise implementation, including professional services, hardware, software licensing, WAN circuits, and ongoing support costs over a 3-year period.

## 10.1 Total Investment

The following table summarizes the total cost of ownership for this engagement across all cost categories and years:

| Cost Category | Year 1 List | AWS/Partner Credits | Year 1 Net | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Services | $0 | $0 | $0 | $0 | $0 | $0 |
| Connectivity | $103,800 | ($12,000) | $91,800 | $103,800 | $103,800 | $299,400 |
| Hardware | $136,500 | ($8,000) | $128,500 | $0 | $0 | $128,500 |
| Software Licenses | $59,200 | ($15,000) | $44,200 | $59,200 | $59,200 | $162,600 |
| Support & Maintenance | $16,200 | $0 | $16,200 | $16,200 | $16,200 | $48,600 |
| TOTAL INVESTMENT | $315,700 | ($35,000) | $280,700 | $179,200 | $179,200 | $639,100 |

Table 5: Total Investment Summary

## 10.2 Partner Credits

Year 1 Credits Applied: $35,000 (router trade-in + SD-WAN license promotion + circuit installation waiver)

Annual Recurring Cost: $179,200/year (WAN circuits, software, support)

MPLS Replacement Savings: $124,000/year (current $300K MPLS vs $176K SD-WAN recurring)

## 10.3 Payment Terms

Pricing Model: Fixed price with milestone-based payments

Payment Schedule:

• 30% upon SOW execution and project kickoff ($24,060)

• 30% upon completion of Phase 2 - Controllers Deployed ($24,060)

• 25% upon completion of Phase 3 - Deployment Complete ($20,050)

• 15% upon successful go-live and MPLS decommission ($12,030)

Invoicing: Monthly invoicing based on milestones completed. Net 30 payment terms.

# 11 Terms & Conditions

## 11.1 General Terms

All services will be delivered in accordance with the executed Master Services Agreement (MSA) between Vendor and Client.

## 11.2 Scope Changes

Any changes to scope, schedule, or cost require a formal Change Request approved by both parties.

## 11.3 Intellectual Property

• Client retains ownership of all deliverables and configurations

• Vendor retains proprietary methodologies and tools

• Pre-existing IP remains with original owner

## 11.4 Confidentiality

• All artifacts under NDA protection

• Client data handled per security requirements

• No disclosure to third parties without consent

# 12 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

eoframework.org