## Cover
[DOCUMENT TITLE]
Level of Effort
DELL - Cloud - Vxrail Hyperconverged
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Cluster Size | 8-node VxRail P570 all-NVMe cluster | 4-node | 8-node enterprise | 16-node large | Enterprise cluster scale
Solution Scope | Storage Capacity | 200TB usable all-NVMe | 80TB usable | 200TB usable | 400TB+ usable | High-performance NVMe storage
Integration | vSphere Stack | vSphere 8 Enterprise Plus with NSX | vSphere only | vSphere + NSX | vSphere NSX vRealize Suite | VMware enterprise stack
Integration | DR Solution | VMware SRM with RecoverPoint for VMs | No DR | SRM replication | Multi-site HA stretched cluster | Disaster recovery complexity
User Base | VM Count | 800 VMs including mission-critical databases | 250 VMs | 800 VMs | 1500+ VMs | Enterprise VM scale
User Base | Database Workloads | Oracle RAC SQL Always-On SAP HANA | No databases | Standard databases | Mission-critical Tier 1 | Database performance requirements
Data Volume | Storage Type | All-NVMe 30.72TB per node | Hybrid or all-flash SSD | All-NVMe performance | NVMe with RAID-6 | Enterprise performance tier
Data Volume | IOPS Requirements | 100000+ IOPS cluster aggregate | 10K IOPS | 100K IOPS | 200K+ IOPS | Mission-critical performance SLA
Technical Environment | Current Infrastructure | EMC VMAX or NetApp enterprise SAN | Mid-range SAN | Enterprise SAN | Multi-array legacy | Migration complexity from Tier 1 storage
Technical Environment | Network Fabric | 100GbE spine-leaf network | 25GbE network | 100GbE fabric | Multi-site WAN connectivity | Enterprise network requirements
Technical Environment | vSAN Features | FTT=2 RAID-6 erasure coding | FTT=1 mirroring | FTT=2 RAID-6 | Stretched cluster multi-site | Advanced vSAN features
Security & Compliance | Compliance | Mission-critical with SOC 2 ISO 27001 | Standard compliance | Enterprise compliance | Regulated (PCI HIPAA FedRAMP) | Enterprise compliance requirements
Security & Compliance | Encryption | vSAN and VM encryption with KMS | vSAN encryption | vSAN + VM encryption | FIPS 140-2 compliance | Enterprise security controls
Performance | Latency SLA | <1ms storage latency for databases | <5ms acceptable | <1ms target | Sub-millisecond | Mission-critical performance SLA
Performance | Availability | 99.99% uptime with N+2 fault tolerance | 99.9% (N+1) | 99.99% (N+2) | 99.999% stretched cluster | Enterprise availability SLA
Environment | DR Requirements | RPO <5 min RTO <15 min with SRM | No DR | Standard DR | Mission-critical DR automation | Disaster recovery SLA

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Database Assessment Enterprise SAN Inventory)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Enterprise VxRail Design NSX Architecture DR Design)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (VxRail Deployment Database Migration DR Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Database Performance SLA Validation DR Failover)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Tier 1 Migration Enterprise Cutover)
Training | TRAINING_MX | 1 | All Training phase tasks (Enterprise Operations NSX Training)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Enterprise Handover SLA Baseline)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Database Assessment | Assess Oracle RAC SQL Always-On workload requirements | EO Engineer | 40 | 1 |  | 200 |  |  | Includes database performance profiling
Discovery | Enterprise SAN Inventory | Document VMAX/NetApp infrastructure and costs | EO Engineer | 24 |  |  | 200 |  |  | Enterprise SAN baseline and TCO analysis
Discovery | DR Requirements | Assess disaster recovery RPO RTO requirements | EO Engineer | 24 |  |  | 200 |  |  | DR architecture and SRM design requirements
Discovery | Network Assessment | Survey 100GbE network fabric and DR site connectivity | EO Engineer | 16 |  |  | 175 |  |  | Spine-leaf and WAN bandwidth validation
Planning | Enterprise VxRail Design | Design 8-node VxRail P570 all-NVMe architecture | EO Engineer | 48 |  |  | 200 |  | Database Assessment | Deliverable: Enterprise architecture with FTT=2
Planning | vSAN FTT=2 Design | Design RAID-6 erasure coding for enterprise vSAN | EO Engineer | 24 |  |  | 200 |  | Enterprise VxRail Design | FTT=2 storage policies and capacity planning
Planning | NSX Architecture | Design NSX Data Center micro-segmentation | EO Engineer | 32 |  |  | 200 |  | Enterprise VxRail Design | NSX distributed firewall and zero-trust design
Planning | DR Architecture | Design VMware SRM and RecoverPoint replication | EO Engineer | 32 |  |  | 200 |  | DR Requirements | SRM failover orchestration and RPO design
Development | VxRail Procurement | Order VxRail P570 all-NVMe nodes and fabric | EO Engineer | 16 |  |  | 175 |  | Enterprise VxRail Design | Coordinate Dell Enterprise sales
Development | VxRail Deployment | Dell ProDeploy Enterprise installation and configuration | EO Engineer | 64 |  |  | 200 |  | VxRail Procurement | ProDeploy Enterprise on-site deployment
Development | vSphere Enterprise Setup | Configure vCenter vRealize Operations and logging | EO Engineer | 40 |  |  | 200 |  | VxRail Deployment | Enterprise management and monitoring platform
Development | vSAN FTT=2 Setup | Configure FTT=2 RAID-6 and deduplication | EO Engineer | 32 |  |  | 200 |  | vSphere Enterprise Setup | Enterprise vSAN with erasure coding
Development | NSX Deployment | Deploy NSX Data Center and distributed firewall | EO Engineer | 40 |  |  | 200 |  | vSAN FTT=2 Setup | Micro-segmentation for database tier
Development | RecoverPoint Deployment | Deploy RecoverPoint for VMs and configure replication | EO Engineer | 32 |  |  | 200 |  | NSX Deployment | RPO <5 min continuous replication
Development | SRM Configuration | Configure VMware SRM for automated DR failover | EO Engineer | 32 |  |  | 200 |  | RecoverPoint Deployment | RTO <15 min automated orchestration
Testing | Database Performance | Benchmark Oracle RAC and SQL performance | EO Engineer | 32 |  |  | 200 |  | vSAN FTT=2 Setup | Validate 100K+ IOPS and <1ms latency
Testing | SLA Validation | Validate 99.99% uptime and N+2 fault tolerance | EO Engineer | 16 |  |  | 200 |  | Database Performance | 2-node failure testing and recovery
Testing | DR Failover Testing | Test SRM automated failover to DR site | EO Engineer | 24 |  |  | 200 |  | SRM Configuration | Validate RPO <5min RTO <15min
Testing | Pilot Database Migration | Migrate non-production Oracle or SQL database | EO Engineer | 24 |  |  | 200 |  | Database Performance | Pilot validation before Tier 1
Deployment | Tier 1 Database Migration | Migrate Oracle RAC SQL Always-On SAP HANA | EO Engineer | 80 |  |  | 200 |  | Pilot Database Migration | Mission-critical database cutover
Deployment | VM Migration | Migrate remaining 700+ VMs to VxRail | EO Engineer | 64 |  |  | 175 |  | Tier 1 Database Migration | Phased migration post-database validation
Deployment | SAN Decommission | Decommission VMAX/NetApp enterprise SAN | EO Engineer | 16 |  |  | 175 |  | VM Migration | Eliminate $250K+ annual SAN support cost
Training | Enterprise Operations | Train team on vRealize Operations and vSAN Enterprise | EO Engineer | 24 |  |  | 200 |  | SAN Decommission | Enterprise platform operations training
Training | NSX Training | Train team on NSX distributed firewall and micro-segmentation | EO Engineer | 24 |  |  | 200 |  | Enterprise Operations | Zero-trust networking administration
Training | DR Training | Train team on SRM failover procedures | EO Engineer | 16 |  |  | 200 |  | NSX Training | DR runbooks and failover procedures
Training | Documentation | Create enterprise runbooks and architecture docs | EO Engineer | 24 |  |  | 175 |  | DR Training | Comprehensive enterprise documentation
Closeout | Knowledge Transfer | Transfer to enterprise operations team | EO Engineer | 16 |  |  | 200 |  | Documentation | Enterprise handover with TAM introduction
Closeout | SLA Baseline | Establish 99.99% uptime and <1ms latency baseline | EO Engineer | 8 |  |  | 200 |  | Knowledge Transfer | Enterprise SLA metrics and monitoring
Management | Technical Leadership | VCDX-level architecture review and guidance | EO Quarterback |  |  |  | 200 |  |  | Enterprise architecture and optimization
Management | Project Management | Enterprise project coordination | EO Project Manager |  |  |  | 200 |  |  | Dell Mission Critical Services coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | Enterprise deployment complexity

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Dell Partner Discount | -50000 | Dell Titanium Partner discount on VxRail P570 enterprise hardware (negotiate 5-10%)
Implementation Discount | 0 | No implementation discount applicable
TOTAL