## Cover
[DOCUMENT TITLE]
Level of Effort
DELL - Network - Powerswitch Datacenter
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Number of Racks | 40 racks with ToR switches | 10-20 racks | 40 racks | 100+ racks | Data center scale and switch quantity
Solution Scope | Spine Switches | 4 Dell Z9432F-ON 100GbE | 2 spines (small) | 4 spines (medium) | 6-8 spines (large) | Core fabric capacity and redundancy
Integration | Leaf Switches | 40 Dell S5248F-ON 25GbE ToR | 10-20 leaf | 40 leaf | 100+ leaf | Top-of-rack switch deployment
Integration | Network Fabric | BGP underlay with EVPN-VXLAN overlay | VLANs only | BGP + VXLAN | BGP EVPN multi-tenant | Network virtualization complexity
User Base | Network Engineers | 3-5 network administrators | 1-2 engineers | 3-5 engineers | 6+ engineers | Team size for training and support
User Base | Automation Maturity | Ansible playbooks and ZTP | Manual CLI only | Ansible automation | Full GitOps automation | Network automation adoption
Data Volume | Server Ports | 1920 ports (40 racks × 48 ports) | 480 ports (10-20 racks) | 1920 ports (40 racks) | 4800 ports (100 racks) | Total server connectivity requirements
Data Volume | Fabric Bandwidth | 1.6Tbps aggregate throughput | 400Gbps (small) | 1.6Tbps (medium) | 4Tbps+ (large) | Total spine-leaf fabric capacity
Technical Environment | Network Connectivity | 100GbE spine 25GbE leaf | 10GbE fabric | 25/100GbE fabric | 40/100/400GbE fabric | Bandwidth tier selection
Technical Environment | Legacy Infrastructure | Cisco Nexus 9K and Catalyst switches | Single vendor | Multi-vendor | Complex legacy | Migration complexity from Cisco
Technical Environment | Operating System | Dell OS10 Enterprise with automation | OS10 Lite | OS10 Enterprise | OS10 + SmartFabric | Software feature requirements
Security & Compliance | Network Segmentation | VXLAN multi-tenancy | VLANs only | VXLAN overlay | Micro-segmentation | Security architecture complexity
Security & Compliance | Access Control | TACACS+ centralized authentication | Local accounts | TACACS+ or RADIUS | Certificate + MFA | Network device authentication
Performance | Latency SLA | <2 microsecond east-west latency | <10ms adequate | <2ms target | <1ms required | Application performance requirements
Performance | Throughput | 7000 Mbps per server (25GbE NIC) | 1000 Mbps (1GbE) | 7000 Mbps (25GbE) | 12500 Mbps (40GbE) | Server uplink bandwidth
Environment | Deployment Approach | Phased rack-by-rack migration | Forklift cutover | Phased migration | Parallel fabric | Migration risk and complexity

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Network Assessment Rack Inventory Cisco Baseline)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Spine-Leaf Design BGP Architecture VXLAN Design)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Switch Installation OS10 Configuration BGP Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Performance Testing Failover Validation Throughput)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Rack Migration Production Cutover)
Training | TRAINING_MX | 1 | All Training phase tasks (OS10 Training BGP/VXLAN Automation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer Network Baseline)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Network Assessment | Assess current data center network and Cisco baseline | EO Engineer | 40 | 1 |  | 150 |  |  | Includes rack inventory and bandwidth analysis
Discovery | Cisco Cost Analysis | Analyze Cisco SmartNet costs and EOL timeline | EO Engineer | 24 |  |  | 175 |  |  | Customer must provide Cisco support contracts and quotes
Discovery | Application Profiling | Profile application bandwidth and latency requirements | EO Engineer | 32 |  |  | 175 |  |  | Identifies north-south vs east-west traffic patterns
Discovery | Physical Infrastructure | Survey data center rack space power and cooling | EO Engineer | 16 |  |  | 150 |  |  | Validates power circuits and HVAC for switch deployment
Planning | Spine-Leaf Design | Design spine-leaf fabric architecture and topology | EO Engineer | 40 |  |  | 200 |  | Network Assessment | Deliverable: Network diagram with spine-leaf topology
Planning | BGP Architecture | Design BGP underlay with ASN and IP addressing plan | EO Engineer | 32 |  |  | 200 |  | Spine-Leaf Design | Deliverable: BGP design with ASN allocation
Planning | VXLAN Overlay | Design EVPN-VXLAN overlay and tenant segmentation | EO Engineer | 32 |  |  | 200 |  | BGP Architecture | VXLAN VNID allocation and L2/L3 gateway design
Planning | Migration Planning | Develop phased migration plan and cutover runbook | EO Engineer | 24 |  |  | 175 |  | Application Profiling | Deliverable: Migration timeline with risk mitigation
Development | Spine Procurement | Order Dell PowerSwitch Z9432F spine switches and optics | EO Engineer | 16 |  |  | 160 |  | Spine-Leaf Design | Coordinate Dell sales and track delivery schedule
Development | Leaf Procurement | Order Dell PowerSwitch S5248F leaf ToR switches | EO Engineer | 16 |  |  | 160 |  | Spine-Leaf Design | 40 ToR switches with 100GbE uplink optics
Development | Spine Installation | Install spine switches in core data center rows | EO Engineer | 24 |  |  | 160 |  | Spine Procurement | Rack installation and power connectivity
Development | Leaf Installation | Install leaf ToR switches in each server rack | EO Engineer | 64 |  |  | 160 |  | Leaf Procurement | 40 racks × 1 ToR per rack installation and cabling
Development | OS10 Configuration | Configure Dell OS10 base system and management | EO Engineer | 32 |  |  | 175 |  | Spine Installation | Includes hostname IP management VLANs and AAA
Development | BGP Configuration | Configure BGP underlay routing on spine and leaf | EO Engineer | 40 |  |  | 200 |  | OS10 Configuration | BGP peer configuration and route verification
Development | VXLAN Setup | Deploy EVPN-VXLAN overlay network | EO Engineer | 40 |  |  | 200 |  | BGP Configuration | VXLAN VNID tenant configuration and gateway
Development | Automation Deployment | Configure Ansible playbooks and ZTP for leaf switches | EO Engineer | 32 |  |  | 175 |  | VXLAN Setup | SmartFabric Services for zero-touch provisioning
Testing | Fabric Validation | Validate spine-leaf fabric connectivity and routing | EO Engineer | 24 |  |  | 160 |  | VXLAN Setup | BGP adjacency and VXLAN tunnel verification
Testing | Performance Testing | Benchmark throughput and latency performance | EO Engineer | 24 |  |  | 160 |  | Fabric Validation | Iperf testing between racks validates 25GbE bandwidth
Testing | Failover Testing | Test spine and leaf failover scenarios | EO Engineer | 16 |  |  | 150 |  | Fabric Validation | Validate HA and redundancy design
Testing | Pilot Rack Migration | Migrate pilot rack to validate production readiness | EO Engineer | 24 |  |  | 160 |  | Performance Testing | Customer must identify pilot rack and application
Deployment | Phased Migration | Migrate racks from Cisco to PowerSwitch fabric | EO Engineer | 80 |  |  | 175 |  | Pilot Rack Migration | 5-10 racks per weekend cutover window
Deployment | Application Validation | Validate application connectivity post-migration | EO Engineer | 32 |  |  | 150 |  | Phased Migration | Application team validation and smoke testing
Deployment | Cisco Decommission | Decommission legacy Cisco infrastructure | EO Engineer | 24 |  |  | 140 |  | Application Validation | Coordinate SmartNet cancellation and RMA
Deployment | Production Support | Provide hypercare support during migration | EO Engineer | 40 |  |  | 150 |  | Phased Migration | Daily monitoring and rapid issue response
Training | Network Engineer Training | Train network team on OS10 and spine-leaf operations | EO Engineer | 24 |  |  | 175 |  | Production Support | OS10 CLI BGP VXLAN troubleshooting
Training | Automation Training | Train team on Ansible automation and SmartFabric | EO Engineer | 16 |  |  | 175 |  | Network Engineer Training | Ansible playbooks ZTP and GitOps workflow
Training | Documentation | Create network runbooks and troubleshooting guides | EO Engineer | 24 |  |  | 150 |  | Automation Training | Deliverable: AS-built docs IP plan BGP design runbooks
Closeout | Knowledge Transfer | Transfer network ownership to IT operations | EO Engineer | 16 |  |  | 175 |  | Documentation | Comprehensive handover including design and procedures
Closeout | Performance Baseline | Establish network performance baseline and monitoring | EO Engineer | 8 |  |  | 150 |  | Knowledge Transfer | Baseline throughput latency and availability metrics
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | Spine-leaf architecture review and BGP optimization
Management | Project Management | Project coordination planning and vendor management | EO Project Manager |  |  |  | 175 |  |  | Includes Dell coordination migration planning risk management
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers based on rack count

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Dell Partner Discount | -25000 | Dell Titanium Partner discount on PowerSwitch hardware (negotiate 5-10% on volume orders)
Implementation Discount | 0 | No implementation discount applicable
TOTAL