## Cover
[DOCUMENT TITLE]
Level of Effort
IBM - Cloud - Openshift Container Platform
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Cluster Size | 6-node cluster (3 control + 3 workers) | 6-node cluster | 12-node cluster | 24+ node cluster | OpenShift cluster sizing for workloads
Solution Scope | Container Capacity | 500-1000 containers | 500-1000 containers | 2000-5000 containers | 10000+ containers | Pod and container density
Integration | CI/CD Integrations | OpenShift Pipelines + GitOps | Tekton + ArgoCD | Jenkins + external tools | Complex multi-tool pipelines | Pipeline and deployment automation
Integration | External Systems | LDAP/AD + monitoring | 2-3 systems | 4-6 systems | 8+ systems or complex protocols | Authentication monitoring storage integrations
User Base | Developer Count | 50 developers | 50 developers | 100-200 developers | 500+ developers | Platform users and application teams
User Base | User Roles | 5 roles | 3-5 standard roles | 6-8 roles | 10+ roles with complex RBAC | Developer admin viewer auditor operator
Data Volume | Application Count | 10 initial applications | 5-10 apps | 20-50 apps | 100+ applications | Applications to containerize and migrate
Data Volume | Persistent Storage | 20 TB | 20 TB | 50 TB | 200+ TB | Persistent volume storage requirements
Technical Environment | Deployment Platform | VMware vSphere | VMware or bare metal | Multi-cloud (VMware + AWS) | Complex multi-cloud hybrid | Infrastructure platform for OpenShift
Technical Environment | Availability Requirements | Multi-AZ HA | Multi-AZ | Multi-region | Global with DR | High availability configuration
Technical Environment | Infrastructure Complexity | Standard 6-node cluster | Standard cluster | Advanced with service mesh | Complex distributed platform | OpenShift platform complexity
Security & Compliance | Security Requirements | RBAC + pod security policies | Basic RBAC | Industry standard (SOC2) | Advanced (FedRAMP multi-framework) | Container and platform security
Security & Compliance | Compliance Frameworks | SOC2 ISO 27001 | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Compliance and governance requirements
Performance | Service Mesh | Istio for microservices | Optional Istio | Full service mesh | Advanced traffic management | Service mesh complexity
Performance | Monitoring Stack | Prometheus + Grafana | Basic monitoring | Standard observability | Advanced with custom integrations | Platform observability and metrics
Environment | Deployment Environments | 3 environments (dev staging prod) | 2 environments | 3 environments | 4+ environments with multi-cluster | Environment management for platform

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Infrastructure Assessment, Application Assessment, Compliance Review)
Planning | PLANNING_MX | 1 | All Planning phase tasks (OpenShift Design, Network Design, Storage Design, Security Design, Project Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Cluster Deployment, Storage Configuration, CI/CD Setup, Application Migration)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Integration Testing, Performance Testing, Security Testing, UAT)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Developer Training, Administrator Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews for OpenShift requirements | EO Engineer | 40 |  |  | 150 |  |  | Includes platform requirements and application portfolio analysis
Discovery | Infrastructure Assessment | Analyze current infrastructure and OpenShift platform readiness | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide infrastructure details and capacity information
Discovery | Application Assessment | Evaluate applications for containerization and migration priority | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide application inventory and architecture documentation
Discovery | Compliance Review | Assess security governance and compliance requirements | EO Engineer | 16 |  |  | 175 |  |  | Identifies regulatory requirements and security controls
Planning | OpenShift Architecture Design | Design OpenShift cluster architecture and platform configuration | EO Engineer | 48 |  |  | 200 |  | Requirements Gathering | Deliverable: OpenShift architecture with HA control plane and worker nodes
Planning | Network Architecture Design | Design OVN-Kubernetes SDN networking and ingress strategy | EO Engineer | 32 |  |  | 180 |  | OpenShift Architecture Design | Deliverable: Network design with policies and load balancer configuration
Planning | Storage Design | Design persistent storage with ODF or external storage integration | EO Engineer | 24 |  |  | 175 |  | OpenShift Architecture Design | Block file object storage for containerized applications
Planning | Security Architecture | Design RBAC pod security policies and authentication integration | EO Engineer | 24 |  |  | 175 |  | Compliance Review | LDAP/AD integration and security controls design
Planning | Project Planning | Develop implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | OpenShift Architecture Design | Deliverable: Project plan with phased rollout schedule
Development | Cluster Deployment | Deploy 6-node OpenShift cluster with HA control plane | EO Engineer | 56 |  |  | 160 |  | OpenShift Architecture Design | Includes cluster installation bootstrap and validation
Development | Storage Configuration | Configure OpenShift Data Foundation or external storage | EO Engineer | 40 |  |  | 150 |  | Cluster Deployment | Storage classes persistent volumes and volume snapshots
Development | Networking Setup | Configure OVN-Kubernetes SDN routes and load balancers | EO Engineer | 32 |  |  | 145 |  | Cluster Deployment | Network policies ingress controllers and external access
Development | Authentication Integration | Integrate LDAP/AD for SSO and configure RBAC | EO Engineer | 32 |  |  | 155 |  | Security Architecture | OAuth provider configuration and role bindings
Development | Monitoring and Logging | Deploy Prometheus Grafana and EFK logging stack | EO Engineer | 32 |  |  | 140 |  | Cluster Deployment | Platform and application observability configuration
Development | CI/CD Pipeline Setup | Configure OpenShift Pipelines (Tekton) and GitOps (ArgoCD) | EO Engineer | 48 |  |  | 150 |  | Cluster Deployment | Pipeline templates and GitOps workflow automation
Development | Container Registry | Configure integrated Quay registry with vulnerability scanning | EO Engineer | 24 |  |  | 140 |  | Cluster Deployment | Image registry security scanning and retention policies
Development | Application Containerization | Containerize 10 pilot applications with Dockerfiles and manifests | EO Engineer | 80 |  |  | 130 |  | CI/CD Pipeline Setup | Customer must provide application access and development support
Development | Service Mesh Deployment | Deploy Istio service mesh for microservices traffic management | EO Engineer | 32 |  |  | 155 |  | Application Containerization | mTLS traffic routing and observability integration
Testing | Unit Testing | Develop automated tests for platform components | EO Engineer | 24 |  |  | 120 |  | Service Mesh Deployment | Automated validation of cluster configuration
Testing | Integration Testing | Test application deployments CI/CD workflows and integrations | EO Engineer | 40 |  |  | 120 |  | Unit Testing | Customer must provide test scenarios and validation criteria
Testing | Performance Testing | Test cluster performance with load and capacity testing | EO Engineer | 32 |  |  | 140 |  | Integration Testing | Load testing with realistic application workloads
Testing | Security Testing | Perform security validation of RBAC policies and network controls | EO Engineer | 24 |  |  | 175 |  | Performance Testing | Includes vulnerability scanning and compliance validation
Testing | User Acceptance Testing | Coordinate UAT with development teams and stakeholders | EO Engineer | 32 |  |  | 150 |  | Security Testing | Developer validation of platform capabilities and workflows
Deployment | Production Deployment | Deploy OpenShift platform to production with validation | EO Engineer | 32 |  |  | 160 |  | User Acceptance Testing | Production cluster deployment with smoke testing
Deployment | Go-Live Support | Provide support during initial production application deployments | EO Engineer | 80 |  |  | 110 |  | Production Deployment | Daily monitoring rapid issue response during hypercare period
Training | Developer Training | Train developers on OpenShift containerization and CI/CD | EO Engineer | 40 |  |  | 130 |  | Production Deployment | Includes hands-on training with Tekton ArgoCD and platform workflows
Training | Administrator Training | Train platform administrators on OpenShift operations | EO Engineer | 40 |  |  | 130 |  | Developer Training | Platform management monitoring troubleshooting and upgrades
Training | Documentation | Create runbooks user guides and operational documentation | EO Engineer | 32 |  |  | 110 |  | Administrator Training | Deliverable: Operations runbooks troubleshooting guides and procedures
Closeout | Knowledge Transfer | Transfer platform ownership to operations team | EO Engineer | 24 |  |  | 140 |  | Documentation | Comprehensive handover including architecture procedures and escalation
Closeout | Performance Baseline | Establish platform performance metrics and monitoring baselines | EO Engineer | 16 |  |  | 130 |  | Knowledge Transfer | Establishes SLAs performance metrics and operational dashboards
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | OpenShift architecture review and technical escalation support
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes weekly status risk management and stakeholder coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers in Estimate Settings based on cluster size and complexity

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Red Hat Partner Services Credit | -5000 | Red Hat partner credit for OpenShift implementation and architecture services
Implementation Discount | 0 | No implementation discount applicable
TOTAL