## Cover
[DOCUMENT TITLE]
Level of Effort
MICROSOFT - Cyber-Security - Cmmc Enclave
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
CMMC Requirements | CMMC Level | Level 2 (Advanced Cyber Hygiene) | Level 2 | Level 3 | Level 4 or 5 | CMMC certification level and NIST control requirements
CMMC Requirements | NIST 800-171 Controls | 110 security requirements | 110 controls | 110 + Level 3 | Additional Level 4/5 controls | Security control implementation complexity
User Base | CUI User Count | 50 users accessing CUI | 50 users | 100-200 users | 300+ users | Users requiring CUI access and GCC High licenses
User Base | User Roles | 3 roles (CUI processor admin reviewer) | 2-3 standard roles | 4-6 roles | 8+ roles with complex permissions | CUI processor administrator reviewer roles
M365 GCC High | M365 Tenant | GCC High (FedRAMP High) | GCC High only | GCC High + DoD | Multiple tenants or complex federation | Microsoft 365 GCC High tenant complexity
M365 GCC High | M365 Services | Exchange SharePoint Teams OneDrive Purview | Core services | Core + advanced | Full suite + custom | GCC High services and features enabled
M365 GCC High | Email Migration Volume | 100 GB total mailbox data | 100 GB | 250 GB | 1+ TB | Email migration from commercial or on-premises
M365 GCC High | File Migration Volume | 500 GB SharePoint and OneDrive | 500 GB | 2 TB | 10+ TB | File migration to GCC High SharePoint
Azure Government | Azure Gov Resources | 5 VMs 2TB storage VNet ExpressRoute | Basic infrastructure | Standard infrastructure | Complex multi-tier | Azure Government compute storage network
Azure Government | Sentinel Capacity | 100GB/month log ingestion | 100GB/month | 250GB/month | 1+ TB/month | Sentinel SIEM log ingestion and retention
Azure Government | Defender Coverage | All Azure resources and M365 workloads | Basic coverage | Standard coverage | Advanced threat protection | Defender for Cloud coverage scope
Security & Compliance | Authentication | CAC/PIV smart card with MFA | CAC/PIV basic | CAC/PIV + biometric | Advanced federated identity | DoD smart card authentication complexity
Security & Compliance | Identity Platform | Azure AD GCC High with SSO | Azure AD GCC High | Federated multi-forest | Complex hybrid identity | Identity and access management complexity
Security & Compliance | Data Encryption | FIPS 140-2 encryption at rest and transit | FIPS 140-2 basic | FIPS 140-2 advanced | Custom encryption + HSM | Encryption and cryptographic requirements
Technical Environment | Availability Requirements | 99.9% (GCC High SLA) | 99.9% standard | 99.95% high availability | 99.99% mission critical | GCC High and Azure Government SLA
Technical Environment | Infrastructure Complexity | Azure Gov + M365 GCC High hybrid | Basic hybrid | Standard hybrid | Complex multi-cloud | Hybrid cloud architecture complexity
Technical Environment | Deployment Regions | Single Azure Gov region (us-gov-virginia) | Single region | 2 regions | Multi-region global | Azure Government geographic distribution
C3PAO Assessment | Assessment Timeline | Month 6 C3PAO assessment | Month 6 | Month 9 | Month 12+ | CMMC certification timeline
Environment | Deployment Environments | 2 environments (dev prod) | 2 environments (dev prod) | 3 environments (dev staging prod) | 4+ environments with pipelines | Environment management for CMMC

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (NIST Gap Assessment, Architecture Design, C3PAO Selection)
Planning | PLANNING_MX | 1 | All Planning phase tasks (GCC High Deployment, Azure Gov Infrastructure, CAC/PIV Authentication)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Sentinel SIEM, Security Monitoring, CMMC Controls Implementation)
Testing | TESTING_MX | 1 | All Testing phase tasks (Control Testing, Compliance Validation, C3PAO Preparation)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, C3PAO Assessment, Certification)
Training | TRAINING_MX | 1 | All Training phase tasks (ISSO/ISSM Training, Security Operations Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Ongoing Compliance Management)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | NIST 800-171 Gap Assessment | Conduct comprehensive gap assessment across 14 control families | EO Engineer | 40 |  |  | 175 |  |  | Evaluate current SPRS score and NIST 800-171 compliance posture
Discovery | GCC High Architecture Design | Design Microsoft 365 GCC High tenant and services architecture | EO Engineer | 32 |  |  | 200 |  |  | GCC High tenant Exchange SharePoint Teams OneDrive architecture
Discovery | Azure Government Design | Design Azure Government infrastructure for CUI workloads | EO Engineer | 24 |  |  | 200 |  |  | VMs storage networking ExpressRoute design
Discovery | C3PAO Selection | Research and select CMMC Third-Party Assessment Organization | EO Engineer | 16 |  |  | 150 |  |  | C3PAO qualification and engagement planning
Planning | GCC High Tenant Provisioning | Provision and configure Microsoft 365 GCC High tenant | EO Engineer | 24 |  |  | 180 |  | GCC High Architecture Design | Domain verification licensing and tenant configuration
Planning | Exchange Online Deployment | Deploy Exchange Online GCC High with archiving and eDiscovery | EO Engineer | 32 |  |  | 175 |  | GCC High Tenant Provisioning | CUI email with 10-year retention and compliance
Planning | SharePoint Teams Deployment | Deploy SharePoint and Teams for CUI collaboration | EO Engineer | 24 |  |  | 175 |  | Exchange Online Deployment | Secure collaboration meeting CMMC requirements
Planning | Email Migration | Migrate email from commercial or on-premises to GCC High | EO Engineer | 16 |  |  | 160 |  | SharePoint Teams Deployment | 100GB mailbox migration with zero data loss
Development | Azure Government Infrastructure | Deploy Azure Government VMs storage networking | EO Engineer | 40 |  |  | 180 |  | Azure Government Design | 5 VMs 2TB storage VNet ExpressRoute deployment
Development | CAC/PIV Authentication | Implement CAC/PIV smart card authentication with Azure AD | EO Engineer | 32 |  |  | 190 |  | Azure Government Infrastructure | DoD smart card integration with conditional access
Development | Sentinel SIEM Deployment | Deploy Sentinel SIEM with 100GB/month log ingestion | EO Engineer | 40 |  |  | 185 |  | CAC/PIV Authentication | Security monitoring and incident response playbooks
Development | Defender for Cloud | Deploy Defender for Cloud with CMMC compliance monitoring | EO Engineer | 24 |  |  | 180 |  | Sentinel SIEM Deployment | Compliance posture management and vulnerability assessment
Development | Microsoft Purview | Implement Purview for DLP information protection and retention | EO Engineer | 24 |  |  | 175 |  | Defender for Cloud | Data loss prevention and compliance policies
Testing | NIST Control Testing | Validate all 110 NIST 800-171 security requirements | EO Engineer | 40 |  |  | 170 |  | Microsoft Purview | Automated and manual testing of security controls
Testing | Security Assessment | Conduct vulnerability scanning and penetration testing | EO Engineer | 24 |  |  | 190 |  | NIST Control Testing | External threat simulation and insider threat testing
Testing | Compliance Audit | Internal compliance audit against CMMC Level 2 requirements | EO Engineer | 32 |  |  | 185 |  | Security Assessment | Validate all controls before C3PAO assessment
Deployment | System Security Plan | Develop SSP documenting GCC High and Azure Gov architecture | EO Engineer | 24 |  |  | 175 |  | Compliance Audit | CMMC documentation and evidence artifacts
Deployment | C3PAO Assessment | Support C3PAO assessment and finding remediation | EO Engineer | 40 |  |  | 180 |  | System Security Plan | Independent CMMC Level 2 assessment support
Deployment | CMMC Certification | Complete certification and DoD contract enablement | EO Engineer | 16 |  |  | 150 |  | C3PAO Assessment | Final certification approval and documentation
Training | ISSO/ISSM Training | Train CMMC compliance lead on control management | EO Engineer | 16 |  |  | 160 |  | CMMC Certification | NIST 800-171 control management and recertification
Training | Security Operations Training | Train security team on Sentinel and Defender operations | EO Engineer | 16 |  |  | 150 |  | ISSO/ISSM Training | SIEM monitoring and incident response procedures
Training | Documentation | Create operations runbook and CMMC maintenance procedures | EO Engineer | 16 |  |  | 140 |  | Security Operations Training | Ongoing compliance management documentation
Closeout | Knowledge Transfer | Transfer CMMC compliance ownership to client team | EO Engineer | 16 |  |  | 150 |  | Documentation | Comprehensive handover of CMMC operations
Closeout | Compliance Monitoring Setup | Establish continuous compliance monitoring and reporting | EO Engineer | 8 |  |  | 140 |  | Knowledge Transfer | Ongoing NIST 800-171 control monitoring setup
Management | Technical Leadership | Quarterback technical oversight and CMMC architecture review | EO Quarterback |  |  |  | 200 |  |  | CMMC compliance architecture and C3PAO coordination
Management | Project Management | Project coordination and C3PAO assessment management | EO Project Manager |  |  |  | 150 |  |  | Stakeholder coordination and certification timeline management
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers based on CMMC scope complexity

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Microsoft Partner Services Credit | 0 | No Microsoft partner credits available for government licensing (GCC High)
Implementation Discount | 0 | No implementation discount applicable
TOTAL |  | Total Cost - no credits available for GCC High government licensing