## Cover
[DOCUMENT TITLE]
Level of Effort
CISCO - Cyber-Security - Secure Access
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Primary Features/Capabilities | ISE for 1000 users 2000 devices | ISE for 1000 users 2000 devices | ISE for 3000 users 5000 devices | ISE for 10000+ users 15000+ devices | Network access control scope
Solution Scope | Customization Level | Standard ISE deployment | Standard 802.1X deployment | Custom policies and portals | Extensive custom integrations and workflows | Configuration vs customization
Integration | External System Integrations | 2 systems (AD + switches) | 2 systems (AD + network) | 4 systems (AD ITSM switches WLC) | 6+ systems including MDM and SIEM | Active Directory and network integration
Integration | Data Sources | User identity only | User identity | Identity + device posture + MDM | Identity + posture + MDM + threat feeds | Authentication and compliance data
User Base | Total Users | 1000 employees and guests | 1000 users | 3000 users and guests | 10000+ users | Concurrent authenticated users
User Base | User Roles | 2 roles (employee + guest) | 2 roles | 4 roles (employee contractor guest IoT) | 6+ roles with complex segmentation | TrustSec security groups
Data Volume | Data Processing Volume | 2000 endpoint authentications | 2000 endpoints | 5000 endpoints | 15000+ endpoints | Network access endpoints
Data Volume | Data Storage Requirements | 100 GB (90-day logs) | 100 GB | 500 GB (1-year logs) | 2+ TB (multi-year logs) | Authentication and authorization logs
Technical Environment | Deployment Regions | Single site | Single site | 2 sites with HA | Multi-site distributed deployment | ISE node distribution
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | ISE uptime SLA
Technical Environment | Infrastructure Complexity | Basic campus network | Basic campus | Campus + branch + wireless | Complex multi-domain fabric | Network infrastructure complexity
Security & Compliance | Security Requirements | Basic 802.1X authentication | Basic 802.1X | TrustSec + posture + BYOD | Advanced TrustSec + threat integration | Security architecture and features
Security & Compliance | Compliance Frameworks | Basic logging | Basic logging | PCI DSS or HIPAA | Multiple regulatory frameworks | Compliance automation requirements
Performance | Performance Requirements | Standard authentication speed | Standard speed | Fast authentication + profiling | Optimized high-throughput | Authentication performance targets
Environment | Deployment Environments | Production only | Production only | Lab + production | Lab + staging + production | Testing and validation environments

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Network Assessment, Security Requirements, Integration Analysis)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Policy Design, Architecture Design, Migration Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (ISE Deployment, Policy Configuration, Integration Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Lab Testing, Pilot Validation, Failover Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Rollout, Policy Enforcement, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Helpdesk Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 0.25 | Project management and technical leadership (25% of total engineering effort)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Estimated Hours | Rate | Cost Estimate | Dependencies | Risk Level | Notes
Discovery | Network Assessment | Assess network infrastructure for 802.1X readiness |  | 40 | 225 |  |  | Medium | Switches WLCs and 802.1X compatibility
Discovery | Security Requirements | Gather access control and segmentation requirements |  | 32 | 200 |  |  | Medium | Policy framework and TrustSec design
Discovery | Active Directory Analysis | Analyze AD structure and identity sources |  | 24 | 200 |  |  | Medium | AD integration and authentication
Discovery | BYOD and Guest Requirements | Define BYOD and guest access requirements |  | 24 | 175 |  |  | Medium | Self-service portals and workflows
Planning | ISE Architecture | Design ISE deployment architecture (2-node HA) |  | 48 | 225 |  | Assessment | Medium | Primary and secondary ISE nodes
Planning | Access Policy Framework | Design authentication authorization and segmentation policies |  | 60 | 225 |  | Requirements | High | 802.1X MAB guest BYOD policies
Planning | TrustSec Design | Design TrustSec SGT and security group policies |  | 40 | 225 |  | Policy Framework | Medium | Micro-segmentation and enforcement
Planning | Rollout Strategy | Plan phased rollout and pilot approach |  | 32 | 200 |  | Policy Design | Medium | Pilot department and deployment waves
Development | ISE Deployment | Deploy ISE appliances (primary + secondary HA) |  | 80 | 225 |  | Architecture | Medium | HA pair installation and licensing
Development | Active Directory Integration | Integrate ISE with Active Directory |  | 30 | 200 |  | ISE Deploy | Medium | LDAP integration and testing
Development | Policy Configuration | Configure authentication and authorization policies |  | 60 | 200 |  | AD Integration | High | 802.1X wired wireless and MAB
Development | BYOD Portal Configuration | Configure self-service BYOD onboarding portal |  | 40 | 200 |  | Policy Config | Medium | Certificate provisioning for iOS Android
Development | Guest Portal Configuration | Configure guest access portal and sponsor workflow |  | 40 | 200 |  | Policy Config | Medium | Self-registration and sponsor approval
Development | TrustSec Configuration | Configure TrustSec SGTs and enforcement policies |  | 50 | 225 |  | Policy Config | Medium | Security group tags and matrix
Development | Network Integration | Configure switches and WLCs for 802.1X |  | 50 | 200 |  | ISE Policies | High | AAA configuration and RADIUS setup
Testing | Lab Validation | Test ISE policies in lab environment |  | 32 | 200 |  | Config Complete | Medium | End-to-end authentication testing
Testing | Pilot Deployment | Deploy to pilot department (50-100 users) |  | 40 | 175 |  | Lab Testing | High | IT department or friendly users
Testing | BYOD Testing | Test BYOD onboarding for iOS and Android |  | 24 | 175 |  | Pilot Deploy | Medium | Self-service certificate provisioning
Testing | Failover Testing | Test ISE HA failover scenarios |  | 16 | 200 |  | Pilot Success | Medium | Primary-secondary failover testing
Deployment | Production Rollout Phase 1 | Deploy wired 802.1X to remaining users |  | 60 | 200 |  | Testing Complete | High | Phased wired authentication rollout
Deployment | Production Rollout Phase 2 | Deploy wireless 802.1X and BYOD |  | 50 | 200 |  | Phase 1 Success | High | Corporate and BYOD SSIDs
Deployment | Guest WiFi Deployment | Enable guest access portal and workflows |  | 24 | 175 |  | Phase 2 Success | Medium | Guest portal and sponsor process
Deployment | TrustSec Enforcement | Enable TrustSec policy enforcement |  | 40 | 225 |  | All Rollouts | High | SGT tagging and enforcement
Deployment | Hypercare Support | Provide post-deployment stabilization support |  | 60 | 150 |  | Deployment Complete | Medium | 4-week hypercare period
Training | Administrator Training | Train ISE administrators on operations |  | 24 | 175 |  | Deployment | Low | Policy management and troubleshooting
Training | Helpdesk Training | Train helpdesk on user support and issues |  | 16 | 150 |  | Admin Training | Low | User authentication and BYOD support
Training | Documentation | Create runbooks user guides and SOPs |  | 32 | 150 |  |  | Low | Operational procedures and guides
Closeout | Knowledge Transfer | Transfer ISE solution to operations team |  | 16 | 175 |  | Training Complete | Low | Operational handoff and escalation
Closeout | Performance Baseline | Establish authentication metrics and KPIs |  | 16 | 175 |  | Hypercare | Low | Authentication success rate and SLA
Management | Technical Leadership | Technical quarterback and architecture oversight |  |  | 225 |  |  | Medium | 25% of total engineering effort
Management | Project Management | Project coordination and stakeholder management |  |  | 175 |  |  | Low | 20% of total engineering effort
|  |  | TOTAL HOURS |  | TOTAL COST |  |  |  | Total ISE Secure Access implementation cost

## Credits
CREDITS
Category | Credit Type | Credit Amount | Credit Comments
Software | ISE License Promotion | -10000 | Year 1 ISE Plus license 20% discount promotion
Hardware | Appliance Trade-In | 0 | No hardware trade-in available
Professional Services | Implementation Services | 0 | No professional services credits available
Support & Maintenance | Support Credit | 0 | No support renewal credits available