## Cover
Test Plan
Generated: | November 27, 2025
Solution: | Openshift Container Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | Cluster API Connectivity | Validate OpenShift API server is accessible and responsive | Cluster deployed; kubeconfig configured | 1. Execute oc login command; 2. Run oc get nodes; 3. Verify API response time < 2 seconds | API accessible; all nodes listed; response within SLA | Critical | Not Started
FT-002 | Unit | Control Plane Health | Verify all control plane components are operational | All master nodes running | 1. Check etcd cluster health; 2. Verify API server pods; 3. Check controller-manager; 4. Verify scheduler pods | All control plane components in Running state | Critical | Not Started
FT-003 | Unit | Worker Node Registration | Validate worker nodes are properly registered and ready | Worker nodes provisioned | 1. Run oc get nodes; 2. Verify Ready status; 3. Check node conditions; 4. Validate node labels | All 3 worker nodes in Ready status | Critical | Not Started
FT-004 | Unit | Pod Scheduling | Verify pods can be scheduled on worker nodes | Cluster operational; worker nodes ready | 1. Deploy test pod; 2. Verify pod scheduled; 3. Check pod running; 4. Validate node placement | Pod scheduled and running within 60 seconds | High | Not Started
FT-005 | Integration | AD/LDAP Authentication | Validate user authentication against corporate LDAP | OAuth configured; LDAP connectivity | 1. Login via OpenShift console; 2. Enter AD credentials; 3. Verify user authenticated; 4. Check group membership | User authenticated; groups mapped to RBAC roles | Critical | Not Started
FT-006 | Integration | RBAC Authorization | Verify role-based access control enforcement | LDAP integration complete; RBAC configured | 1. Login as admin user; 2. Verify admin access; 3. Login as developer; 4. Verify restricted access | Access granted/denied per RBAC configuration | Critical | Not Started
FT-007 | Integration | OpenShift Pipelines | Validate Tekton pipeline execution end-to-end | Pipelines operator installed; test repo ready | 1. Create PipelineRun; 2. Monitor task execution; 3. Verify build stage; 4. Check deploy stage | Pipeline completes successfully within 15 minutes | High | Not Started
FT-008 | Integration | ArgoCD GitOps Sync | Validate ArgoCD application synchronization | ArgoCD deployed; Git repo configured | 1. Create ArgoCD application; 2. Trigger sync; 3. Verify resources created; 4. Check sync status | Application synced; resources deployed correctly | High | Not Started
FT-009 | Integration | Quay Registry Push/Pull | Validate container image push and pull operations | Quay deployed; credentials configured | 1. Build container image; 2. Push to Quay; 3. Pull from Quay; 4. Verify image integrity | Image pushed and pulled successfully | High | Not Started
FT-010 | Integration | Prometheus Metrics Collection | Verify metrics collection from cluster and applications | Monitoring stack deployed | 1. Access Prometheus UI; 2. Query cluster metrics; 3. Verify application metrics; 4. Check metric retention | Metrics collected; queries return expected data | High | Not Started
FT-011 | Integration | Grafana Dashboard Display | Validate Grafana dashboards display metrics correctly | Prometheus operational; dashboards imported | 1. Access Grafana; 2. Load cluster dashboard; 3. Verify data displayed; 4. Check all panels | Dashboards display real-time metrics | Medium | Not Started
FT-012 | Integration | EFK Log Aggregation | Verify log collection and aggregation in Kibana | Logging stack deployed | 1. Generate application logs; 2. Access Kibana; 3. Search for logs; 4. Verify log timestamps | Logs aggregated; searchable within 5 minutes | High | Not Started
FT-013 | System | Application Deployment E2E | Complete application deployment workflow | All platform components operational | 1. Push code to Git; 2. Pipeline triggered; 3. Image built; 4. ArgoCD syncs; 5. App running | Application deployed via GitOps within 20 minutes | Critical | Not Started
FT-014 | System | Self-Service Namespace | Developer self-service namespace provisioning | Developer RBAC configured | 1. Login as developer; 2. Create namespace; 3. Deploy application; 4. Verify access controls | Namespace created; deployment successful | High | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | Cluster Availability | Validate 99.5% uptime requirement | Production cluster operational; monitoring active | 1. Monitor cluster for 30 days; 2. Track any downtime; 3. Calculate availability percentage | Cluster maintains 99.5%+ availability | Critical | Not Started
NFT-002 | Performance | API Response Time | Verify API response time under normal load | Cluster under typical workload | 1. Execute API calls; 2. Measure response times; 3. Calculate p95 latency; 4. Compare to baseline | API p95 response time < 500ms | Critical | Not Started
NFT-003 | Performance | Pod Startup Time | Validate container startup time requirements | Worker nodes operational; images cached | 1. Deploy new pod; 2. Measure time to running; 3. Repeat 10 times; 4. Calculate average | Average pod startup < 45 seconds | High | Not Started
NFT-004 | Performance | Pipeline Duration | Verify CI/CD pipeline execution time | Pipelines configured; source code ready | 1. Execute standard pipeline; 2. Measure total duration; 3. Repeat 5 times; 4. Calculate average | Pipeline completes within 15 minutes average | High | Not Started
NFT-005 | Performance | Concurrent Deployments | Validate platform handles concurrent deployments | Multiple applications configured | 1. Trigger 10 simultaneous deployments; 2. Monitor resource usage; 3. Verify all complete; 4. Check for failures | All deployments complete without resource contention | Medium | Not Started
NFT-006 | Performance | Node Failure Recovery | Verify workload recovery after node failure | Multi-node deployment active | 1. Simulate worker node failure; 2. Monitor pod rescheduling; 3. Measure recovery time; 4. Verify application availability | Pods rescheduled within 5 minutes; zero data loss | Critical | Not Started
NFT-007 | Security | Network Policy Enforcement | Validate network policies restrict traffic correctly | Network policies deployed | 1. Test allowed traffic flows; 2. Test denied traffic flows; 3. Verify policy logging; 4. Check egress controls | Traffic allowed/denied per policy configuration | Critical | Not Started
NFT-008 | Security | Pod Security Admission | Verify pod security policies prevent privileged containers | PSA configured; restricted profile active | 1. Deploy privileged pod; 2. Verify admission denied; 3. Deploy compliant pod; 4. Verify allowed | Privileged pods rejected; compliant pods allowed | Critical | Not Started
NFT-009 | Security | Secret Encryption | Validate etcd encryption for Kubernetes secrets | Encryption enabled at cluster level | 1. Create secret; 2. Verify encrypted in etcd; 3. Retrieve via API; 4. Confirm decrypted correctly | Secrets encrypted at rest; accessible via API | Critical | Not Started
NFT-010 | Security | TLS Certificate Validation | Verify all endpoints use valid TLS certificates | Certificates provisioned | 1. Check API server cert; 2. Check router certs; 3. Verify cert chain; 4. Check expiration dates | All certificates valid; no warnings | Critical | Not Started
NFT-011 | Security | Vulnerability Scan | Validate container images pass security scanning | Quay scanning enabled | 1. Push test image; 2. Run vulnerability scan; 3. Review findings; 4. Verify no critical CVEs | No critical vulnerabilities; medium remediated | Critical | Not Started
NFT-012 | Reliability | ETCD Backup Restore | Validate backup and restore procedures work correctly | Backup configuration complete | 1. Create ETCD backup; 2. Simulate data loss; 3. Execute restore; 4. Verify cluster state | Cluster restored to backup state within 30 minutes | Critical | Not Started
NFT-013 | Reliability | Storage Persistence | Verify persistent volumes survive pod restarts | PVC provisioned; data written | 1. Create PVC and write data; 2. Delete pod; 3. Recreate pod; 4. Verify data persisted | Data persists across pod lifecycle | High | Not Started
NFT-014 | Reliability | Horizontal Pod Autoscaling | Validate HPA scales pods based on load | HPA configured; metrics server active | 1. Apply load to application; 2. Monitor pod count; 3. Verify scale-up; 4. Remove load; 5. Verify scale-down | Pods scale up/down based on CPU thresholds | High | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Business Process | Developer Self-Service Workflow | Validate developers can deploy applications independently | Developer training complete; RBAC configured | 1. Login as developer; 2. Create namespace; 3. Deploy from template; 4. View application | Developer deploys without operations intervention | High | Not Started
UAT-002 | Business Process | CI/CD Pipeline Workflow | Validate complete GitOps workflow from code to deployment | Git repo access; pipeline configured | 1. Commit code change; 2. Pipeline auto-triggers; 3. Image built and scanned; 4. ArgoCD deploys | Code changes deployed automatically via pipeline | High | Not Started
UAT-003 | Business Process | Application Monitoring | Validate operations team can monitor applications | Monitoring stack operational; dashboards configured | 1. Access Grafana; 2. View application metrics; 3. Check alerting rules; 4. Verify notification | Operations can monitor all deployed applications | High | Not Started
UAT-004 | Business Process | Log Analysis Workflow | Validate support team can troubleshoot via logs | EFK stack operational | 1. Access Kibana; 2. Search application logs; 3. Filter by time range; 4. Export relevant logs | Support can locate and analyze application logs | Medium | Not Started
UAT-005 | User Interface | OpenShift Console Navigation | Validate administrators can manage cluster via console | Admin credentials; console accessible | 1. Login to console; 2. Navigate workloads; 3. View node status; 4. Access project quotas | Console provides full cluster visibility | High | Not Started
UAT-006 | User Interface | ArgoCD Application Management | Validate GitOps management via ArgoCD UI | ArgoCD accessible; applications deployed | 1. Login to ArgoCD; 2. View sync status; 3. Trigger manual sync; 4. Review health status | ArgoCD UI shows accurate application state | Medium | Not Started
UAT-007 | User Interface | Quay Registry Management | Validate registry management via Quay UI | Quay accessible; images pushed | 1. Login to Quay; 2. Browse repositories; 3. View vulnerability scans; 4. Manage image tags | Quay UI provides image management capabilities | Medium | Not Started
UAT-008 | Business Process | Incident Response Workflow | Validate operations can respond to platform alerts | Alerting configured; PagerDuty integrated | 1. Trigger test alert; 2. Verify PagerDuty notification; 3. Follow runbook; 4. Resolve alert | Operations receives alerts and can respond per runbook | High | Not Started
UAT-009 | Business Process | Capacity Management | Validate operations can monitor and plan capacity | Metrics collection active; quotas configured | 1. Review resource utilization; 2. Check quota usage; 3. Generate capacity report; 4. Identify growth needs | Operations can track and forecast capacity requirements | Medium | Not Started
UAT-010 | Business Process | Platform Update Process | Validate operations can perform platform updates | Update documentation available; test cluster ready | 1. Review release notes; 2. Execute update in test; 3. Verify cluster health; 4. Document results | Operations can safely update platform following procedures | High | Not Started