## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Ansible Automation Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 2 days | Week 1 | Week 1 | None | Project Manager | Complete
Discovery | IT Operations Assessment | 5 days | Week 1 | Week 2 | Project Kickoff | Business Analyst | Complete
Discovery | Automation Opportunity Analysis | 5 days | Week 2 | Week 3 | Operations Assessment | Automation Architect | Complete
Discovery | Platform Requirements Gathering | 5 days | Week 2 | Week 3 | Operations Assessment | Solution Architect | Complete
Discovery | Architecture Design Sign-off | 3 days | Week 3 | Week 3 | Requirements Gathering | Solution Architect | Complete
Platform | Cloud Infrastructure Provisioning | 5 days | Week 4 | Week 5 | Architecture Sign-off | Cloud Engineer | Complete
Platform | Controller Cluster Deployment | 5 days | Week 5 | Week 6 | Infrastructure Provisioning | Platform Engineer | Complete
Platform | Execution Node Setup (4 nodes) | 3 days | Week 5 | Week 6 | Controller Deployment | Platform Engineer | Complete
Platform | PostgreSQL HA Configuration | 3 days | Week 5 | Week 6 | Controller Deployment | Database Engineer | Complete
Platform | Private Automation Hub Setup | 3 days | Week 6 | Week 6 | Controller Deployment | Platform Engineer | Complete
Platform | LDAP/AD SSO Integration | 5 days | Week 6 | Week 7 | Hub Setup | Security Architect | Complete
Platform | RBAC Configuration | 3 days | Week 7 | Week 7 | SSO Integration | Security Architect | Complete
Integration | HashiCorp Vault Integration | 5 days | Week 7 | Week 8 | RBAC Configuration | Integration Engineer | Complete
Integration | ServiceNow Connector Setup | 5 days | Week 8 | Week 9 | Vault Integration | Integration Engineer | Complete
Integration | Monitoring Webhook Configuration | 3 days | Week 9 | Week 9 | ServiceNow Setup | Integration Engineer | Complete
Integration | Git Repository Integration | 3 days | Week 9 | Week 10 | Monitoring Setup | DevOps Engineer | Complete
Development | Playbook Standards Definition | 5 days | Week 8 | Week 9 | Platform Ready | Automation Architect | Complete
Development | Server Playbooks (25) | 10 days | Week 9 | Week 11 | Standards Definition | Automation Engineer | Complete
Development | Server Playbooks (25 more) | 10 days | Week 11 | Week 13 | First 25 Complete | Automation Engineer | Complete
Development | Network Playbooks (30) | 10 days | Week 11 | Week 14 | Standards Definition | Network Automation | Complete
Development | Cloud/Compliance Playbooks (20) | 10 days | Week 13 | Week 16 | Server Playbooks Done | Automation Engineer | Complete
Development | Self-Service Portal Config | 5 days | Week 14 | Week 15 | Playbooks Development | Platform Engineer | Complete
Development | Event-Driven Automation Setup | 5 days | Week 15 | Week 16 | Portal Configuration | Automation Engineer | Complete
Test | Functional Testing | 7 days | Week 16 | Week 17 | All Playbooks Complete | QA Team | Complete
Test | Performance Testing | 5 days | Week 17 | Week 18 | Functional Testing | Performance Engineer | Complete
Test | Security Testing | 5 days | Week 17 | Week 18 | Functional Testing | Security Team | Complete
Test | User Acceptance Testing | 5 days | Week 18 | Week 19 | Performance Testing | Business Users | Complete
Test | Go-Live Readiness Review | 2 days | Week 19 | Week 20 | UAT Complete | Project Manager | Complete
Deploy | Production Automation Enablement | 5 days | Week 20 | Week 20 | Go-Live Readiness | Deployment Team | Complete
Deploy | Phased Rollout Execution | 10 days | Week 20 | Week 22 | Initial Enablement | Operations Team | Complete
Training | Administrator Training | 5 days | Week 18 | Week 19 | Platform Testing | Training Team | Complete
Training | Developer Training | 5 days | Week 19 | Week 20 | Admin Training | Training Team | Complete
Closure | Hypercare Support | 20 days | Week 21 | Week 24 | Production Rollout | Support Team | Complete
Closure | Documentation Finalization | 5 days | Week 23 | Week 24 | Hypercare Start | Project Manager | Complete
Closure | Project Closeout Meeting | 1 day | Week 24 | Week 24 | Documentation Complete | Project Manager | Complete

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Assessment Complete | Week 3 | Assessment delivered; architecture approved; playbook roadmap defined | Automation Architect | Complete
M2 | Platform Deployed | Week 6 | HA controller operational; execution nodes active; integrations configured | Platform Engineer | Complete
M3 | 50 Playbooks Ready | Week 12 | 50 playbooks developed; tested in dev; ready for production | Automation Engineer | Complete
M4 | 100 Playbooks Complete | Week 16 | All 100 playbooks developed; integration testing complete; documented | Automation Lead | Complete
M5 | Testing Complete | Week 19 | All test phases passed; zero critical defects; UAT signed off | QA Lead | Complete
M6 | Go-Live | Week 20 | Production automation enabled; self-service operational; monitoring active | Project Manager | Complete
M7 | Project Closure | Week 24 | Hypercare complete; training delivered; documentation handed over | Project Manager | Complete

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Architect | DevOps | SecArch | QA | Ops | NetEng | Client
Project Charter | A | C | I | I | I | I | I | C
Architecture Design | A | R | C | C | I | I | C | I
Security Design | A | C | I | R | I | I | I | C
Platform Deployment | A | C | R | I | I | I | I | I
RBAC Configuration | A | C | C | R | I | I | I | C
Vault Integration | A | C | R | R | I | I | I | I
ServiceNow Integration | A | C | R | I | I | C | I | C
Server Playbooks | A | C | R | I | I | C | I | C
Network Playbooks | A | C | R | I | I | I | R | C
Compliance Playbooks | A | C | R | R | I | I | I | C
Functional Testing | A | I | C | I | R | C | I | C
Security Testing | A | I | I | R | C | I | I | I
UAT Execution | A | I | I | I | R | C | I | R
Administrator Training | A | C | R | I | I | R | I | R
Developer Training | A | R | R | I | I | C | I | R
Production Rollout | A | C | R | C | C | R | C | C
Hypercare Support | A | C | R | I | I | C | C | I
Documentation | A | R | C | C | I | I | I | I
Project Closure | R | C | I | I | I | I | I | A
Legend:
R | A A R: Responsible - Does the work
A | A A R: Accountable - Ultimate ownership
C | A A R: Consulted - Provides input
I | A A R: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on objectives | Project Manager | Week 1 Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and issue escalation | Project Manager | Alternate Tuesdays 14:00
Status Meeting | Weekly | Core project team | Review progress and address blockers | Project Manager | Mondays 10:00
Technical Review | Weekly | Technical leads and architects | Architecture decisions and technical issues | Automation Architect | Wednesdays 14:00
Security Review | Bi-weekly | Security and compliance team | Security posture and policy validation | Security Architect | Alternate Thursdays 11:00
Playbook Review | Weekly | Development and operations teams | Playbook demo and feedback collection | Automation Lead | Fridays 15:00
QA Sync | Weekly | QA and Development teams | Test progress and defect triage | QA Lead | Thursdays 11:00
Training Coordination | Weekly (during training) | Training team and participants | Training logistics and feedback | Training Lead | Mondays 09:00
Go-Live Readiness | Daily (2 weeks pre) | Go-live team | Go-live preparation and checklist | Project Manager | Daily 09:00
Hypercare Check-in | Daily (first 2 weeks) | Support team and operations | Post-go-live health check and issues | Support Lead | Daily 09:00
Project Closeout | Once | All stakeholders | Project review and formal closure | Project Manager | Week 24