## Cover
Test Plan
Generated: | November 27, 2025
Solution: | Ansible Automation Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | Controller API Access | Validate Ansible Controller API endpoint authentication | Controller deployed; Admin credentials available | 1. Send GET request to /api/v2/ping; 2. Authenticate with admin token; 3. Verify response status | API returns 200 OK with pong response and version info | Critical | Not Started
FT-002 | Unit | LDAP Authentication | Validate LDAP SSO integration for user login | LDAP configured; Test user in AD | 1. Navigate to controller login; 2. Enter LDAP credentials; 3. Verify team assignment | User authenticated via LDAP with correct team membership | Critical | Not Started
FT-003 | Unit | Vault Credential Lookup | Validate HashiCorp Vault credential retrieval | Vault integrated; Test secret created | 1. Create credential type for Vault; 2. Configure lookup path; 3. Execute test playbook | Credentials retrieved from Vault without exposure in logs | Critical | Not Started
FT-004 | Integration | Job Template Execution | Validate end-to-end job template workflow | Playbook in project; Inventory configured | 1. Launch job template; 2. Monitor execution progress; 3. Verify host completion status | Job completes successfully with all hosts in OK state | High | Not Started
FT-005 | Integration | ServiceNow Ticket Trigger | Validate ServiceNow webhook job triggering | ServiceNow connector configured; Workflow active | 1. Create ServiceNow incident; 2. Verify webhook received; 3. Check job launched | Job automatically triggered from ServiceNow ticket creation | High | Not Started
FT-006 | Integration | Event-Driven Remediation | Validate monitoring webhook auto-remediation | Event-Driven Ansible configured; Test rulebook active | 1. Simulate monitoring alert; 2. Verify rulebook trigger; 3. Check remediation job | Remediation playbook executes within 60 seconds of alert | High | Not Started
FT-007 | System | Workflow Template Chain | Validate multi-step workflow execution | Multiple job templates defined; Workflow configured | 1. Launch workflow template; 2. Verify sequential execution; 3. Check conditional branches | Workflow completes all steps with correct branching logic | High | Not Started
FT-008 | System | Inventory Sync Dynamic | Validate dynamic inventory sync from cloud | Cloud credentials configured; AWS/Azure account ready | 1. Trigger inventory source sync; 2. Verify host discovery; 3. Check variable population | Hosts discovered with correct groups and host_vars applied | Medium | Not Started
FT-009 | System | Self-Service Portal Access | Validate survey-based job submission | Survey configured; Operator user created | 1. Login as operator; 2. Launch job with survey; 3. Verify parameter application | Job executes with user-provided survey variables correctly applied | Medium | Not Started
FT-010 | Unit | Git Project Sync | Validate SCM project synchronization | Git repo configured; SSH key or token provided | 1. Trigger project sync; 2. Verify playbook files; 3. Check branch/tag selection | Project syncs successfully with correct playbook inventory visible | High | Not Started
FT-011 | Integration | Notification Integration | Validate job notification to external systems | Notification template configured; Slack/email endpoint ready | 1. Execute job template; 2. Verify notification sent; 3. Check notification content | Notifications delivered with job status and execution details | Medium | Not Started
FT-012 | System | RBAC Permission Boundary | Validate role-based access restrictions | Multiple roles configured; Test users assigned | 1. Login as restricted user; 2. Attempt unauthorized action; 3. Verify access denied | Permission denied for operations outside assigned RBAC scope | Critical | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | Concurrent Job Execution | Validate 100 concurrent job capacity | Execution nodes deployed; Test inventory ready | 1. Launch 100 simultaneous jobs; 2. Monitor queue and execution; 3. Measure completion time | All 100 jobs complete within acceptable time without queue backlog | Critical | Not Started
NFT-002 | Performance | Job Execution Speed | Validate playbook execution time targets | Baseline playbooks developed; Target hosts available | 1. Execute standard server config playbook; 2. Measure end-to-end time; 3. Compare to manual baseline | Server configuration completes in under 15 minutes vs 4 hours manual | High | Not Started
NFT-003 | Performance | Controller API Response | Validate API response time under load | Load testing tool configured; API endpoints identified | 1. Generate 500 concurrent API requests; 2. Measure response times; 3. Check error rate | 95% of API requests complete within 2 seconds with less than 1% errors | High | Not Started
NFT-004 | Reliability | Controller HA Failover | Validate controller high availability | HA cluster deployed; Health checks configured | 1. Simulate primary controller failure; 2. Verify automatic failover; 3. Check job continuity | Failover completes within 2 minutes; running jobs resume or restart | Critical | Not Started
NFT-005 | Reliability | Execution Node Recovery | Validate execution node failure handling | Multiple execution nodes active; Jobs running | 1. Terminate execution node; 2. Verify job rescheduling; 3. Check completion status | In-flight jobs rescheduled to healthy nodes; new jobs distributed correctly | High | Not Started
NFT-006 | Reliability | Database Backup Recovery | Validate PostgreSQL backup and restore | Backup schedule configured; Test data populated | 1. Trigger manual backup; 2. Simulate database failure; 3. Restore from backup | Database restored within 1-hour RPO; all job history and configs intact | Critical | Not Started
NFT-007 | Security | Credential Encryption | Validate credential storage encryption | Credentials stored; Database access available | 1. Query credentials table; 2. Verify encrypted storage; 3. Check decryption only during use | All credentials encrypted at rest; plaintext never visible in logs or database | Critical | Not Started
NFT-008 | Security | Audit Log Completeness | Validate comprehensive audit trail | Audit logging enabled; Test operations performed | 1. Perform various operations; 2. Query activity stream; 3. Verify log completeness | All user actions and job executions logged with timestamp and user context | High | Not Started
NFT-009 | Security | Network Isolation | Validate execution node network access | Network policies configured; Firewall rules applied | 1. Attempt unauthorized network access; 2. Verify only permitted connections; 3. Check segmentation | Execution nodes only reach managed hosts on approved ports (SSH/WinRM) | High | Not Started
NFT-010 | Scalability | Execution Node Scaling | Validate adding execution nodes for capacity | Base configuration stable; Additional node ready | 1. Add new execution node; 2. Verify mesh registration; 3. Check job distribution | New node joins mesh within 5 minutes and receives job assignments | Medium | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Business Process | Server Provisioning Workflow | Validate complete server deployment automation | Server playbooks developed; Cloud credentials configured | 1. Request new server via portal; 2. Verify automated provisioning; 3. Confirm configuration complete | Server provisioned and configured end-to-end without manual intervention | High | Not Started
UAT-002 | Business Process | Network Configuration Change | Validate automated network device update | Network playbooks tested; Change window approved | 1. Submit network change request; 2. Execute configuration playbook; 3. Verify device state | Network configuration applied correctly in 30 minutes vs 2 days manual | High | Not Started
UAT-003 | Business Process | Compliance Remediation | Validate automated compliance fix workflow | Compliance playbooks ready; Audit report generated | 1. Identify compliance violation; 2. Execute remediation playbook; 3. Verify compliance restored | Security hardening applied automatically; compliance scan passes | High | Not Started
UAT-004 | User Interface | Operator Self-Service | Validate operator job submission experience | Self-service catalog configured; Operator training complete | 1. Login as operations user; 2. Browse job catalog; 3. Submit job with parameters | Operator successfully launches approved automation without admin assistance | Medium | Not Started
UAT-005 | User Interface | Job Monitoring Dashboard | Validate job execution monitoring capability | Jobs executed; Dashboard configured | 1. Navigate to job dashboard; 2. Filter by status and date; 3. Drill into job details | Operations team can monitor job status and troubleshoot failures effectively | Medium | Not Started
UAT-006 | Business Process | Scheduled Maintenance | Validate scheduled automation execution | Schedule configured; Maintenance playbooks ready | 1. Configure maintenance schedule; 2. Verify automatic execution; 3. Check completion report | Scheduled maintenance jobs execute at configured times without manual trigger | Medium | Not Started
UAT-007 | Business Process | Patch Management Automation | Validate OS patching workflow | Patch playbooks developed; Test servers identified | 1. Identify servers requiring patches; 2. Execute patching playbook; 3. Verify patch status | Servers patched successfully with proper reboot handling and verification | High | Not Started
UAT-008 | Integration | ITSM Workflow End-to-End | Validate ServiceNow-triggered automation | ServiceNow workflows configured; Approval chain ready | 1. Create change request in ServiceNow; 2. Verify approval triggers job; 3. Check status sync | Automation triggered by approved change; status updates flow to ServiceNow | High | Not Started
UAT-009 | Business Process | Incident Auto-Remediation | Validate monitoring alert response | Monitoring integration active; Remediation playbooks ready | 1. Trigger test monitoring alert; 2. Verify automatic job launch; 3. Check incident resolution | Alert automatically triggers remediation; incident resolved without manual intervention | High | Not Started
UAT-010 | Business Process | Multi-Environment Deployment | Validate dev-to-prod automation promotion | Multiple environments configured; Promotion workflow ready | 1. Test playbook in dev environment; 2. Promote to production; 3. Execute in prod with approval | Playbook promoted through environments with proper approval gates | Medium | Not Started