## Cover
[VENDOR LOGO]
Level Of Effort Estimate
Presales Document
Generated: | November 18, 2025
Solution: | Virtual Desktop
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Host Pools | 3 host pools | 3 host pools | Enhanced host pools | Enterprise-scale host pools | Sizing parameter for Host Pools
Solution Scope | Application Groups | 5-10 app groups | 5-10 app groups | Enhanced application groups | Enterprise-scale application groups | Sizing parameter for Application Groups
Integration | Identity Integration | Azure AD hybrid join | Azure AD hybrid join | Enhanced identity integration | Enterprise-scale identity integration | Sizing parameter for Identity Integration
Integration | Profile Management | FSLogix profile containers | FSLogix profile containers | Enhanced profile management | Enterprise-scale profile management | Sizing parameter for Profile Management
User Base | Total Users | 200 concurrent users | 200 concurrent users | Enhanced total users | Enterprise-scale total users | Sizing parameter for Total Users
User Base | User Roles | 3 roles (standard power admin) | 3 roles (standard power admin) | Enhanced user roles | Enterprise-scale user roles | Sizing parameter for User Roles
Data Volume | User Profiles | 10 GB per user | 10 GB per user | Enhanced user profiles | Enterprise-scale user profiles | Sizing parameter for User Profiles
Data Volume | Application Data | 500 GB shared storage | 500 GB shared storage | Enhanced application data | Enterprise-scale application data | Sizing parameter for Application Data
Technical Environment | Deployment Regions | Single Azure region (East US) | Single Azure region (East US) | Enhanced deployment regions | Enterprise-scale deployment regions | Sizing parameter for Deployment Regions
Technical Environment | Availability Requirements | Standard (99.9%) | Standard (99.9%) | Enhanced availability requirements | Enterprise-scale availability requirements | Sizing parameter for Availability Requirements
Technical Environment | Infrastructure Complexity | Multi-session Windows 11 hosts | Multi-session Windows 11 hosts | Enhanced infrastructure complexity | Enterprise-scale infrastructure complexity | Sizing parameter for Infrastructure Complexity
Security & Compliance | Security Requirements | Conditional Access MFA Intune | Conditional Access MFA Intune | Enhanced security requirements | Enterprise-scale security requirements | Sizing parameter for Security Requirements
Security & Compliance | Compliance Frameworks | SOC2 | SOC2 | Enhanced compliance frameworks | Enterprise-scale compliance frameworks | Sizing parameter for Compliance Frameworks
Performance | User Experience | Standard latency requirements | Standard latency requirements | Enhanced user experience | Enterprise-scale user experience | Sizing parameter for User Experience
Performance | Graphics Requirements | Standard office workloads | Standard office workloads | Enhanced graphics requirements | Enterprise-scale graphics requirements | Sizing parameter for Graphics Requirements
Environment | Deployment Environments | 2 environments (pilot prod) | 2 environments (pilot prod) | Enhanced deployment environments | Enterprise-scale deployment environments | Sizing parameter for Deployment Environments

## Estimate Settings
INSTRUCTIONS: How to Use Estimate Settings
This sheet contains phase-based multiplier variables that control effort scaling for each project phase.
The EO Sales Engineer updates these multipliers based on customer scope compared to baseline assumptions.
How It Works:
1. Review customer requirements from Discovery Questionnaire
2. Compare customer scope to Baseline Assumptions (see 'Scope Assumptions' sheet)
3. Update YELLOW HIGHLIGHTED multiplier values below (Column C) for each phase
4. All tasks in that phase on the 'LOE' sheet automatically update their Actual Hours
5. Total cost recalculates automatically
Multiplier Guidelines:
• 1.0 = Matches baseline exactly (Small scope)
• 1.5-2.0 = Medium scope (moderately above baseline)
• 2.0-3.0 = Large scope (significantly above baseline)
• 3.0+ = Very large/complex (substantially above baseline, document rationale)
Example: Customer needs comprehensive testing due to compliance → Set TESTING_MX to 2.0
Example: Complex architecture requiring more technical oversight → Set LEADERSHIP_MX to 1.5
ESTIMATE SETTINGS - Update phase multipliers in Column C below:
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks
Planning | PLANNING_MX | 1 | All Planning phase tasks
Development | DEVELOPMENT_MX | 1 | All Development phase tasks
Testing | TESTING_MX | 1 | All Testing phase tasks
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks
Training | TRAINING_MX | 1 | All Training phase tasks
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks
Management | MANAGEMENT_MX | 1.5 | Project Management overhead
Leadership | LEADERSHIP_MX | 1.5 | Technical Leadership overhead

## LOE
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Azure Requirements Gathering | Conduct stakeholder interviews for Azure cloud strategy | EO Engineer | 40 |  |  | 150 |  | $# | ##0"") | $#
Discovery | Current Environment Assessment | Analyze existing infrastructure and Azure readiness | EO Engineer | 32 |  |  | 200 |  | $# | ##0"") | $#
Discovery | Azure Services Assessment | Evaluate Azure services and landing zone requirements | EO Engineer | 24 |  |  | 200 |  | $# | ##0"") | $#
Discovery | Compliance Review | Assess governance security and regulatory requirements | EO Engineer | 16 |  |  | 175 |  | $# | ##0"") | $#
Planning | Azure Landing Zone Design | Design Azure landing zone architecture and governance model | EO Engineer | 48 |  |  | 200 |  | $# | ##0"") | $#
Planning | Identity and Access Design | Design Azure AD integration and access management strategy | EO Engineer | 32 |  |  | 180 |  | $# | ##0"") | $#
Planning | Network Architecture Design | Design Azure networking security and hybrid connectivity | EO Engineer | 24 |  |  | 175 |  | $# | ##0"") | $#
Planning | Project Planning | Develop Azure implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | $# | ##0"") | $#
Development | Management Groups and Subscriptions | Configure Azure management groups subscription structure and policies | EO Engineer | 40 |  |  | 160 |  | $# | ##0"") | $#
Development | Azure Policy Implementation | Implement Azure policies governance controls and compliance | EO Engineer | 60 |  |  | 145 |  | $# | ##0"") | $#
Development | Network Infrastructure | Build Azure networking VNet peering and hybrid connectivity | EO Engineer | 48 |  |  | 140 |  | $# | ##0"") | $#
Development | Identity and Access Implementation | Implement Azure AD integration access controls and SSO | EO Engineer | 40 |  |  | 155 |  | $# | ##0"") | $#
Development | Monitoring and Operations | Build Azure monitoring logging alerting and operational tools | EO Engineer | 32 |  |  | 130 |  | $# | ##0"") | $#
Testing | Unit Testing | Develop automated tests for all solution components | EO Engineer | 32 |  |  | 120 |  | $# | ##0"") | $#
Testing | Integration Testing | Test system integrations data flows and external dependencies | EO Engineer | 40 |  |  | 120 |  | $# | ##0"") | $#
Testing | Performance Testing | Conduct load performance and scalability testing | EO Engineer | 24 |  |  | 140 |  | $# | ##0"") | $#
Testing | Security Testing | Perform security assessments penetration testing and compliance validation | EO Engineer | 16 |  |  | 175 |  | $# | ##0"") | $#
Testing | User Acceptance Testing | Coordinate UAT with business users and stakeholders | EO Engineer | 32 |  |  | 150 |  | $# | ##0"") | $#
Deployment | Production Deployment | Deploy solution to production environment with monitoring | EO Engineer | 24 |  |  | 160 |  | $# | ##0"") | $#
Deployment | Go-Live Support | Provide comprehensive support during initial production rollout | EO Engineer | 48 |  |  | 110 |  | $# | ##0"") | $#
Training | Administrator Training | Train system administrators and technical support teams | EO Engineer | 16 |  |  | 130 |  | $# | ##0"") | $#
Training | End User Training | Train business users on solution functionality and workflows | EO Engineer | 24 |  |  | 120 |  | $# | ##0"") | $#
Training | Documentation | Create comprehensive technical and user documentation | EO Engineer | 32 |  |  | 110 |  | $# | ##0"") | $#
Closeout | Knowledge Transfer | Transfer solution ownership to operations and support teams | EO Engineer | 16 |  |  | 140 |  | $# | ##0"") | $#
Closeout | Performance Baseline | Establish performance metrics monitoring baselines and SLAs | EO Engineer | 8 |  |  | 130 |  | $# | ##0"") | $#
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  | $# | ##0"")
Management | Project Management | Project coordination and management activities | EO Project Manager |  |  | $# | ##0"")
[5 empty] | TOTAL HOURS |  | TOTAL COST |  | $H$33:$H$59) | $# | ##0"") | EO Sales Engineer: Update multipliers based on customer scope