## Cover
[DOCUMENT TITLE]
Level of Effort
CISCO - Devops - Ci Cd Automation
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Primary Features/Capabilities | Ansible + GitLab CI/CD for 100 devices | Ansible + GitLab for 100 devices | Ansible + Terraform + GitLab for 250 devices | Multi-tool stack for 500+ devices | Network automation platform scope
Solution Scope | Customization Level | Standard playbooks and templates | Standard playbooks | Custom playbooks and modules | Extensive custom development and integrations | Ansible and Terraform customization
Integration | External System Integrations | 2 systems (Git + NetBox) | 2 systems (Git + NetBox) | 4 systems (Git NetBox ServiceNow monitoring) | 6+ systems including CMDB and orchestration | ITSM and IPAM integration
Integration | Data Sources | Network device configs | Network device configs | Devices + IPAM + monitoring | Devices + IPAM + monitoring + external data | Configuration and inventory data
User Base | Total Users | 5 network engineers | 5 network engineers | 10 network team members | 20+ distributed automation users | GitLab and AWX users
User Base | User Roles | 2 roles (developer + operator) | 2 roles (developer + operator) | 4 roles with approvers | 6+ roles with complex workflows | RBAC and approval gates
Data Volume | Data Processing Volume | 100 device configs | 100 device configs | 250 device configs | 500+ device configs | Configuration management scope
Data Volume | Data Storage Requirements | 50 GB (Git + backups) | 50 GB | 200 GB | 500+ GB | Git repositories and config backups
Technical Environment | Deployment Regions | Single data center | Single data center | 2 data centers | Multi-region deployment | CI/CD infrastructure distribution
Technical Environment | Availability Requirements | Standard (99%) | Standard (99%) | High availability (99.5%) | Mission critical (99.9%+) | GitLab and AWX uptime requirements
Technical Environment | Infrastructure Complexity | Basic network (single platform) | Basic network | Multi-vendor multi-platform | Complex heterogeneous environment | Network device diversity
Security & Compliance | Security Requirements | Basic Git auth and secrets | Basic Git auth | Vault integration and RBAC | Advanced secrets management and audit | Credential and secrets management
Security & Compliance | Compliance Frameworks | Change tracking only | Change tracking | PCI DSS or SOC 2 | Multiple regulatory frameworks | Audit and compliance automation
Performance | Performance Requirements | Standard deployment speed | Standard speed | Fast parallel deployment | Optimized high-speed automation | Deployment performance targets
Environment | Deployment Environments | Production only | Production only | Lab + production | Lab + staging + production | Testing and validation environments

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Current State Assessment, Tool Selection, Requirements Gathering)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Architecture Design, Workflow Design, Security Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Platform Setup, Playbook Development, Pipeline Configuration)
Testing | TESTING_MX | 1 | All Testing phase tasks (Lab Testing, Integration Testing, Security Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Device Onboarding, Policy Rollout)
Training | TRAINING_MX | 1 | All Training phase tasks (Team Training, Documentation, Knowledge Transfer)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Operational Handoff, Performance Baseline)
Management | MANAGEMENT_MX | 0.25 | Project management and technical leadership (25% of total engineering effort)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Estimated Hours | Rate | Cost Estimate | Dependencies | Risk Level | Notes
Discovery | Automation Assessment | Assess current network automation maturity and processes |  | 40 | 225 |  |  | Medium | Current state and automation roadmap
Discovery | Tool Evaluation | Evaluate automation tools (Ansible Terraform GitLab) |  | 24 | 200 |  |  | Medium | Tool selection and architecture
Discovery | Device Inventory | Inventory 100 devices and platform types |  | 16 | 175 |  |  | Low | Device compatibility assessment
Discovery | Use Case Definition | Define priority automation use cases |  | 24 | 200 |  |  | Medium | VLAN ACL interface routing playbooks
Planning | CI/CD Architecture | Design GitLab CI/CD and runner infrastructure |  | 40 | 225 |  | Assessment | Medium | Pipeline and workflow architecture
Planning | Automation Workflow | Design GitOps workflow and approval processes |  | 32 | 200 |  | Use Cases | Medium | Merge request and deployment workflow
Planning | Security Architecture | Design secrets management and access control |  | 24 | 225 |  | Architecture | Medium | Vault integration and RBAC
Planning | Testing Strategy | Plan lab testing and validation approach |  | 16 | 175 |  | Workflow | Low | GNS3 CML or staging devices
Development | GitLab Deployment | Deploy GitLab and configure CI/CD runners |  | 40 | 225 |  | Architecture | Medium | Self-hosted GitLab Premium setup
Development | NetBox IPAM Setup | Deploy and configure NetBox for network inventory |  | 40 | 200 |  | GitLab Setup | Medium | Source of truth and dynamic inventory
Development | Ansible Playbook Development | Develop 6 core Ansible playbooks for device configs |  | 120 | 200 |  | Planning Complete | High | VLAN ACL interface routing QoS compliance
Development | Terraform Module Development | Develop Terraform modules for ACI DCNM Meraki (optional) |  | 80 | 225 |  | Playbooks | Medium | Infrastructure as Code for SDN
Development | CI/CD Pipeline Configuration | Configure GitLab pipelines for automated testing |  | 60 | 200 |  | Playbooks | Medium | Syntax validation linting pre-deployment tests
Development | Secrets Management | Implement Vault or GitLab secrets management |  | 24 | 200 |  | Security Design | Medium | Credential rotation and access control
Testing | Lab Validation | Test playbooks in lab environment (GNS3/CML) |  | 40 | 200 |  | Playbooks | Medium | Pre-deployment testing and validation
Testing | Integration Testing | Test CI/CD pipeline end-to-end workflows |  | 32 | 175 |  | Pipeline Config | Medium | Commit to deployment workflow
Testing | Rollback Testing | Test automated rollback and failure scenarios |  | 24 | 175 |  | Lab Testing | High | Config restore and recovery procedures
Testing | Security Testing | Validate secrets management and access controls |  | 16 | 200 |  | Secrets Setup | Medium | Credential security and audit logging
Deployment | Production Deployment | Deploy GitLab NetBox and pipelines to production |  | 40 | 200 |  | Testing Complete | Medium | Production infrastructure setup
Deployment | Device Onboarding | Onboard 100 devices for automation management |  | 30 | 175 |  | Prod Deployment | Medium | Device authentication and connectivity
Deployment | Pilot Automation | Execute pilot automations (10-20 devices) |  | 40 | 175 |  | Device Onboarding | High | Validate automation in production
Deployment | Full Rollout | Enable automation for all 100 devices |  | 30 | 175 |  | Pilot Success | Medium | Phased enablement and monitoring
Training | Ansible Training | Train team on Ansible playbooks and best practices |  | 24 | 175 |  | Deployment | Low | Hands-on playbook development
Training | GitLab CI/CD Training | Train team on GitLab workflows and pipelines |  | 16 | 175 |  | Ansible Training | Low | GitOps workflow and merge requests
Training | Documentation | Create runbooks playbook docs and SOPs |  | 40 | 150 |  |  | Low | Operational procedures and guides
Closeout | Knowledge Transfer | Transfer automation platform to operations |  | 16 | 175 |  | Training Complete | Low | Operational handoff and support model
Closeout | Performance Baseline | Establish automation metrics and KPIs |  | 8 | 150 |  | Production Rollout | Low | Deployment frequency error rate metrics
Management | Technical Leadership | Technical quarterback and architecture oversight |  |  | 225 |  |  | Medium | 25% of total engineering effort
Management | Project Management | Project coordination and stakeholder management |  |  | 175 |  |  | Low | 20% of total engineering effort
|  |  | TOTAL HOURS |  | TOTAL COST |  |  |  | Total CI/CD Automation implementation cost

## Credits
CREDITS
Category | Credit Type | Credit Amount | Credit Comments
Software | GitLab License Credit | 0 | No GitLab license credits available
Cloud Infrastructure | Infrastructure Hosting Credit | -1000 | Year 1 cloud hosting credit for GitLab runners
Professional Services | Implementation Services | 0 | No professional services credits available
Support & Maintenance | Support Credit | 0 | No support credits available