## Cover
Requirements
Delivery Document
Generated: | November 13, 2025
Solution: | Document Intelligence
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement_ID | Requirement_Name | Description | Priority | Type | Acceptance_Criteria | Dependencies | Source | Status | Assigned_To | Estimated_Effort | Risk_Level | Validation_Method
Functional | FR001 | Document Upload Capability | System must accept document uploads via web interface and API endpoints | High | Functional | Users can successfully upload PDF JPEG PNG and TIFF files up to 50MB |  | Business Stakeholder | Approved | Development Team | 40 hours | Low | Integration Testing
Functional | FR002 | Multi-format Document Support | Solution must process PDF images and common office document formats | High | Functional | Successful processing of PDF JPG PNG TIFF and basic Office formats with >95% success rate | FR001 | Business Analyst | Approved | AI/ML Engineer | 32 hours | Medium | Unit Testing + UAT
Functional | FR003 | Automated Text Extraction | System must extract text and data from documents using AI services | High | Functional | Text extraction accuracy >98% for typed documents >90% for handwritten content | FR002 | Technical Lead | Approved | AI/ML Engineer | 60 hours | Medium | Performance Testing
Functional | FR004 | Pre-built Model Support | Support for industry-standard document types using pre-built AI models | High | Functional | Invoice receipt and form processing using Azure pre-built models with >95% accuracy | FR003 | Business Stakeholder | Approved | AI/ML Engineer | 24 hours | Low | UAT
Functional | FR005 | Custom Model Training | Ability to train custom models for organization-specific document formats | Medium | Functional | Custom models achieve >90% accuracy for specific document types after training | FR004 | Business Analyst | Approved | AI/ML Engineer | 80 hours | High | Performance Testing
Functional | FR006 | Batch Document Processing | Process multiple documents simultaneously for high-volume scenarios | High | Functional | Process minimum 100 documents in parallel with <10% failure rate | FR003 | Business Stakeholder | Approved | Development Team | 48 hours | Medium | Performance Testing
Functional | FR007 | Real-time Processing | Individual document processing within defined time limits | High | Functional | Single document processing completes within 5 seconds for documents <10 pages | FR003 | Business Stakeholder | Approved | Development Team | 36 hours | Medium | Performance Testing
Functional | FR008 | Data Validation Rules | Implement business rules for extracted data validation and verification | Medium | Functional | Configurable validation rules with 95% accuracy in identifying invalid data | FR003 | Business Analyst | Approved | Development Team | 56 hours | Medium | Unit Testing
Functional | FR009 | Error Handling and Retry | Graceful error handling with automatic retry capabilities | High | Functional | Failed documents automatically retried up to 3 times with appropriate error logging | FR003 | Technical Lead | Approved | Development Team | 32 hours | Low | Integration Testing
Functional | FR010 | Document Classification | Automatically classify documents by type and route appropriately | Medium | Functional | Document classification accuracy >90% with proper routing to designated workflows | FR003 | Business Analyst | Approved | AI/ML Engineer | 44 hours | Medium | UAT
Integration | IR001 | ERP System Integration | Seamless integration with existing ERP systems for data transfer | High | Integration | Extracted data successfully transferred to ERP with >99% accuracy and <5 second latency | FR003 | Integration Specialist | Approved | Integration Team | 72 hours | High | Integration Testing
Integration | IR002 | REST API Endpoints | Comprehensive REST API for all system functions and data access | High | Integration | RESTful API with OpenAPI documentation supporting all core functions |  | Technical Lead | Approved | Development Team | 48 hours | Low | API Testing
Integration | IR003 | Webhook Notifications | Real-time notifications for processing events and status updates | Medium | Integration | Webhook delivery within 5 seconds of event with 99% reliability | IR002 | Technical Lead | Approved | Development Team | 28 hours | Low | Integration Testing
Integration | IR004 | Database Connectivity | Direct database integration for storing and retrieving processed results | Medium | Integration | Database operations complete within 2 seconds with ACID compliance |  | Database Administrator | Approved | Database Team | 40 hours | Medium | Unit Testing
Integration | IR005 | File System Integration | Integration with network file shares and document management systems | Low | Integration | Automated file pickup and delivery with support for SMB and FTP protocols |  | Integration Specialist | Approved | Integration Team | 36 hours | Medium | Integration Testing
Performance | PR001 | Processing Throughput | System must handle defined document processing volumes | High | Performance | Minimum 500 documents per hour processing capacity with auto-scaling | FR006 | Performance Engineer | Approved | Development Team | 32 hours | Medium | Load Testing
Performance | PR002 | Response Time Requirements | API responses within acceptable time limits | High | Performance | API responses within 2 seconds for simple requests 30 seconds for complex processing | IR002 | Performance Engineer | Approved | Development Team | 24 hours | Low | Performance Testing
Performance | PR003 | Concurrent User Support | Support for multiple simultaneous users and processing requests | Medium | Performance | Support minimum 50 concurrent users with <5% performance degradation | PR001 | Performance Engineer | Approved | Development Team | 40 hours | Medium | Load Testing
Performance | PR004 | Scalability Requirements | Automatic scaling based on processing demand | Medium | Performance | Auto-scaling triggers at 80% capacity with scale-out within 5 minutes | PR001 | DevOps Engineer | Approved | DevOps Team | 48 hours | High | Performance Testing
Performance | PR005 | Storage Performance | Efficient storage operations for document and result management | Low | Performance | Storage operations complete within 1 second with 99.9% availability |  | System Administrator | Approved | Infrastructure Team | 16 hours | Low | Performance Testing
Security | SR001 | Authentication and Authorization | Secure access control with role-based permissions | High | Security | Multi-factor authentication with role-based access control and Azure AD integration |  | Security Architect | Approved | Security Team | 40 hours | Medium | Security Testing
Security | SR002 | Data Encryption | Encryption of data at rest and in transit | High | Security | AES-256 encryption for stored data TLS 1.2+ for data transmission |  | Security Architect | Approved | Security Team | 24 hours | Low | Security Testing
Security | SR003 | Audit Trail Requirements | Comprehensive logging and audit trail for all system activities | High | Security | Complete audit trail with tamper-proof logging and 90-day retention minimum |  | Security Architect | Approved | Development Team | 36 hours | Medium | Security Testing
Security | SR004 | Network Security Controls | Network-level security controls and access restrictions | Medium | Security | Network segmentation with firewall rules and intrusion detection |  | Security Architect | Approved | Security Team | 32 hours | Medium | Security Testing
Security | SR005 | Data Privacy Protection | Protection of sensitive data and PII in processed documents | High | Security | Automatic PII detection and redaction with configurable privacy controls | SR002 | Security Architect | Approved | Development Team | 48 hours | High | Security Testing
Usability | UR001 | User Interface Design | Intuitive web interface for document processing and monitoring | Medium | Usability | User interface passes usability testing with >4.0/5.0 satisfaction rating |  | UX Designer | Approved | UI/UX Team | 56 hours | Low | UAT
Usability | UR002 | Administrative Interface | Comprehensive admin interface for system configuration and monitoring | Medium | Usability | Admin interface provides access to all configuration and monitoring functions | UR001 | UX Designer | Approved | UI/UX Team | 44 hours | Low | UAT
Usability | UR003 | Reporting and Analytics | Business reporting and analytics capabilities for processed documents | Low | Usability | Customizable reports and dashboards with export capabilities |  | Business Analyst | Approved | Development Team | 48 hours | Medium | UAT
Usability | UR004 | Mobile Responsiveness | Mobile-friendly interface for document upload and status monitoring | Low | Usability | Responsive design supporting tablets and smartphones with core functionality | UR001 | UX Designer | Approved | UI/UX Team | 32 hours | Low | UAT
Reliability | RR001 | System Availability | High availability with minimal downtime | High | Reliability | 99.9% uptime SLA with automated failover and recovery |  | System Administrator | Approved | Operations Team | 40 hours | Medium | Load Testing
Reliability | RR002 | Backup and Recovery | Automated backup and disaster recovery capabilities | High | Reliability | Daily automated backups with 4-hour recovery time objective |  | System Administrator | Approved | Operations Team | 36 hours | Medium | Disaster Recovery Testing
Reliability | RR003 | Monitoring and Alerting | Comprehensive system monitoring with proactive alerting | Medium | Reliability | Real-time monitoring with alerts for performance degradation and failures | RR001 | System Administrator | Approved | Operations Team | 32 hours | Low | Integration Testing
Reliability | RR004 | Data Integrity | Ensure data integrity throughout processing workflow | High | Reliability | Data validation and checksums with 99.99% data integrity guarantee |  | Development Team | Approved | Development Team | 28 hours | Medium | Integration Testing
Compliance | CR001 | GDPR Compliance | Compliance with data protection regulations | Medium | Compliance | GDPR-compliant data handling with right to erasure and data portability | SR005 | Compliance Officer | Approved | Development Team | 40 hours | High | Compliance Testing
Compliance | CR002 | SOC 2 Compliance | SOC 2 Type II compliance for security and availability | Medium | Compliance | SOC 2 Type II compliant controls and documentation | SR001 | Compliance Officer | Approved | Security Team | 48 hours | High | Compliance Testing
Compliance | CR003 | Industry-Specific Compliance | Support for industry-specific compliance requirements | Low | Compliance | Configurable compliance controls for healthcare finance and legal industries | CR001 | Compliance Officer | Approved | Development Team | 56 hours | Medium | Compliance Testing
Maintenance | MR001 | System Updates and Patches | Regular system updates and security patches | Low | Maintenance | Automated patching with rollback capability and minimal downtime |  | DevOps Engineer | Approved | DevOps Team | 24 hours | Low | System Testing
Maintenance | MR002 | Performance Optimization | Ongoing performance monitoring and optimization | Low | Maintenance | Regular performance tuning with documented optimization procedures | PR001 | Performance Engineer | Approved | Operations Team | 32 hours | Medium | Performance Testing
Documentation | DR001 | Technical Documentation | Comprehensive technical documentation for system maintenance | Medium | Documentation | Complete technical documentation with architecture diagrams and procedures |  | Technical Writer | Approved | Documentation Team | 40 hours | Low | Documentation Review
Documentation | DR002 | User Documentation | End-user guides and training materials | Medium | Documentation | User-friendly documentation with step-by-step procedures and troubleshooting | UR001 | Technical Writer | Approved | Documentation Team | 48 hours | Low | UAT
Documentation | DR003 | API Documentation | Complete API documentation with examples and integration guides | Medium | Documentation | OpenAPI specification with examples and SDK documentation | IR002 | Technical Writer | Approved | Documentation Team | 32 hours | Low | API Testing
Training | TR001 | Administrator Training | Comprehensive training program for system administrators | Medium | Training | Administrator training program with certification and competency validation | DR001 | Training Specialist | Approved | Training Team | 40 hours | Low | Training Evaluation
Training | TR002 | End User Training | User training program for document processing workflows | Medium | Training | End-user training with hands-on exercises and competency assessment | DR002 | Training Specialist | Approved | Training Team | 48 hours | Low | Training Evaluation
Training | TR003 | Train-the-Trainer Program | Training program for internal trainers and support staff | Low | Training | Train-the-trainer materials and certification program | TR002 | Training Specialist | Approved | Training Team | 32 hours | Low | Training Evaluation