## Cover
Roles
Delivery Document
Generated: | November 13, 2025
Solution: | Document Intelligence
Customer Name: | Data table for roles
Version: | 1.0

## Roles
Role_Category | Role_Title | EO_Framework_Role | Responsibilities | Required_Skills | Experience_Level | Time_Commitment | Phase_Involvement | Key_Deliverables | Success_Criteria | Reporting_Structure
Executive Sponsor | Executive Sponsor | Executive Sponsor | Provide strategic direction and executive support for solution implementation | Executive leadership strategic planning budget authority | Senior Executive | 5-10% throughout project | All phases | Executive approval budget authorization strategic guidance | Project success and ROI achievement | Reports to: CEO/CTO
Executive Sponsor | Business Owner | Business Stakeholder | Own business requirements and ensure solution meets organizational needs | Business process knowledge change management stakeholder engagement | Director/VP Level | 20-30% throughout project | Planning Design UAT | Business requirements user acceptance criteria change management plan | User adoption and business value realization | Reports to: Executive Sponsor
Project Leadership | Project Manager | Project Manager | Overall project coordination timeline management and stakeholder communication | Project management methodologies risk management stakeholder communication | Senior PM with 5+ years | 80-100% throughout project | All phases | Project plan risk register status reports stakeholder communications | On-time on-budget delivery with quality | Reports to: Executive Sponsor
Project Leadership | Solution Architect | Technical Lead | Technical solution design architecture oversight and technology decisions | Azure architecture AI/ML solutions enterprise integration patterns | Principal/Senior Architect | 60-80% during design and implementation | Architecture Design Implementation | Solution architecture technical specifications integration design | Technical solution meets requirements and standards | Reports to: Project Manager
Technical Implementation | Lead Developer | Technical Implementer | Lead technical development and coding activities | Azure development Python/C# AI services REST APIs | Senior Developer | 80-100% during implementation | Design Implementation Testing | Code implementation API development deployment scripts | Code quality and functionality standards met | Reports to: Solution Architect
Technical Implementation | DevOps Engineer | DevOps Specialist | CI/CD pipeline deployment automation infrastructure management | Azure DevOps Terraform Infrastructure as Code CI/CD pipelines | Senior DevOps Engineer | 60-80% during implementation | Implementation Deployment Operations | Deployment pipelines infrastructure automation monitoring setup | Reliable automated deployments and operations | Reports to: Solution Architect
Technical Implementation | AI/ML Engineer | AI/ML Specialist | Form Recognizer configuration custom model training AI optimization | Azure Cognitive Services machine learning model training data science | AI/ML Engineer | 60-80% during design and implementation | Design Implementation Testing | AI model configuration training data custom models optimization | AI accuracy and performance targets achieved | Reports to: Solution Architect
Quality Assurance | QA Lead | Quality Assurance Lead | Quality assurance testing strategy and validation coordination | Test planning test automation quality assurance methodologies | Senior QA Engineer | 60-80% during testing phases | Testing UAT | Test plans test cases test reports quality metrics | Quality standards met defect rates within targets | Reports to: Project Manager
Quality Assurance | Test Engineer | Test Engineer | Execute test cases performance testing security testing | Manual testing automated testing performance testing tools | Mid-Senior QA Engineer | 80-100% during testing phases | Testing UAT | Test execution results performance reports security validation | All tests executed successfully within schedule | Reports to: QA Lead
Security and Compliance | Security Architect | Security Specialist | Security design compliance requirements security validation | Azure security identity management compliance frameworks | Senior Security Architect | 40-60% during design and testing | Architecture Design Security Testing | Security architecture compliance framework security test results | Security requirements met compliance validated | Reports to: Solution Architect
Security and Compliance | Compliance Officer | Compliance Specialist | Regulatory compliance audit preparation compliance validation | Regulatory frameworks audit processes compliance documentation | Compliance Manager | 20-40% during key phases | Design Testing Deployment | Compliance documentation audit reports regulatory validation | Compliance requirements satisfied audit readiness | Reports to: Business Owner
Business Analysis | Business Analyst | Business Analyst | Requirements gathering business process analysis user story creation | Business analysis requirements documentation process mapping | Senior Business Analyst | 60-80% during planning and UAT | Planning Design UAT | Requirements documentation process maps user acceptance criteria | Complete and accurate requirements delivered | Reports to: Business Owner
Business Analysis | Data Analyst | Data Specialist | Data requirements analysis reporting requirements dashboard design | Data analysis reporting tools business intelligence | Senior Data Analyst | 40-60% during design and implementation | Design Implementation | Data requirements reporting specifications dashboard designs | Data and reporting requirements met user needs | Reports to: Business Analyst
Change Management | Change Manager | Change Manager | Change management strategy user adoption training coordination | Change management user adoption training development | Change Management Specialist | 40-60% throughout project | All phases | Change management plan training materials user adoption metrics | Successful user adoption and change acceptance | Reports to: Business Owner
Change Management | Training Specialist | Training Specialist | Training program development user training delivery knowledge transfer | Training development adult learning technical writing | Training Specialist | 60-80% during training phases | Implementation UAT Operations | Training materials training delivery knowledge transfer documentation | Users trained and competent in system usage | Reports to: Change Manager
Operations Support | Operations Manager | Operations Manager | Operational readiness planning support model definition day-2 operations | Operations management ITIL incident management | Operations Manager | 40-60% during final phases | Implementation Operations | Operations procedures support model incident response procedures | Operational readiness and support capability established | Reports to: Solution Architect
Operations Support | System Administrator | System Administrator | System administration monitoring configuration ongoing maintenance | Azure administration system monitoring troubleshooting | Senior System Admin | 40-60% during operations phase | Implementation Operations | System documentation operational procedures monitoring configuration | Systems properly configured and monitored | Reports to: Operations Manager
Integration Support | Integration Specialist | Integration Specialist | Enterprise system integration API development data mapping | Enterprise integration patterns API development data transformation | Senior Integration Developer | 60-80% during integration phases | Design Implementation Testing | Integration specifications API implementations data mapping | Successful integration with enterprise systems | Reports to: Solution Architect
Integration Support | Database Administrator | Database Specialist | Database design optimization performance tuning backup procedures | Database administration performance tuning backup recovery | Senior DBA | 40-60% during implementation | Design Implementation Operations | Database design backup procedures performance optimization | Database performance and reliability standards met | Reports to: Integration Specialist
User Experience | UX Designer | UX Designer | User interface design user experience optimization usability testing | UI/UX design user research usability testing | Senior UX Designer | 40-60% during design phase | Design UAT | UI designs user experience specifications usability test results | User interface meets usability and accessibility standards | Reports to: Solution Architect
User Experience | Technical Writer | Documentation Specialist | Technical documentation user guides operational procedures | Technical writing documentation development content management | Senior Technical Writer | 40-60% throughout project | All phases | User guides technical documentation operational procedures | Comprehensive accurate and usable documentation | Reports to: Project Manager
Domain Expertise | Financial Systems Expert | Subject Matter Expert | Financial process expertise accounting system integration requirements | Financial systems AP/AR processes ERP systems | Finance System Expert | 20-40% during requirements | Planning Design Testing | Financial requirements integration specifications validation criteria | Financial requirements met integration successful | Reports to: Business Analyst
Domain Expertise | Document Processing Expert | Subject Matter Expert | Document processing expertise workflow optimization best practices | Document processing workflows business rules data extraction | Document Processing SME | 30-50% during requirements and testing | Planning Design UAT | Document processing requirements workflow designs validation criteria | Document processing requirements met user acceptance achieved | Reports to: Business Analyst
Vendor Management | Microsoft Relationship Manager | Vendor Manager | Microsoft partnership solution support escalation management | Vendor management relationship management escalation procedures | Vendor Relationship Manager | 10-20% throughout project | All phases | Vendor agreements support escalation procedures partnership management | Successful vendor partnership and support delivery | Reports to: Project Manager
External Support | Implementation Consultant | External Consultant | Specialized implementation guidance best practices knowledge transfer | Azure AI implementation specialized expertise industry best practices | Senior Consultant | 40-60% during implementation | Implementation Testing | Implementation guidance best practices recommendations knowledge transfer | Successful implementation with best practices followed | Reports to: Solution Architect