## Cover
Communication Plan
Delivery Document
Generated: | November 13, 2025
Solution: | Enterprise Landing Zone
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Cloud Status | Executive Sponsors | Azure cloud project status and digital transformation progress | Weekly | Email Report | EO Project Manager | Email distribution list |  | Cloud migration progress, cost optimization, key decisions needed | EO Quarterback and CTO | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include cloud adoption dashboard and ROI tracking
COMM-002 | Cloud Steering Committee | Project Steering Committee | Strategic direction for Azure cloud adoption and governance | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | Cloud strategy, governance policies, budget, timeline, scope changes | EO Quarterback and IT Leadership | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for cloud governance and budget
COMM-003 | Cloud Team Standup | Core Cloud Development Team | Daily coordination for Azure implementation and migration | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | Azure deployment progress, migration status, technical blockers | Cloud Team and Azure Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on cloud development coordination and impediments
COMM-004 | Azure Architecture Review | Technical and Cloud Teams | Azure architecture and cloud optimization | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | Landing zone design, policies, network architecture | EO Sales Engineer (Solution Architecture) and Cloud Architects | Technical | Cloud decisions documented and performance targets achieved | Active | [DATE] | Include Azure optimization results and governance metrics
COMM-005 | Cloud Operations Review | Operations Team | Azure operations and management procedures | Bi-weekly | Operations Meeting | EO Quarterback | Meeting invitation | 45 minutes | Operational procedures, monitoring, cost management | EO Project Manager and EO Engineer (Technical Leadership) | Management | Operations procedures updated and Azure-specific processes tracked | Active | [DATE] | Focus on cloud operational excellence and cost optimization
COMM-010 | Testing Coordination | QA and Testing Teams | Testing progress and quality validation | Weekly | QA Meeting | EO Quarterback | Meeting invitation | 45 minutes | Test execution, quality metrics, defect resolution | QA Team and Test Engineers | Quality | Quality gates met and testing within tolerance | Active | [DATE] | Include testing metrics and quality validation results
COMM-011 | Deployment Planning | Deployment Teams | Production deployment planning and coordination | Weekly | Deployment Meeting | EO Project Manager | Meeting invitation | 60 minutes | Deployment readiness, rollback procedures, go-live coordination | Deployment Team and Operations | Deployment | Deployment readiness achieved and procedures validated | Active | [DATE] | Include deployment checklist and risk mitigation
COMM-012 | Stakeholder Updates | Business Stakeholders | Business impact and readiness updates | Bi-weekly | Business Meeting | EO Sales Engineer | Meeting invitation | 45 minutes | Business readiness, training status, change management | Business Leaders and Change Management | Business | Business stakeholder engagement and readiness achieved | Active | [DATE] | Include business impact assessment and training progress