## Cover
[DOCUMENT TITLE]
Level of Effort
CISCO - Cloud - Hybrid Infrastructure
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Primary Features/Capabilities | HyperFlex 4-node for 200-300 VMs | HyperFlex 4-node for 200-300 VMs | HyperFlex 6-node for 400-600 VMs | HyperFlex 8+ node for 800+ VMs | Hyperconverged infrastructure scope
Solution Scope | Customization Level | Standard HyperFlex deployment | Standard deployment | Custom vSphere policies and automation | Extensive custom integrations | Configuration vs customization
Integration | External System Integrations | 2 systems (vCenter + backup) | 2 systems (vCenter + backup) | 4 systems (vCenter backup monitoring CMDB) | 6+ systems including orchestration | vCenter Veeam Intersight integration
Integration | Data Sources | VM inventory only | VM inventory | VM + storage + network telemetry | VM + storage + network + app metrics | Infrastructure monitoring data
User Base | Total Users | 10 infrastructure admins | 10 admins | 20 virtualization team members | 40+ distributed team members | vCenter and Intersight users
User Base | User Roles | 2 roles (admin + operator) | 2 roles | 4 roles with resource delegation | 6+ roles with complex RBAC | Role-based access control
Data Volume | Data Processing Volume | 200-300 VMs workload | 200-300 VMs | 400-600 VMs mixed workload | 800+ VMs high-density | Virtual machine capacity
Data Volume | Data Storage Requirements | 20 TB usable storage | 20 TB | 40 TB usable storage | 80+ TB usable storage | After deduplication and compression
Technical Environment | Deployment Regions | Single data center | Single data center | 2 data centers with replication | Multi-site with disaster recovery | Geographic distribution
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | Infrastructure uptime SLA
Technical Environment | Infrastructure Complexity | Basic 3-tier compute storage network | Basic 3-tier | Complex multi-tier with DR | Distributed multi-site architecture | Infrastructure complexity level
Security & Compliance | Security Requirements | Basic encryption and RBAC | Basic security | Encryption + compliance scanning | Advanced security + multi-framework compliance | Data protection and compliance
Security & Compliance | Compliance Frameworks | Basic logging | Basic logging | PCI DSS or HIPAA | Multiple regulatory frameworks | Regulatory compliance requirements
Performance | Performance Requirements | Standard IOPS and latency | Standard performance | High IOPS all-flash NVMe | Extreme performance low-latency | Storage performance tier
Environment | Deployment Environments | Production only | Production only | Dev + production | Dev + staging + production + DR | Environment management

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Infrastructure Assessment, Workload Analysis, Requirements Gathering)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Architecture Design, Capacity Planning, Migration Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (HyperFlex Deployment, vSphere Configuration, VM Migration)
Testing | TESTING_MX | 1 | All Testing phase tasks (Performance Testing, Failover Testing, Application Validation)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, VM Migration, Cutover Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Operations Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline, Legacy Decommission)
Management | MANAGEMENT_MX | 0.25 | Project management and technical leadership (25% of total engineering effort)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Estimated Hours | Rate | Cost Estimate | Dependencies | Risk Level | Notes
Discovery | Infrastructure Assessment | Assess current servers storage and network infrastructure |  | 40 | 225 |  |  | Medium | Capacity utilization and performance analysis
Discovery | Workload Analysis | Analyze VM workloads and resource requirements |  | 32 | 200 |  |  | Medium | vCPU memory storage IOPS profiling
Discovery | Capacity Planning | Size HyperFlex cluster for current and future needs |  | 24 | 225 |  | Workload Analysis | Medium | 3-year capacity planning
Discovery | Application Dependencies | Map application dependencies and migration priorities |  | 32 | 200 |  | Workload Analysis | Medium | VM grouping and migration waves
Planning | HyperFlex Architecture | Design 4-node HyperFlex cluster architecture |  | 48 | 225 |  | Capacity Planning | Medium | HA redundancy and storage design
Planning | Network Design | Design fabric interconnect and network topology |  | 32 | 200 |  | Architecture | Medium | 25GbE connectivity and VLANs
Planning | Migration Strategy | Plan phased VM migration approach |  | 40 | 200 |  | Dependencies | High | vMotion vs cold migration strategy
Planning | Backup Integration | Plan backup integration with Veeam or Commvault |  | 24 | 175 |  | Migration Plan | Medium | Snapshot-based backup design
Development | HyperFlex Deployment | Deploy 4-node HyperFlex cluster with HA |  | 80 | 225 |  | Architecture | Medium | Hardware installation and cluster init
Development | vSphere Configuration | Install and configure vSphere 8 on HyperFlex |  | 40 | 200 |  | HyperFlex Deploy | Medium | vCenter integration and vSphere setup
Development | Network Configuration | Configure fabric interconnects and virtual networking |  | 32 | 200 |  | vSphere Setup | Medium | VLANs distributed switches port groups
Development | Storage Configuration | Configure HyperFlex storage and data services |  | 32 | 200 |  | vSphere Setup | Medium | Deduplication compression replication
Development | Intersight Integration | Integrate HyperFlex with Cisco Intersight |  | 20 | 175 |  | Cluster Deploy | Low | Cloud management and monitoring
Development | Backup Configuration | Configure Veeam backup integration |  | 30 | 200 |  | Storage Config | Medium | Backup jobs and retention policies
Testing | Performance Testing | Test storage and VM performance benchmarks |  | 30 | 200 |  | Config Complete | Medium | IOPS latency throughput validation
Testing | Failover Testing | Test HA failover and node failure scenarios |  | 24 | 200 |  | Performance Tests | High | Node failure and cluster resilience
Testing | VM Migration Testing | Test vMotion and migration procedures |  | 30 | 175 |  | Failover Tests | Medium | Pilot VM migrations (20 VMs)
Testing | Application Validation | Validate application functionality post-migration |  | 40 | 175 |  | VM Migration | High | Business application testing
Deployment | Production VM Migration Wave 1 | Migrate 50 non-critical VMs (Wave 1) |  | 30 | 175 |  | Testing Complete | Medium | Dev/test and low-priority VMs
Deployment | Production VM Migration Wave 2 | Migrate 50 business application VMs (Wave 2) |  | 40 | 175 |  | Wave 1 Success | Medium | Business apps and file servers
Deployment | Production VM Migration Wave 3 | Migrate 50 critical VMs (Wave 3) |  | 50 | 200 |  | Wave 2 Success | High | Databases and mission-critical apps
Deployment | Remaining VM Migration | Migrate final VMs and validate infrastructure |  | 40 | 175 |  | Wave 3 Success | Medium | Cleanup and final migrations
Deployment | Hypercare Support | Provide post-migration stabilization support |  | 60 | 150 |  | Migration Complete | Medium | 4-week hypercare period
Training | Administrator Training | Train infrastructure team on HyperFlex operations |  | 24 | 175 |  | Deployment | Low | HyperFlex and Intersight management
Training | Operations Training | Train operations on monitoring and troubleshooting |  | 16 | 150 |  | Admin Training | Low | Day-to-day operations and alerts
Training | Documentation | Create runbooks SOPs and architecture docs |  | 32 | 150 |  |  | Low | Operational procedures and diagrams
Closeout | Knowledge Transfer | Transfer infrastructure to operations team |  | 16 | 175 |  | Training Complete | Low | Operational handoff and escalation
Closeout | Performance Baseline | Establish performance baselines and SLAs |  | 16 | 175 |  | Hypercare | Low | VM performance and storage metrics
Closeout | Legacy Decommission Planning | Plan decommissioning of legacy infrastructure |  | 24 | 150 |  | Migration Complete | Low | Server and SAN retirement planning
Management | Technical Leadership | Technical quarterback and architecture oversight |  |  | 225 |  |  | Medium | 25% of total engineering effort
Management | Project Management | Project coordination and stakeholder management |  |  | 175 |  |  | Low | 20% of total engineering effort
|  |  | TOTAL HOURS |  | TOTAL COST |  |  |  | Total HyperFlex HCI implementation cost

## Credits
CREDITS
Category | Credit Type | Credit Amount | Credit Comments
Hardware | Server Trade-In Credit | -15000 | Legacy server trade-in credit
Software | VMware ELA Credit | -20000 | Existing VMware Enterprise License Agreement credit
Professional Services | Implementation Services | 0 | No professional services credits available
Support & Maintenance | Support Credit | 0 | No support renewal credits available