## Slide 1
Project Closeout
Cisco HyperFlex Hybrid Infrastructure
Project Manager | November 27, 2025

## Slide 2
Executive Summary
Project Duration: 12 weeks, on schedule
Budget: $417,000 Year 1 delivered on budget
Go-Live Date: Week 12 as planned
Quality: Zero critical defects at launch
Space Reduction: 71% achieved (target: 70%)
VM Provisioning: 8 minutes (target: 10 minutes)
ROI Status: On track for 30-month payback
Cisco HyperFlex Hybrid Infrastructure
Notes: *Opening Statement:*
Good [morning/afternoon]. Today we're celebrating the successful completion of the Cisco HyperFlex Hybrid Infrastructure implementation. This project has transformed [Client Name]'s data center from traditional 3-tier infrastructure to modern hyperconverged platform.
*Key Talking Points - Expand on Each Bullet:*
**Project Duration - 12 Weeks:**
- Executed exactly as planned in the Statement of Work
- Phase 1 (Weeks 1-2): Infrastructure assessment, HyperFlex design
- Phase 2 (Weeks 3-4): HyperFlex 4-node cluster deployment, vSphere 8 setup
- Phase 3 (Weeks 5-8): VM migration in 4 waves (pilot + 3 production)
- Phase 4 (Weeks 9-12): Optimization, training, hypercare transition
- No schedule slippage despite migration complexity
**Budget - $417,000 Year 1:**
- Hardware: $279,000 (4x HyperFlex HX240c M5 + UCS 6454 FIs)
- Software Licenses: $86,000 (VMware Enterprise Plus + HyperFlex)
- Support & Maintenance: $52,000
- Annual recurring cost: $158,000/year for Years 2-3
- 3-Year TCO: $733,000
**Go-Live - Week 12:**
- Phased migration approach validated with pilot first
- 20 VMs in pilot proved approach before production
- All 180 VMs migrated by Week 8
- Zero rollback events required during migration
**Quality - Zero Critical Defects:**
- All test cases executed with 100% pass rate
- No P1 or P2 defects at go-live
- VM migration validated with application testing
- Performance targets exceeded
**Space Reduction - 71%:**
- Baseline: 42U rack space (servers + SAN)
- Current: 12U (4-node HyperFlex + FIs)
- Exceeded 70% target
- Additional 2U available for growth
**VM Provisioning - 8 Minutes:**
- Target: 10 minutes (vs 4-8 hours manual)
- Achieved: 8 minutes average
- Template-based provisioning
- 98% faster than legacy process
**ROI - 30-Month Payback:**
- Annual operational savings: $85K (power/cooling)
- Labor efficiency: $45K (simplified operations)
- Total Year 1 benefit: $130K
- Payback within target window
*Transition to Next Slide:*
"Let me walk you through exactly what we built together..."

## Slide 3
Solution Architecture
Compute & Storage
  4-node HyperFlex HX240c M5 cluster
  20TB usable all-flash storage
  256 vCPUs 3TB RAM capacity
Network Fabric
  UCS 6454 Fabric Interconnects
  25GbE unified fabric
  N+1 redundancy throughout
Management Platform
  Cisco Intersight cloud management
  VMware vSphere 8 virtualization
  Veeam snapshot-based backup
Cisco HyperFlex Hybrid Infrastructure
Notes: *Architecture Overview - Walk Through the Diagram:*
"This diagram shows the production architecture we deployed. Let me walk through the key components..."
**Compute & Storage - HyperFlex Cluster:**
- 4x HyperFlex HX240c M5 nodes in hyperconverged cluster
- Dual Intel Xeon Gold 6248R processors per node
- 768 GB RAM per node (3 TB total)
- All-NVMe storage with 7.68 TB drives
- 20 TB usable capacity after deduplication/compression
- Data replication factor of 3 for protection
**Network Fabric:**
- 2x UCS 6454 Fabric Interconnects (redundant)
- 54 ports each (48x 25GbE + 6x 100GbE)
- Unified fabric for LAN and SAN traffic
- vPC configuration for high availability
- Full redundancy - survives single FI failure
**VM Workload Capacity:**
- Current: 180 VMs running
- Capacity: 200-300 VMs per design
- Growth headroom: 50% additional capacity
- Can add nodes for further scaling
**Management Platform:**
- Cisco Intersight for HyperFlex management
- Cloud-based monitoring and analytics
- Firmware updates and compliance
- Health monitoring and alerts
- VMware vSphere 8 for VM management
- vCenter Server for centralized management
- DRS for automatic load balancing
- HA for automatic VM restart
- Veeam Backup & Replication
- Snapshot-based backup integration
- Policy-based backup schedules
- 30-day daily retention
**Key Architecture Decisions:**
1. All-flash NVMe for performance (30.7 TB raw)
2. Replication factor 3 for data protection
3. N+1 fault tolerance (cluster survives node failure)
4. Cloud management with Intersight
*Transition:*
"Now let me show you the complete deliverables package we're handing over..."

## Slide 4
Deliverables Inventory
Deliverable | Purpose | Location
Infrastructure Assessment | VM workload analysis and sizing | `/delivery/assessment-report.docx`
Detailed Design Document | HyperFlex architecture and config | `/delivery/detailed-design.docx`
Implementation Guide | Step-by-step deployment procedures | `/delivery/implementation-guide.docx`
Project Plan | Timeline, milestones, RACI matrix | `/delivery/project-plan.xlsx`
Test Plan & Results | Validation testing and acceptance | `/delivery/test-plan.xlsx`
Migration Reports | VM migration status per wave | `/delivery/migration-reports/`
Operations Runbook | Day-2 procedures and troubleshooting | `/delivery/runbook.docx`
Training Materials | Administrator guides and recordings | `/delivery/training/`
Cisco HyperFlex Hybrid Infrastructure
Notes: *Deliverables Deep Dive - Review Each Item:*
**1. Infrastructure Assessment:**
- Complete inventory of 180 VMs with resource requirements
- Storage analysis showing 15 TB actual usage
- Performance baselines for migration comparison
- Dependency mapping for migration wave planning
- Reviewed and accepted by Infrastructure Lead
**2. Detailed Design Document:**
- 40+ pages comprehensive technical documentation
- HyperFlex cluster configuration specifications
- Network fabric design with UCS configuration
- vSphere 8 architecture and settings
- Intersight integration architecture
- Living document - recommend annual review
**3. Implementation Guide:**
- Step-by-step deployment procedures
- Prerequisites checklist
- HyperFlex installation and configuration
- vSphere deployment and VM migration
- Validated by rebuilding test environment
**4. Project Plan:**
- Four worksheets:
1. Project Timeline - 28 tasks across 12 weeks
2. Milestones - 6 major milestones tracked
3. RACI Matrix - Clear ownership for all activities
4. Communications Plan - Meeting cadence defined
- All milestones achieved on schedule
**5. Test Plan & Results:**
- Three test categories:
1. Functional Tests - HyperFlex and vSphere validation
2. Non-Functional Tests - Performance and resilience
3. User Acceptance Tests - Migration validation
- 100% pass rate on all test cases
**6. Migration Reports:**
- Wave-by-wave migration status
- Application validation results
- Performance comparison data
- Rollback plans (unused)
**7. Operations Runbook:**
- Daily operations checklist
- Intersight monitoring guide
- Common troubleshooting scenarios
- Escalation procedures
- Backup verification procedures
**8. Training Materials:**
- Administrator Guide (PDF, 25 pages)
- Quick reference cards
- Video recordings (24 hours total):
1. HyperFlex administration
2. Intersight cloud management
3. vSphere operations
4. Backup and recovery
- Total: 24 hours training as per SOW
*Transition:*
"Let's look at how the solution is performing against our targets..."

## Slide 5
Quality & Performance
Infrastructure Metrics
  Space Reduction: 71% (target: 70%)
  VM Provisioning: 8 min (target: 10)
  Storage IOPS: 180K (target: 100K)
  Storage Latency: 0.5ms (target: <5ms)
  VMs Migrated: 180 with zero downtime
Platform Metrics
  Availability: 99.95% (target: 99.9%)
  Deduplication Ratio: 2.3:1 average
  Data Protection: 3-way replication
  Backup Success Rate: 100%
  Recovery Test: 15 min RTO achieved
Cisco HyperFlex Hybrid Infrastructure
Notes: *Quality & Performance Deep Dive:*
**Infrastructure Metrics - Detailed Breakdown:**
*Space Reduction: 71%*
- Legacy: 42U rack space
- 40+ rack-mounted servers (36U)
- SAN storage arrays (6U)
- HyperFlex: 12U rack space
- 4x HyperFlex nodes (8U)
- 2x Fabric Interconnects (4U)
- Power reduction: 35% lower consumption
- Cooling reduction: Corresponding decrease
*VM Provisioning: 8 Minutes*
- Legacy process: 4-8 hours
- Manual server selection
- Storage provisioning
- Network configuration
- OS installation
- HyperFlex process: 8 minutes
- Template-based deployment
- Automated storage allocation
- Pre-configured networking
- One-click provisioning
*Storage Performance:*
- IOPS: 180,000 (80% above target)
- Latency: 0.5ms average (90% under target)
- All-flash NVMe performance
- Inline deduplication and compression
**Platform Metrics - Detailed Analysis:**
*Availability: 99.95%*
- Target: 99.9%
- Achieved: 99.95% in first 30 days
- No unplanned outages
- N+1 fault tolerance validated
*Deduplication Ratio: 2.3:1*
- Effective capacity increase
- 20 TB usable becomes ~46 TB effective
- Varies by workload type
- Windows VMs: 2.5:1 average
- Database VMs: 1.8:1 average
*Data Protection:*
- 3-way replication across nodes
- Survives any single node failure
- Self-healing after failure
- 4-hour rebuild time tested
**Testing Summary:**
- All functional tests: PASS
- All non-functional tests: PASS
- All UAT tests: PASS
- Migration validation: 180 VMs successful
*Transition:*
"These performance improvements translate directly into business value. Let me show you the benefits..."

## Slide 6
Benefits Realized
Benefit Category | SOW Target | Achieved | Business Impact
Space Reduction | 70% | 71% | 42U to 12U rack space
VM Provisioning | 10 min | 8 min | 4-8 hrs to 8 minutes
CapEx Savings | 50% | 51% | $294K vs $600K traditional
Management Time | 75% reduction | 78% | Unified Intersight platform
Power/Cooling | 30% reduction | 35% | $85K annual savings
Availability | 99.9% | 99.95% | Near-zero downtime
Cisco HyperFlex Hybrid Infrastructure
Notes: *Benefits Analysis - Detailed ROI Discussion:*
**Space Reduction - 71%:**
*Before (3-Tier Infrastructure):*
- 40+ rack-mounted servers across 36U
- SAN storage arrays consuming 6U
- Separate network switches
- Total: 42U of rack space
*After (HyperFlex):*
- 4x HyperFlex nodes in 8U
- 2x Fabric Interconnects in 4U
- Total: 12U of rack space
- 30U freed for other use
**CapEx Savings - 51%:**
*Traditional 3-Tier Quote:*
| Component | Cost |
|-----------|------|
| Servers (40+) | $360,000 |
| SAN Storage | $180,000 |
| Network Switches | $60,000 |
| **Total** | **$600,000** |
*HyperFlex Solution:*
| Component | Cost |
|-----------|------|
| HyperFlex Cluster | $200,000 |
| UCS Fabric Interconnects | $54,000 |
| Software Licenses | $40,000 |
| **Total** | **$294,000** |
*Savings: $306,000 (51%)*
**Operational Savings - Annual:**
| Category | Legacy | HyperFlex | Savings |
|----------|--------|-----------|---------|
| Power/Cooling | $150,000 | $65,000 | $85,000 |
| Admin Labor | $60,000 | $15,000 | $45,000 |
| **Total Annual** | | | **$130,000** |
**ROI Summary:**
| Metric | Value |
|--------|-------|
| Total Investment (Year 1) | $417,000 |
| Year 1 Operational Savings | $130,000 |
| Year 1 Net Cost | $287,000 |
| Year 2 Savings | $130,000 |
| Year 3 Savings | $130,000 |
| 3-Year Net Savings | $390,000 |
| Payback Period | 30 months |
*Transition:*
"We learned valuable lessons during this implementation..."

## Slide 7
Lessons Learned & Recommendations
What Worked Well
  Pilot migration validated approach
  Wave-based migration reduced risk
  Weekly stakeholder updates built trust
  Intersight cloud management simplified ops
  vMotion live migration minimized downtime
Challenges Overcome
  Legacy VM compatibility issues resolved
  Network VLAN mapping required cleanup
  Application dependency discovery needed
  Backup integration testing extended
  Storage policy tuning iterative
Recommendations
  Consider DR site with stretch cluster
  Evaluate Kubernetes on HyperFlex
  Plan for additional node in Year 2
  Quarterly Intersight health reviews
  Annual firmware upgrade planning
Cisco HyperFlex Hybrid Infrastructure
Notes: *Lessons Learned - Comprehensive Review:*
**What Worked Well - Details:**
*1. Pilot Migration (Week 5):*
- Started with 20 non-critical VMs
- File servers and development systems
- Validated vMotion process
- Established application testing procedures
- Built team confidence before production
*2. Wave-Based Migration:*
- Wave 1: 50 business applications
- Wave 2: 50 critical VMs (databases, ERP)
- Wave 3: 60 remaining VMs
- Each wave validated before proceeding
- Rollback procedures ready (unused)
*3. Intersight Cloud Management:*
- Simplified HyperFlex monitoring
- Proactive firmware recommendations
- Health score trending
- Single pane for all Cisco infrastructure
**Challenges Overcome - Details:**
*1. Legacy VM Compatibility:*
- Challenge: 15 VMs on old VMware Tools
- Impact: vMotion failures
- Resolution: Pre-migration VMware Tools upgrades
- Prevention: Add to migration checklist
*2. Network VLAN Mapping:*
- Challenge: Legacy VLANs not documented
- Impact: Network connectivity issues
- Resolution: Network discovery and mapping
- Prevention: Network audit in assessment phase
*3. Application Dependencies:*
- Challenge: Undocumented app dependencies
- Impact: Migration sequencing issues
- Resolution: Application owner interviews
- Prevention: Include dependency mapping in scope
**Recommendations for Future:**
*1. DR Site with Stretch Cluster:*
- Optional scope item from SOW
- Geographic redundancy
- RPO near-zero, RTO <15 minutes
- Estimated: $150K additional
*2. Kubernetes on HyperFlex:*
- Container workload support
- HyperFlex native Kubernetes
- Modern application platform
*3. Additional Node (Year 2):*
- Current utilization: 65%
- Growth projection: 15%/year
- 5th node provides headroom
*Transition:*
"Let me walk you through how we're transitioning support..."

## Slide 8
Support Transition
Hypercare Complete (4 weeks)
  Daily health checks completed
  3 minor issues resolved
  Knowledge transfer sessions done
  Runbook procedures validated
  Team trained (24 hours total)
Steady State Support
  Business hours monitoring (8AM-6PM)
  Intersight proactive alerts
  Monthly performance reviews
  Quarterly optimization checks
  Cisco TAC escalation path
Escalation Path
  L1: Internal Infrastructure Desk
  L2: Virtualization Operations Team
  L3: Cisco TAC via SmartNet
  Partner: Vendor support (optional)
  Executive: Account Manager
Cisco HyperFlex Hybrid Infrastructure
Notes: *Support Transition - Complete Details:*
**Hypercare Period Summary (4 Weeks Post-Go-Live):**
*Daily Activities Completed:*
- Morning health check calls (9am)
- Intersight dashboard review
- HyperFlex cluster health validation
- vSphere resource monitoring
- Backup job verification
*Issues Resolved During Hypercare:*
Issue #1 (P3) - Day 3:
- Problem: VM storage policy mismatch
- Root cause: Default policy applied incorrectly
- Resolution: Policy corrected, VM reconfigured
- Prevention: Added to deployment checklist
Issue #2 (P3) - Day 8:
- Problem: Intersight alert threshold noisy
- Root cause: Default thresholds too sensitive
- Resolution: Threshold tuning
- Cost impact: None
Issue #3 (P3) - Day 15:
- Problem: Veeam job timing conflict
- Root cause: Overlapping backup windows
- Resolution: Staggered backup schedules
- Prevention: Backup planning in runbook
*Knowledge Transfer Sessions:*
| Session | Date | Attendees | Hours |
|---------|------|-----------|-------|
| HyperFlex Admin | Week 9 | 4 admins | 8 |
| Intersight Ops | Week 10 | 4 admins | 4 |
| vSphere on HX | Week 10 | 4 admins | 8 |
| Backup/Recovery | Week 11 | 4 admins | 4 |
**Steady State Support Model:**
*What Client Team Handles (L1/L2):*
- Daily monitoring via Intersight
- VM provisioning and management
- Backup verification
- Basic troubleshooting (per runbook)
- Performance monitoring
*When to Escalate to Cisco TAC (L3):*
- HyperFlex cluster issues
- Node failures
- Firmware upgrades
- Performance degradation
- Complex troubleshooting
**Support Contacts:**
| Role | Contact | Availability |
|------|---------|--------------|
| Infrastructure Lead | [Name/Email] | Business hours |
| Cisco TAC | SmartNet | 24/7 |
| VMware Support | Enterprise | 24/7 |
| Veeam Support | Standard | Business hours |
*Transition:*
"Let me acknowledge the team and outline next steps..."

## Slide 9
Acknowledgments & Next Steps
Client Team: Executive sponsor, Infrastructure Lead, Virtualization team, App owners
Vendor Team: Project manager, HCI engineer, Virtualization engineer
Cisco Team: Partner enablement, TAC support, Professional services
This Week: Final documentation handover, archive project artifacts
Next 30 Days: Monthly performance review, DR site planning kickoff
Next Quarter: HyperFlex node expansion assessment, Kubernetes pilot
Cisco HyperFlex Hybrid Infrastructure
Notes: *Acknowledgments - Recognize Key Contributors:*
**Client Team Recognition:**
*Executive Sponsor - [Name]:*
- Championed infrastructure modernization
- Secured budget approval
- Removed organizational blockers
- Key decision: Approved HyperFlex approach
*Infrastructure Lead - [Name]:*
- Technical counterpart throughout
- HyperFlex configuration validation
- Migration wave coordination
- Future platform owner
*Virtualization Lead - [Name]:*
- vSphere administration lead
- VM migration execution
- Application testing coordination
- Knowledge transfer recipient
**Vendor Team Recognition:**
*EO Project Manager - [Name]:*
- Overall delivery accountability
- Stakeholder communication
- On-time, on-budget delivery
*EO HCI Engineer - [Name]:*
- HyperFlex cluster deployment
- Intersight integration
- Performance optimization
*EO Virtualization Engineer - [Name]:*
- vSphere 8 deployment
- VM migration execution
- Training delivery
**Immediate Next Steps (This Week):**
| Task | Owner | Due Date |
|------|-------|----------|
| Final documentation handover | PM | [Date] |
| Archive project artifacts | PM | [Date] |
| Legacy decommission planning | Infra Lead | [Date] |
**30-Day Next Steps:**
| Task | Owner | Due Date |
|------|-------|----------|
| First monthly performance review | Infra Lead | [Date+30] |
| DR site planning workshop | PM | [Date+30] |
| Node expansion assessment | HCI Engineer | [Date+45] |
*Transition:*
"Thank you for your partnership. Questions?"

## Slide 10
Thank You
Notes: *Closing and Q&A Preparation:*
**Closing Statement:**
"Thank you for your partnership throughout this project. We've successfully transformed your data center from 40+ servers to a modern 4-node hyperconverged platform. HyperFlex is exceeding all targets, the team is trained and confident, and you're already seeing measurable savings."
**Anticipated Questions:**
*Q: What happens if a node fails?*
A: The cluster is N+1 fault tolerant. VMs restart automatically on remaining nodes within minutes. Data is replicated 3 ways.
*Q: Can we add more VMs?*
A: Yes, current utilization is 65%. You have capacity for 60-80 more VMs before adding nodes.
*Q: What are the ongoing Cisco costs?*
A: Annual recurring is $158K covering licenses and SmartNet support.
*Q: How do we handle capacity growth?*
A: Add HyperFlex nodes non-disruptively. Linear scaling. Recommend planning 5th node in Year 2.
*Q: When should we consider DR?*
A: Recommend 60-90 days to stabilize, then evaluate stretch cluster for geographic redundancy.
**Demo Offer:**
"Would anyone like to see a live Intersight dashboard demo? I can show health monitoring and performance metrics."
**Final Closing:**
"Thank you again for trusting our team. This project demonstrates what's possible with modern hyperconverged infrastructure. We look forward to supporting your continued growth."