## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Hybrid Infrastructure
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | EO Project Manager | Not Started
Discovery | Infrastructure Assessment | 5 days | [START_DATE+1] | [START_DATE+6] | Project Kickoff | EO HCI Engineer | Not Started
Discovery | VM Workload Analysis (72 hours) | 5 days | [START_DATE+3] | [START_DATE+8] | Infrastructure Assessment | EO Virtualization Engineer | Not Started
Discovery | HyperFlex Sizing and Design | 4 days | [START_DATE+6] | [START_DATE+10] | VM Workload Analysis | EO Quarterback | Not Started
Discovery | Network Integration Planning | 3 days | [START_DATE+8] | [START_DATE+11] | HyperFlex Sizing | EO HCI Engineer | Not Started
Discovery | Migration Strategy Definition | 2 days | [START_DATE+10] | [START_DATE+12] | Network Planning | EO Virtualization Engineer | Not Started
Foundation | Data Center Preparation | 5 days | [START_DATE+12] | [START_DATE+17] | Discovery Complete | Client Infrastructure | Not Started
Foundation | HyperFlex Hardware Rack and Stack | 3 days | [START_DATE+17] | [START_DATE+20] | Data Center Prep | EO HCI Engineer | Not Started
Foundation | UCS 6454 Fabric Interconnect Setup | 2 days | [START_DATE+18] | [START_DATE+20] | Hardware Installation | EO HCI Engineer | Not Started
Foundation | HyperFlex Cluster Deployment (80 hrs) | 5 days | [START_DATE+20] | [START_DATE+25] | FI Setup | EO HCI Engineer | Not Started
Foundation | Cisco Intersight Integration (20 hrs) | 2 days | [START_DATE+23] | [START_DATE+25] | Cluster Deployment | EO HCI Engineer | Not Started
Virtualization | VMware vSphere 8 Installation (72 hrs) | 5 days | [START_DATE+25] | [START_DATE+30] | HyperFlex Cluster | EO Virtualization Engineer | Not Started
Virtualization | vCenter Configuration | 3 days | [START_DATE+28] | [START_DATE+31] | vSphere Install | EO Virtualization Engineer | Not Started
Virtualization | HA and DRS Configuration | 2 days | [START_DATE+30] | [START_DATE+32] | vCenter Config | EO Virtualization Engineer | Not Started
Virtualization | Network Connectivity Validation | 2 days | [START_DATE+31] | [START_DATE+33] | HA/DRS Config | EO HCI Engineer | Not Started
Migration | Pilot Migration: 20 VMs (30 hrs) | 3 days | [START_DATE+33] | [START_DATE+36] | Network Validation | EO Virtualization Engineer | Not Started
Migration | Pilot Validation and Testing | 2 days | [START_DATE+36] | [START_DATE+38] | Pilot Migration | Client Applications | Not Started
Migration | Wave 1: 50 Business VMs (40 hrs) | 4 days | [START_DATE+38] | [START_DATE+42] | Pilot Complete | EO Virtualization Engineer | Not Started
Migration | Wave 1 Application Testing | 2 days | [START_DATE+42] | [START_DATE+44] | Wave 1 Migration | Client Applications | Not Started
Migration | Wave 2: 50 Critical VMs (50 hrs) | 5 days | [START_DATE+44] | [START_DATE+49] | Wave 1 Complete | EO Virtualization Engineer | Not Started
Migration | Wave 2 Application Testing | 2 days | [START_DATE+49] | [START_DATE+51] | Wave 2 Migration | Client Applications | Not Started
Migration | Wave 3: Remaining VMs (40 hrs) | 4 days | [START_DATE+51] | [START_DATE+55] | Wave 2 Complete | EO Virtualization Engineer | Not Started
Migration | Wave 3 Final Validation | 2 days | [START_DATE+55] | [START_DATE+57] | Wave 3 Migration | Client Applications | Not Started
Optimization | Performance Tuning (45 hrs) | 4 days | [START_DATE+57] | [START_DATE+61] | Migration Complete | EO Quarterback | Not Started
Optimization | Veeam Backup Integration | 3 days | [START_DATE+59] | [START_DATE+62] | Performance Tuning | EO HCI Engineer | Not Started
Optimization | Team Training: HyperFlex Admin | 8 hours | [START_DATE+62] | [START_DATE+63] | Backup Integration | EO HCI Engineer | Not Started
Optimization | Team Training: Intersight Cloud | 4 hours | [START_DATE+63] | [START_DATE+64] | HyperFlex Training | EO HCI Engineer | Not Started
Optimization | Team Training: vSphere on HX | 8 hours | [START_DATE+64] | [START_DATE+65] | Intersight Training | EO Virtualization Engineer | Not Started
Optimization | Team Training: Backup Recovery | 4 hours | [START_DATE+65] | [START_DATE+66] | vSphere Training | EO HCI Engineer | Not Started
Go-Live | Production Go-Live | 2 days | [START_DATE+66] | [START_DATE+68] | Training Complete | EO Project Manager | Not Started
Support | Hypercare Support Week 1 | 7 days | [START_DATE+68] | [START_DATE+75] | Go-Live | EO HCI Engineer | Not Started
Support | Hypercare Support Week 2 | 7 days | [START_DATE+75] | [START_DATE+82] | Hypercare Week 1 | EO HCI Engineer | Not Started
Support | Hypercare Support Weeks 3-4 | 14 days | [START_DATE+82] | [START_DATE+96] | Hypercare Week 2 | EO Virtualization Engineer | Not Started
Closure | Legacy Decommission Planning | 5 days | [START_DATE+85] | [START_DATE+90] | Hypercare | Client Infrastructure | Not Started
Closure | Knowledge Transfer Completion | 3 days | [START_DATE+90] | [START_DATE+93] | Decommission Plan | EO Project Manager | Not Started
Closure | Documentation Delivery | 2 days | [START_DATE+93] | [START_DATE+95] | Knowledge Transfer | EO Quarterback | Not Started
Closure | Project Closure | 1 day | [START_DATE+95] | [START_DATE+96] | Documentation | EO Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Design Complete | [START_DATE+14] | HyperFlex architecture approved; Network design complete; Migration strategy defined | EO Quarterback | Not Started
M2 | Cluster Deployed | [START_DATE+28] | HyperFlex 4-node cluster operational; Intersight integration complete; vSphere 8 installed | EO HCI Engineer | Not Started
M3 | Pilot Complete | [START_DATE+38] | 20 VMs migrated successfully; Application testing passed; Performance validated | EO Virtualization Engineer | Not Started
M4 | Migration Complete | [START_DATE+57] | All 180 VMs migrated; Application validation complete; Performance baselines met | EO Virtualization Engineer | Not Started
M5 | Go-Live | [START_DATE+68] | Production operational; Team trained (24 hours); All tests passed; Backup operational | EO Project Manager | Not Started
M6 | Hypercare End | [START_DATE+96] | Support period complete; Knowledge transfer done; Lessons learned documented | EO Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | QB | HCIEng | VirtEng | InfraLead | VirtLead | AppOwners | Client
Project Charter & Kickoff | A | C | C | I | C | I | I | C
Infrastructure Assessment | A | C | R | C | C | I | I | I
VM Workload Analysis | A | C | C | R | I | C | I | I
HyperFlex Sizing and Design | A | R | C | C | C | I | I | I
Network Integration Planning | A | C | R | I | C | I | I | I
Migration Strategy Definition | A | R | C | R | C | C | C | I
Data Center Preparation | A | I | C | I | R | I | I | C
HyperFlex Cluster Deployment | A | C | R | I | C | I | I | I
UCS Fabric Interconnect Setup | A | C | R | I | C | I | I | I
Intersight Integration | A | C | R | I | I | I | I | I
vSphere 8 Installation | A | C | I | R | I | C | I | I
vCenter Configuration | A | C | I | R | I | C | I | I
Pilot VM Migration | A | C | C | R | I | C | C | I
Production VM Migration Waves | A | C | C | R | I | C | A | I
Application Testing Validation | A | I | I | C | I | C | R | A
Veeam Backup Integration | A | C | R | C | I | I | I | I
Performance Tuning | A | R | C | C | I | I | I | I
Team Training (24 hours) | A | R | R | R | C | C | I | I
Production Go-Live | A | C | C | C | C | C | I | R
Hypercare Support (60 hours) | A | C | R | R | C | C | I | I
Legend:
R | A A A A A A A A A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on HyperFlex objectives and migration strategy | EO Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and major decisions on infrastructure transformation | EO Project Manager | Alternate Tuesdays
Project Status Meeting | Weekly | Core project team | Review progress and address blockers across all workstreams | EO Project Manager | Mondays 10:00
Technical Design Review | Weekly | Technical leads | HyperFlex architecture decisions and vSphere configuration | EO Quarterback | Wednesdays 14:00
Migration Standup | Daily | Migration team | VM migration progress and application validation status | EO Virtualization Engineer | Daily 09:30
Risk & Issue Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | EO Project Manager | Alternate Fridays
Infrastructure Review | Weekly | HCI and Infra teams | HyperFlex cluster health and performance monitoring | EO HCI Engineer | Thursdays 11:00
Application Owner Sync | Weekly | App owners and migration team | Migration wave planning and application testing coordination | Client App Owners | Fridays 14:00
Go-Live Readiness | Daily (2 weeks pre) | Go-live team | Deployment preparation and migration checklist review | EO Project Manager | Daily 09:00
Post Go-Live Review | Weekly (hypercare) | Support and operations | Production stability and HyperFlex performance | EO HCI Engineer | Mondays 11:00
Hypercare Closeout | Once | All stakeholders | Hypercare completion and operational handoff | EO Project Manager | Week 16