## Cover
[DOCUMENT TITLE]
Level of Effort
IBM - Devops - Ansible Automation Platform
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Server Count | 500 servers (Linux/Windows) | 500 servers | 1000 servers | 2000+ servers | Managed server inventory size
Solution Scope | Network Device Count | 100 network devices | 100 devices | 200 devices | 500+ devices | Routers switches firewalls
Solution Scope | Playbook Count | 100 custom automation playbooks | 100 playbooks | 250 playbooks | 500+ playbooks | Server network cloud compliance automation
Integration | ITSM Integration | ServiceNow ticket-driven workflows | ServiceNow | ServiceNow + JIRA | Multiple ITSM platforms complex workflows | Service ticket automation integration
Integration | External Systems | Monitoring systems + credential vault | 2-3 systems | 4-6 systems | 8+ systems or complex integrations | Monitoring vaults CMDBs cloud providers
User Base | Automation Users | 50 operations staff | 50 users | 100-200 users | 500+ users | Platform users and automation developers
User Base | User Roles | 5 roles (operator admin developer approver auditor) | 5 standard roles | 8-10 roles | 15+ roles with complex RBAC | Role-based access control requirements
Data Volume | Automation Executions | 10000+ job runs per month | 10K jobs/month | 50K jobs/month | 200K+ jobs/month | Monthly automation job execution volume
Data Volume | Inventory Management | 600 managed nodes total | 600 nodes | 1500 nodes | 5000+ nodes | Total managed infrastructure inventory
Technical Environment | Deployment Platform | AWS/Azure cloud infrastructure | Single cloud provider | Multi-cloud (AWS + Azure) | Complex hybrid cloud + on-prem | Infrastructure hosting for automation platform
Technical Environment | Availability Requirements | HA controller cluster (99.5% uptime) | Multi-node HA | Multi-region HA | Global with DR | Platform availability configuration
Technical Environment | Infrastructure Complexity | Controller HA + distributed execution nodes | Standard HA cluster | Advanced with geo-distributed nodes | Complex multi-region federated platform | Automation platform infrastructure complexity
Security & Compliance | Security Requirements | RBAC + credential vault integration | Basic RBAC + vault | Industry standard (SOC2) | Advanced (FedRAMP multi-framework) | Platform and automation security
Security & Compliance | Compliance Frameworks | SOC2 ISO 27001 | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Compliance and governance requirements
Performance | Execution Capacity | 100 concurrent job executions | 100 concurrent jobs | 500 concurrent jobs | 2000+ concurrent jobs | Platform concurrent automation capacity
Performance | Automation Orchestration | Event-driven automation + scheduled jobs | Basic event-driven | Advanced orchestration | Complex workflow automation | Automation execution patterns
Environment | Deployment Environments | 2 environments (dev/staging + prod) | 2 environments | 3 environments | 4+ environments multi-cluster | Environment management for automation platform

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Infrastructure Assessment, Automation Assessment, Compliance Review)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Automation Platform Design, Network Design, Integration Design, Security Design, Project Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Platform Deployment, Playbook Development, ServiceNow Integration, Event-Driven Automation)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Integration Testing, Performance Testing, Security Testing, UAT)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Developer Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews for automation platform requirements | EO Engineer | 40 |  |  | 150 |  |  | Includes automation use cases and infrastructure inventory analysis
Discovery | Infrastructure Assessment | Analyze current IT operations and manual process inefficiencies | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide infrastructure details and operational workflows
Discovery | Automation Assessment | Evaluate automation opportunities and prioritize high-value use cases | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide process documentation and pain points
Discovery | Compliance Review | Assess security governance and compliance requirements for automation | EO Engineer | 16 |  |  | 175 |  |  | Identifies regulatory requirements and security controls
Planning | Automation Platform Design | Design Ansible platform architecture with HA controller and execution nodes | EO Engineer | 48 |  |  | 200 |  | Requirements Gathering | Deliverable: Ansible architecture with HA controller cluster and distributed execution
Planning | Network Architecture Design | Design network connectivity for automation controller and managed infrastructure | EO Engineer | 24 |  |  | 180 |  | Automation Platform Design | Deliverable: Network design with firewall rules and connectivity
Planning | Integration Design | Design ServiceNow integration and event-driven automation workflows | EO Engineer | 32 |  |  | 175 |  | Automation Platform Design | ITSM ticket-driven automation and monitoring webhooks
Planning | Security Architecture | Design RBAC credential vault integration and audit controls | EO Engineer | 24 |  |  | 175 |  | Compliance Review | HashiCorp Vault or CyberArk integration and security controls design
Planning | Project Planning | Develop playbook roadmap timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | Automation Platform Design | Deliverable: Project plan with phased automation rollout schedule
Development | Platform Deployment | Deploy Ansible Automation Platform with HA controller cluster | EO Engineer | 40 |  |  | 160 |  | Automation Platform Design | Includes controller deployment PostgreSQL setup and execution nodes
Development | Execution Node Configuration | Configure distributed execution nodes for scalable job processing | EO Engineer | 24 |  |  | 150 |  | Platform Deployment | 4+ execution nodes with auto-scaling and geographic distribution
Development | Authentication Integration | Integrate LDAP/AD for SSO and configure RBAC teams and organizations | EO Engineer | 24 |  |  | 155 |  | Security Architecture | OAuth provider configuration and role-based permissions
Development | Credential Vault Integration | Integrate HashiCorp Vault or CyberArk for secure credential management | EO Engineer | 32 |  |  | 155 |  | Security Architecture | External vault for SSH keys API tokens and secrets
Development | Private Automation Hub | Deploy and configure Private Automation Hub for organization content | EO Engineer | 24 |  |  | 140 |  | Platform Deployment | Organization playbook repository and collection management
Development | Server Playbooks | Develop 50 server automation playbooks (provisioning patching configuration) | EO Engineer | 120 |  |  | 130 |  | Platform Deployment | Linux and Windows server automation with idempotency and error handling
Development | Network Playbooks | Develop 30 network device playbooks (configuration backup compliance) | EO Engineer | 80 |  |  | 135 |  | Platform Deployment | Cisco Juniper Arista device automation with rollback capabilities
Development | Compliance Playbooks | Develop 20 compliance and cloud automation playbooks | EO Engineer | 60 |  |  | 130 |  | Platform Deployment | Security hardening vulnerability remediation and audit reporting
Development | ServiceNow Integration | Configure ServiceNow connector for ticket-driven automation workflows | EO Engineer | 32 |  |  | 150 |  | Integration Design | Ticket creation job trigger and status update workflows
Development | Event-Driven Automation | Deploy Event-Driven Ansible for monitoring webhook auto-remediation | EO Engineer | 32 |  |  | 145 |  | Platform Deployment | Monitoring system integration for automated incident response
Development | Self-Service Portal | Configure automation catalog for operations team self-service | EO Engineer | 24 |  |  | 140 |  | Platform Deployment | Job templates surveys and approval workflows
Testing | Unit Testing | Develop automated tests for playbooks with test inventory | EO Engineer | 32 |  |  | 120 |  | Server Playbooks | Molecule testing framework and playbook validation
Testing | Integration Testing | Test ServiceNow integration monitoring webhooks and vault connectivity | EO Engineer | 40 |  |  | 120 |  | ServiceNow Integration | Customer must provide test credentials and integration endpoints
Testing | Performance Testing | Test concurrent job execution capacity and platform scaling | EO Engineer | 24 |  |  | 140 |  | Integration Testing | Load testing with 100 concurrent automation jobs
Testing | Security Testing | Perform RBAC validation credential handling and audit logging verification | EO Engineer | 16 |  |  | 175 |  | Performance Testing | Includes vulnerability scanning and compliance validation
Testing | User Acceptance Testing | Coordinate UAT with operations teams for automation workflows | EO Engineer | 32 |  |  | 150 |  | Security Testing | Operations team validation of playbooks and workflows
Deployment | Production Deployment | Deploy Ansible platform to production with validation and monitoring | EO Engineer | 24 |  |  | 160 |  | User Acceptance Testing | Production cluster deployment with smoke testing
Deployment | Go-Live Support | Provide support during initial production automation rollout | EO Engineer | 80 |  |  | 110 |  | Production Deployment | Daily monitoring rapid issue response during hypercare period
Training | Administrator Training | Train platform administrators on Ansible controller management | EO Engineer | 32 |  |  | 130 |  | Production Deployment | Platform management RBAC user administration monitoring troubleshooting
Training | Developer Training | Train automation developers on playbook development best practices | EO Engineer | 32 |  |  | 130 |  | Administrator Training | Playbook authoring testing Git workflows and coding standards
Training | Documentation | Create playbook catalog runbooks and operational documentation | EO Engineer | 24 |  |  | 110 |  | Developer Training | Deliverable: Operations runbooks playbook usage guides and best practices
Closeout | Knowledge Transfer | Transfer platform ownership to automation and operations teams | EO Engineer | 16 |  |  | 140 |  | Documentation | Comprehensive handover including architecture procedures and escalation
Closeout | Performance Baseline | Establish automation metrics monitoring baselines and KPIs | EO Engineer | 8 |  |  | 130 |  | Knowledge Transfer | Establishes SLAs automation success rate and operational dashboards
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | Ansible architecture review and technical escalation support
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes weekly status risk management and stakeholder coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers in Estimate Settings based on server count and playbook complexity

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Red Hat Partner Services Credit | -3000 | Red Hat partner credit for Ansible platform implementation and playbook development
AWS/Azure Cloud Credit | -2000 | Cloud provider promotional credit for new automation platform workloads
TOTAL