## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Srx Firewall Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | Project Manager | Not Started
Phase 1 | Current State Discovery | 5 days | [START_DATE+1] | [START_DATE+6] | Project Kickoff | Security Architect | Not Started
Phase 1 | Policy Export and Analysis | 5 days | [START_DATE+4] | [START_DATE+9] | Current State Discovery | Security Engineer | Not Started
Phase 1 | Lab Environment Setup | 5 days | [START_DATE+6] | [START_DATE+11] | Policy Export | Network Engineer | Not Started
Phase 1 | Architecture Design Review | 3 days | [START_DATE+9] | [START_DATE+12] | Lab Environment Setup | Solution Architect | Not Started
Phase 1 | Policy Migration Testing (Lab) | 7 days | [START_DATE+12] | [START_DATE+19] | Architecture Design Review | Security Engineer | Not Started
Phase 1 | Security Director Deployment | 3 days | [START_DATE+15] | [START_DATE+18] | Lab Environment Setup | Platform Engineer | Not Started
Phase 1 | Integration Testing (Lab) | 5 days | [START_DATE+19] | [START_DATE+24] | Policy Migration Testing | QA Engineer | Not Started
Phase 2 | SRX4600 Hardware Installation | 2 days | [START_DATE+24] | [START_DATE+26] | Integration Testing | Network Engineer | Not Started
Phase 2 | Chassis Cluster Configuration | 2 days | [START_DATE+26] | [START_DATE+28] | Hardware Installation | Network Engineer | Not Started
Phase 2 | Zone and Interface Configuration | 3 days | [START_DATE+28] | [START_DATE+31] | Chassis Cluster Config | Security Engineer | Not Started
Phase 2 | Security Services Activation | 3 days | [START_DATE+31] | [START_DATE+34] | Zone Configuration | Security Engineer | Not Started
Phase 2 | Policy Deployment (Datacenter) | 5 days | [START_DATE+34] | [START_DATE+39] | Security Services | Security Engineer | Not Started
Phase 2 | VPN Configuration | 3 days | [START_DATE+37] | [START_DATE+40] | Policy Deployment | Network Engineer | Not Started
Phase 2 | SIEM Integration | 2 days | [START_DATE+39] | [START_DATE+41] | Policy Deployment | Integration Engineer | Not Started
Phase 2 | Zone Migration (DMZ) | 3 days | [START_DATE+41] | [START_DATE+44] | SIEM Integration | Network Engineer | Not Started
Phase 2 | Zone Migration (Internal) | 3 days | [START_DATE+44] | [START_DATE+47] | Zone Migration DMZ | Network Engineer | Not Started
Phase 2 | HA Failover Testing | 2 days | [START_DATE+47] | [START_DATE+49] | Zone Migration Internal | QA Engineer | Not Started
Phase 2 | Performance Validation | 3 days | [START_DATE+49] | [START_DATE+52] | HA Failover Testing | Performance Engineer | Not Started
Phase 3 | Branch Site 1-2 Deployment | 3 days | [START_DATE+52] | [START_DATE+55] | Performance Validation | Field Engineer | Not Started
Phase 3 | Branch Site 3-4 Deployment | 3 days | [START_DATE+55] | [START_DATE+58] | Branch 1-2 Complete | Field Engineer | Not Started
Phase 3 | Branch Site 5-6 Deployment | 3 days | [START_DATE+58] | [START_DATE+61] | Branch 3-4 Complete | Field Engineer | Not Started
Phase 3 | Branch Site 7-8 Deployment | 3 days | [START_DATE+61] | [START_DATE+64] | Branch 5-6 Complete | Field Engineer | Not Started
Phase 3 | Branch Site 9-10 Deployment | 3 days | [START_DATE+64] | [START_DATE+67] | Branch 7-8 Complete | Field Engineer | Not Started
Phase 3 | SD-WAN Configuration | 3 days | [START_DATE+67] | [START_DATE+70] | All Branches Complete | Network Engineer | Not Started
Phase 3 | Branch VPN Validation | 2 days | [START_DATE+70] | [START_DATE+72] | SD-WAN Configuration | QA Engineer | Not Started
Phase 4 | Security Optimization | 3 days | [START_DATE+72] | [START_DATE+75] | Branch VPN Validation | Security Engineer | Not Started
Phase 4 | Documentation Finalization | 3 days | [START_DATE+75] | [START_DATE+78] | Security Optimization | Technical Writer | Not Started
Phase 4 | Administrator Training | 2 days | [START_DATE+78] | [START_DATE+80] | Documentation Complete | Training Lead | Not Started
Phase 4 | Operations Training | 2 days | [START_DATE+80] | [START_DATE+82] | Administrator Training | Training Lead | Not Started
Phase 4 | Knowledge Transfer | 2 days | [START_DATE+82] | [START_DATE+84] | Operations Training | Technical Lead | Not Started
Phase 4 | Project Closure | 1 day | [START_DATE+84] | [START_DATE+85] | Knowledge Transfer | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | [START_DATE] | Kickoff meeting completed; project charter signed; resources confirmed | Project Manager | Not Started
M2 | Lab Validation | [START_DATE+24] | Policy migration validated in lab; integration testing passed; architecture approved | Solution Architect | Not Started
M3 | Datacenter Go-Live | [START_DATE+52] | SRX4600 HA operational; traffic migrated; performance validated at 80 Gbps | Network Engineer | Not Started
M4 | Branch Deployment | [START_DATE+72] | All 10 SRX300 deployed; VPN tunnels operational; SD-WAN configured | Field Engineer | Not Started
M5 | Training Complete | [START_DATE+82] | Admin and ops training delivered; certification achieved; handover ready | Training Lead | Not Started
M6 | Project Closure | [START_DATE+85] | Documentation complete; warranty started; closeout presentation delivered | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | NE | SE | QA | TL | FE | Client
Project Charter | A | C | I | I | I | C | I | C
Architecture Design | A | R | C | C | I | C | I | I
Policy Migration Plan | A | C | I | R | C | C | I | I
Lab Environment Setup | A | C | R | C | C | I | I | I
SRX4600 Installation | A | C | R | C | I | C | I | I
Security Services Config | A | C | I | R | C | C | I | I
Zone Migration | A | C | R | R | I | C | I | C
Branch Deployment | A | C | C | I | I | C | R | I
VPN Configuration | A | C | R | C | C | C | I | I
SIEM Integration | A | C | I | R | C | C | I | I
Performance Testing | A | I | C | C | R | I | I | I
HA Failover Testing | A | C | C | C | R | C | I | I
Training Delivery | A | I | I | I | I | R | I | R
Documentation | A | C | C | C | C | R | C | I
Go-Live Approval | A | C | C | C | C | C | I | R
Project Closeout | A | C | C | C | C | C | C | R
Legend:
R | A A: Responsible - Does the work
A | A A: Accountable - Ultimate ownership
C | A A: Consulted - Provides input
I | A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project and align on objectives and timeline | Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic oversight and escalation resolution | Project Manager | Alternate Tuesdays
Status Meeting | Weekly | Core project team | Review progress and address blockers and risks | Project Manager | Mondays 10:00
Technical Review | Weekly | Technical leads and architects | Design decisions and technical issue resolution | Solution Architect | Wednesdays 14:00
Cutover Planning | Daily (Week 5-8) | Migration team and operations | Coordinate zone migrations and validate traffic | Network Engineer | Daily 09:00
Branch Deployment | Daily (Week 9-11) | Field and network engineers | Branch deployment status and issue resolution | Field Engineer | Daily 08:00
Training Sessions | Per schedule | Training participants | Knowledge transfer and skill development | Training Lead | Per schedule
Go-Live Readiness | Daily (Week 12) | Go-live team and stakeholders | Final validation and go-live checklist review | Project Manager | Daily 09:00