## Cover
Test Plan
Generated: | November 27, 2025
Solution: | Srx Firewall Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | Firewall Policy Permit | Validate permitted traffic flows through firewall policy | SRX4600 operational; test VMs deployed | 1. Initiate HTTP traffic from internal to DMZ; 2. Capture session table; 3. Verify traffic logged | Traffic permitted; session established; log entry created | High | Not Started
FT-002 | Unit | Firewall Policy Deny | Validate denied traffic is blocked by policy | SRX4600 operational; deny policy configured | 1. Initiate blocked traffic type; 2. Monitor session table; 3. Check deny logs | Traffic blocked; no session created; deny log generated | High | Not Started
FT-003 | Unit | IPS Signature Detection | Validate IPS detects known attack signatures | IPS enabled; signature database current | 1. Generate test attack traffic; 2. Monitor IPS alerts; 3. Verify blocking action | Attack detected; alert generated; traffic blocked | High | Not Started
FT-004 | Integration | ATP Cloud Malware Detection | Validate ATP Cloud sandbox integration | ATP Cloud configured; internet connectivity | 1. Download EICAR test file; 2. Monitor ATP verdict; 3. Verify file blocked | Malware detected; ATP verdict received; download blocked | High | Not Started
FT-005 | Integration | SecIntel C2 Blocking | Validate SecIntel blocks C2 communications | SecIntel feeds active; test C2 domain | 1. Attempt connection to test C2 domain; 2. Monitor SecIntel logs; 3. Verify blocking | C2 connection blocked; SecIntel alert generated | High | Not Started
FT-006 | System | Security Director Policy Push | Validate centralized policy deployment | Security Director configured; SRX registered | 1. Create policy in Security Director; 2. Deploy to SRX; 3. Verify policy active | Policy deployed successfully; active on SRX device | Medium | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | Firewall Throughput | Validate 80 Gbps firewall throughput specification | iperf servers deployed; 100GbE connectivity | 1. Configure iperf client/server; 2. Run throughput test 60 seconds; 3. Record sustained rate | Sustained throughput >= 80 Gbps with < 1% loss | Critical | Not Started
NFT-002 | Performance | IPS Throughput | Validate 40 Gbps IPS throughput with inspection | IPS enabled; traffic generator ready | 1. Enable IPS on all policies; 2. Run throughput test; 3. Measure inspection rate | IPS throughput >= 40 Gbps with full inspection | Critical | Not Started
NFT-003 | Performance | HA Failover Time | Validate sub-second failover for HA cluster | HA cluster operational; traffic flowing | 1. Establish baseline traffic; 2. Trigger failover; 3. Measure interruption duration | Failover completes in < 1 second; traffic resumes | Critical | Not Started
NFT-004 | Security | VPN Encryption | Validate AES-256-GCM encryption for VPN tunnels | VPN tunnels established; packet capture ready | 1. Establish VPN session; 2. Capture encrypted packets; 3. Verify encryption algorithm | All VPN traffic encrypted with AES-256-GCM | Critical | Not Started
NFT-005 | Reliability | Session Persistence | Validate sessions survive HA failover | Active sessions established; HA cluster ready | 1. Establish 1000 TCP sessions; 2. Trigger failover; 3. Verify session continuity | All sessions persist through failover; no drops | High | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Business Process | Policy Migration Accuracy | Validate all legacy policies migrated correctly | Policy migration complete; legacy config available | 1. Compare legacy vs SRX policies; 2. Test sample traffic flows; 3. Verify no gaps | 100% policy accuracy; all traffic flows match legacy | High | Not Started
UAT-002 | Business Process | Site-to-Site VPN Connectivity | Validate VPN tunnels to all branch sites | VPN configuration complete; branch sites online | 1. Verify tunnel status all 30 tunnels; 2. Test bidirectional traffic; 3. Measure latency | All tunnels UP; traffic flows bidirectionally; latency < 50ms | High | Not Started
UAT-003 | User Interface | Security Director Dashboard | Validate monitoring dashboard functionality | Security Director operational; devices connected | 1. Access dashboard; 2. Verify device status display; 3. Test alert generation | Dashboard displays real-time status; alerts functional | Medium | Not Started
UAT-004 | Business Process | SSL VPN Remote Access | Validate SSL VPN for remote user connectivity | SSL VPN configured; test user accounts ready | 1. Connect via Juniper Secure Connect; 2. Access internal resources; 3. Verify MFA | Users authenticate with MFA; access internal resources | High | Not Started
UAT-005 | Business Process | SIEM Log Integration | Validate security logs forwarded to Splunk | Syslog configured; Splunk collector operational | 1. Generate security events; 2. Search Splunk for events; 3. Verify event format | Events received in Splunk within 30 seconds; correct format | High | Not Started