## Slide 1
Project Closeout
Juniper Mist AI Network
Project Manager | November 28, 2025

## Slide 2
Executive Summary
Project Duration: 8 weeks, completed on schedule
Budget: $222,724 delivered on budget
Go-Live Date: [DATE] as planned
Coverage: 50 AP45 WiFi 6E access points deployed
SLE Achievement: 99.2% successful connections (target: 99%)
Marvis AI: Operational with proactive anomaly detection
User Impact: 60% reduction in wireless helpdesk tickets
Juniper Mist AI Network
Notes: *Talking Points:*
- Open with confidence - project delivered on time and on budget
- WiFi 6E provides 8x throughput improvement over legacy WiFi 5
- Marvis AI eliminates manual troubleshooting, averaging 90% faster resolution
- Location services operational with vBLE for wayfinding
- Client team trained and independently operating Mist Cloud dashboard

## Slide 3
Solution Architecture
Access Layer
  50 AP45 WiFi 6E access points
  9.6 Gbps tri-band throughput
  Built-in vBLE for location
Network Layer
  4 EX4400 PoE switches
  Wired Assurance enabled
  Unified Mist management
Cloud Intelligence
  Mist Cloud AI platform
  Marvis virtual assistant
  Real-time SLE monitoring
Juniper Mist AI Network
Notes: *Talking Points:*
- Walk through architecture from client device to cloud
- AP45 provides WiFi 6E with 6 GHz band for high-density areas
- EX4400 switches provide PoE++ power and Wired Assurance
- Mist Cloud eliminates on-premises controller infrastructure
- All management through single Mist dashboard

## Slide 4
Deliverables Inventory
Deliverable | Purpose | Location
RF Site Survey Report | Coverage predictions and AP placement design | `/delivery/rf-survey.pdf`
Detailed Design Document | Architecture, SSIDs, VLANs, security config | `/delivery/detailed-design.docx`
Implementation Guide | Step-by-step deployment procedures | `/delivery/implementation-guide.docx`
AP Placement Maps | Floor-by-floor AP locations with coverage | `/delivery/ap-placement-maps/`
Test Plan & Results | RF validation, SLE testing, UAT results | `/delivery/test-plan.xlsx`
Operations Runbook | Day-to-day wireless operations procedures | `/delivery/operations-runbook.docx`
Administrator Training | Mist dashboard and Marvis training | Recorded sessions available
As-Built Documentation | Final configuration and network diagrams | `/delivery/as-built/`
Juniper Mist AI Network
Notes: *Talking Points:*
- All deliverables have been reviewed and accepted by client team
- RF site survey used Mist AI predictive modeling for accurate planning
- Training recordings available for future team member onboarding
- Operations runbook covers common tasks and troubleshooting
- As-built documentation reflects actual production configuration

## Slide 5
Quality & Performance
Wireless SLE Results
  Successful Connections: 99.2% (target: 99%)
  Coverage SLE: 98.5% (target: 95%)
  Capacity SLE: 99.1% (target: 95%)
  Roaming SLE: 97.8% (target: 95%)
  Throughput SLE: 98.7% (target: 95%)
Deployment Metrics
  Access Points Deployed: 50/50 (100%)
  RF Coverage: 100% building area
  Location Accuracy: 3.2 meters (target: 3-5m)
  Test Cases Passed: 42/42 (100%)
  Training Completed: 10 administrators
Juniper Mist AI Network
Notes: *Talking Points:*
- All SLE targets met or exceeded
- RF validation confirmed complete building coverage
- Location services accuracy exceeds specification
- Roaming performance tested across all floor transitions
- Client team certified on Mist Cloud administration

## Slide 6
Benefits Realized
Benefit Category | Target | Achieved | Impact
Wireless Uptime | 99.9% | 99.95% | Zero unplanned wireless outages
Helpdesk Tickets | 60% reduction | 62% reduction | 31 fewer tickets per month
Troubleshooting Time | 90% faster | 92% faster | Marvis AI root cause in seconds
RF Optimization | Automated | 100% automated | Zero manual channel tuning
Client Experience | 99% SLE | 99.2% SLE | Measurable user satisfaction
Location Services | 3-5m accuracy | 3.2m accuracy | Wayfinding operational
Juniper Mist AI Network
Notes: *Talking Points:*
- 99.95% uptime means less than 4.5 hours downtime annually
- 62% reduction in helpdesk tickets frees IT staff for strategic work
- Marvis AI provides instant root cause analysis vs hours of packet captures
- Automated RF optimization eliminates quarterly manual site surveys
- SLE dashboard provides ongoing visibility into client experience

## Slide 7
Lessons Learned & Recommendations
What Worked Well
  Predictive RF site survey accuracy
  Floor-by-floor phased deployment
  Early RADIUS integration testing
  Daily SLE monitoring during rollout
  Comprehensive admin training
Challenges Overcome
  Dense construction in server room
  Legacy AP interference during cutover
  Guest portal customization
  vBLE calibration refinement
  VLAN trunk configuration
Recommendations
  Enable 6 GHz band for high-density
  Expand location analytics usage
  Implement Marvis Actions automation
  Schedule quarterly SLE reviews
  Plan capacity for IoT expansion
Juniper Mist AI Network
Notes: *Talking Points:*
- Predictive RF survey matched actual coverage within 3 dB
- Phased deployment allowed validation before legacy cutover
- Dense construction required 2 additional APs in server room
- Legacy AP interference resolved by coordinated cutover
- 6 GHz band provides cleanest RF environment for density

## Slide 8
Support Transition
Warranty (Days 1-30)
  Dedicated project team support
  Daily SLE health check reviews
  4-hour response for critical issues
  Configuration assistance
  Performance optimization
Steady State (Day 31+)
  Juniper JTAC 24x7 support
  4-hour hardware replacement
  Mist Cloud subscription support
  Monthly SLE trend reviews
  Annual architecture review
Escalation Contacts
  L1: Client NOC (15 min)
  L2: Client Network Team (1 hour)
  L3: JTAC (4 hour 24x7)
  Account: am@consulting.com
  Emergency: 1-888-314-JTAC
Juniper Mist AI Network
Notes: *Talking Points:*
- 30-day warranty period provides transition support
- Client team trained and capable of day-to-day operations
- Mist Cloud provides continuous updates and new features
- JTAC provides 24x7 expert support with 4-hour RMA
- Monthly SLE reviews ensure ongoing performance visibility

## Slide 9
Acknowledgments & Next Steps
Network team for infrastructure preparation and VLAN config
Facilities team for AP mounting access and coordination
Security team for RADIUS integration and policy validation
IT leadership for project prioritization and support
This Week: Final documentation handover and warranty start
Next 30 Days: Warranty support with daily SLE reviews
Next Quarter: 6 GHz band enablement planning
Ongoing: Monthly SLE reviews and quarterly optimization
Juniper Mist AI Network
Notes: *Talking Points:*
- Acknowledge the partnership - successful wireless transformation
- Network team's VLAN and trunk configuration enabled SSIDs
- Facilities coordination enabled efficient AP installation
- Security team validated 802.1X authentication flows
- 6 GHz band provides opportunity for even better performance

## Slide 10
Thank You
Notes: *Talking Points:*
- Open the floor for questions and discussion
- Have backup slides ready for deep-dive on RF, Marvis, location
- Offer to schedule follow-up sessions for specific topics
- Confirm warranty support contact procedures
- Celebrate the successful wireless transformation