## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Mist Ai Network
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | Project Manager | Not Started
Phase 1 | Requirements Gathering | 3 days | [START_DATE+1] | [START_DATE+4] | Project Kickoff | Wireless Architect | Not Started
Phase 1 | Building Floor Plan Review | 2 days | [START_DATE+2] | [START_DATE+4] | Requirements Gathering | Wireless Architect | Not Started
Phase 1 | RF Site Survey (Predictive) | 3 days | [START_DATE+4] | [START_DATE+7] | Floor Plan Review | Wireless Engineer | Not Started
Phase 1 | AP Placement Design | 2 days | [START_DATE+7] | [START_DATE+9] | RF Site Survey | Wireless Architect | Not Started
Phase 1 | WLAN Architecture Design | 2 days | [START_DATE+9] | [START_DATE+11] | AP Placement | Wireless Architect | Not Started
Phase 1 | Design Review and Approval | 2 days | [START_DATE+11] | [START_DATE+13] | WLAN Architecture | Network Manager | Not Started
Phase 2 | EX4400 Switch Deployment | 2 days | [START_DATE+13] | [START_DATE+15] | Design Approval | Network Engineer | Not Started
Phase 2 | Switch Configuration (Wired Assurance) | 2 days | [START_DATE+15] | [START_DATE+17] | Switch Deployment | Network Engineer | Not Started
Phase 2 | Mist Cloud Organization Setup | 1 day | [START_DATE+15] | [START_DATE+16] | Design Approval | Wireless Engineer | Not Started
Phase 2 | Site and Floor Plan Upload | 1 day | [START_DATE+16] | [START_DATE+17] | Mist Cloud Setup | Wireless Engineer | Not Started
Phase 2 | AP45 Installation (Floor 1) | 2 days | [START_DATE+17] | [START_DATE+19] | Switch Config | Field Engineer | Not Started
Phase 2 | AP45 Installation (Floor 2) | 2 days | [START_DATE+19] | [START_DATE+21] | Floor 1 Complete | Field Engineer | Not Started
Phase 2 | AP45 Installation (Floor 3) | 2 days | [START_DATE+21] | [START_DATE+23] | Floor 2 Complete | Field Engineer | Not Started
Phase 2 | AP45 Installation (Floor 4) | 2 days | [START_DATE+23] | [START_DATE+25] | Floor 3 Complete | Field Engineer | Not Started
Phase 2 | AP45 Installation (Floor 5) | 2 days | [START_DATE+25] | [START_DATE+27] | Floor 4 Complete | Field Engineer | Not Started
Phase 2 | SSID and VLAN Configuration | 2 days | [START_DATE+27] | [START_DATE+29] | All APs Installed | Wireless Engineer | Not Started
Phase 2 | RF Policy Configuration | 1 day | [START_DATE+29] | [START_DATE+30] | SSID Config | Wireless Engineer | Not Started
Phase 2 | 802.1X RADIUS Integration | 2 days | [START_DATE+30] | [START_DATE+32] | SSID Config | Security Engineer | Not Started
Phase 2 | Guest Portal Configuration | 1 day | [START_DATE+32] | [START_DATE+33] | RADIUS Integration | Wireless Engineer | Not Started
Phase 3 | Marvis AI Activation | 1 day | [START_DATE+33] | [START_DATE+34] | Guest Portal | Wireless Engineer | Not Started
Phase 3 | SLE Baseline Configuration | 1 day | [START_DATE+34] | [START_DATE+35] | Marvis Activation | Wireless Architect | Not Started
Phase 3 | Location Services (vBLE) Setup | 2 days | [START_DATE+35] | [START_DATE+37] | SLE Baseline | Wireless Engineer | Not Started
Phase 3 | Wayfinding Map Creation | 2 days | [START_DATE+37] | [START_DATE+39] | vBLE Setup | Wireless Engineer | Not Started
Phase 3 | Wired Assurance Activation | 1 day | [START_DATE+39] | [START_DATE+40] | Marvis Activation | Network Engineer | Not Started
Phase 3 | SIEM Integration (Syslog) | 1 day | [START_DATE+40] | [START_DATE+41] | Wired Assurance | Security Engineer | Not Started
Phase 4 | RF Validation Testing | 2 days | [START_DATE+41] | [START_DATE+43] | SIEM Integration | QA Engineer | Not Started
Phase 4 | Client Connectivity Testing | 2 days | [START_DATE+43] | [START_DATE+45] | RF Validation | QA Engineer | Not Started
Phase 4 | Roaming Performance Testing | 1 day | [START_DATE+45] | [START_DATE+46] | Connectivity Testing | QA Engineer | Not Started
Phase 4 | SLE Validation | 1 day | [START_DATE+46] | [START_DATE+47] | Roaming Testing | QA Engineer | Not Started
Phase 4 | Location Services Testing | 1 day | [START_DATE+47] | [START_DATE+48] | SLE Validation | QA Engineer | Not Started
Phase 4 | User Acceptance Testing | 2 days | [START_DATE+48] | [START_DATE+50] | Location Testing | Network Manager | Not Started
Phase 4 | Legacy AP Cutover | 2 days | [START_DATE+50] | [START_DATE+52] | UAT Complete | Network Engineer | Not Started
Phase 4 | Administrator Training | 1 day | [START_DATE+52] | [START_DATE+53] | Legacy Cutover | Training Lead | Not Started
Phase 4 | Documentation Finalization | 2 days | [START_DATE+53] | [START_DATE+55] | Admin Training | Technical Writer | Not Started
Phase 4 | Project Closure | 1 day | [START_DATE+55] | [START_DATE+56] | Documentation | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | [START_DATE] | Kickoff meeting completed; project charter signed; resources confirmed | Project Manager | Not Started
M2 | RF Design Approved | [START_DATE+13] | Site survey complete; AP placement approved; WLAN architecture finalized | Wireless Architect | Not Started
M3 | Infrastructure Deployed | [START_DATE+33] | 50 APs installed; switches configured; Mist Cloud operational | Network Engineer | Not Started
M4 | AI Services Active | [START_DATE+41] | Marvis AI operational; location services enabled; SLEs configured | Wireless Engineer | Not Started
M5 | Testing Complete | [START_DATE+52] | RF validation passed; 99% SLE achieved; UAT approved | QA Engineer | Not Started
M6 | Project Closure | [START_DATE+56] | Training complete; documentation delivered; warranty started | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | WA | WE | NE | SE | QA | TL | Client
Project Charter | A | C | I | I | I | I | I | C
RF Site Survey | A | R | C | I | I | I | I | I
WLAN Architecture | A | R | C | C | C | I | I | I
Switch Deployment | A | I | I | R | I | I | I | I
AP Installation | A | C | R | C | I | I | I | I
SSID Configuration | A | C | R | I | C | I | I | I
RADIUS Integration | A | C | C | I | R | I | I | I
Marvis AI Activation | A | C | R | I | I | I | I | I
Location Services | A | C | R | I | I | I | I | I
RF Validation Testing | A | C | C | I | I | R | I | I
SLE Validation | A | C | C | I | I | R | I | I
User Acceptance Testing | A | C | I | I | I | C | I | R
Administrator Training | A | I | I | I | I | I | R | R
Documentation | A | C | C | C | C | C | R | I
Project Closeout | A | C | C | C | C | C | C | R
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project and align on objectives and timeline | Project Manager | Day 1
Steering Committee | Weekly | Executive sponsors and PM | Strategic oversight and escalation resolution | Project Manager | Fridays 14:00
Status Meeting | Weekly | Core project team | Review progress and address blockers and risks | Project Manager | Mondays 10:00
Technical Review | Weekly | Wireless architect and engineers | Design decisions and technical issue resolution | Wireless Architect | Wednesdays 14:00
Installation Sync | Daily (Week 3-5) | Field engineers and network team | AP installation coordination and issue resolution | Field Engineer | Daily 08:00
Testing Review | Daily (Week 7) | QA and wireless engineers | Testing progress and defect resolution | QA Engineer | Daily 09:00
Training Sessions | Per schedule | Administrators and helpdesk | Knowledge transfer and skill development | Training Lead | Per schedule
Go-Live Readiness | Daily (Week 8) | Go-live team and stakeholders | Final validation and cutover checklist review | Project Manager | Daily 09:00