## Cover
Test Plan
Generated: | November 28, 2025
Solution: | Mist Ai Network
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Name | Description | Prerequisites | Expected Result | Priority | Duration | Owner
FT-001 | AP Cloud Connectivity | Verify all 50 APs connect to Mist Cloud and appear in dashboard | APs installed and powered | All APs show connected status with green LED | Critical | 30 min | Wireless Engineer
FT-002 | Corporate SSID Authentication | Test 802.1X authentication with valid AD credentials on Corporate SSID | RADIUS configured and SSID enabled | User authenticates and receives Corporate VLAN IP | Critical | 15 min | Wireless Engineer
FT-003 | Guest Portal Functionality | Verify guest captive portal displays and accepts terms of service | Guest SSID enabled with portal configured | User sees portal and gains access after acceptance | High | 15 min | Wireless Engineer
FT-004 | IoT SSID PSK Authentication | Test PSK authentication on IoT SSID with correct passphrase | IoT SSID enabled with PSK configured | Device connects and receives IoT VLAN IP | High | 10 min | Wireless Engineer
FT-005 | VLAN Assignment Verification | Verify clients receive correct VLAN based on SSID connection | All SSIDs configured with VLAN mappings | Corporate=VLAN200 Guest=VLAN300 IoT=VLAN400 | Critical | 20 min | Network Engineer
FT-006 | DHCP IP Assignment | Verify DHCP assigns IPs from correct scope for each VLAN | DHCP scopes configured for all VLANs | Clients receive IPs from correct DHCP range | Critical | 15 min | Network Engineer
FT-007 | DNS Resolution | Test DNS resolution from wireless clients on all SSIDs | DNS servers configured and accessible | Internal and external DNS queries resolve correctly | High | 10 min | Network Engineer
FT-008 | Internet Connectivity | Verify internet access from all wireless networks | Firewall rules configured for wireless VLANs | Clients can browse internet and access cloud services | High | 10 min | Network Engineer
FT-009 | Marvis AI Query Response | Test Marvis conversational interface with sample troubleshooting query | Marvis AI activated for site | Marvis returns relevant insights for query | High | 15 min | Wireless Engineer
FT-010 | SLE Dashboard Display | Verify SLE metrics display correctly in Mist dashboard | APs operational with client traffic | SLE categories show data for connections coverage capacity | High | 10 min | Wireless Engineer
FT-011 | Location Services Positioning | Test indoor positioning accuracy using mobile device | vBLE enabled and floor plans calibrated | Device location accurate within 3-5 meters | Medium | 30 min | Wireless Engineer
FT-012 | Wayfinding Navigation | Verify wayfinding provides directions to configured destinations | Wayfinding maps created with destinations | App displays correct navigation path to destination | Medium | 20 min | Wireless Engineer
FT-013 | Wired Assurance Switch View | Verify EX4400 switches appear in Mist Wired Assurance dashboard | Switches claimed to Mist organization | All 4 switches show connected with port status | High | 10 min | Network Engineer
FT-014 | AP Firmware Auto-Update | Verify APs update firmware during scheduled maintenance window | Auto-upgrade enabled with schedule set | APs update to latest firmware without manual intervention | Medium | 60 min | Wireless Engineer
FT-015 | RADIUS Failover | Test failover to secondary RADIUS server when primary unavailable | Secondary RADIUS configured | Authentication continues via secondary server | High | 20 min | Security Engineer

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Name | Description | Prerequisites | Expected Result | Priority | Duration | Owner
NF-001 | RF Coverage Validation | Walk test to verify signal strength meets -67 dBm minimum | All APs operational | Coverage exceeds -67 dBm in all required areas | Critical | 120 min | QA Engineer
NF-002 | 5 GHz Throughput Test | Measure single-client throughput on 5 GHz using iPerf3 | Test client with WiFi 6 support | Throughput exceeds 500 Mbps single stream | High | 30 min | QA Engineer
NF-003 | 6 GHz Throughput Test | Measure throughput on 6 GHz band using WiFi 6E client | Test client with WiFi 6E support | Throughput exceeds 1 Gbps with 160 MHz channel | High | 30 min | QA Engineer
NF-004 | Roaming Performance Test | Measure handoff time while walking between APs during voice call | Test client with voice application active | Roaming completes in less than 150ms with no call drop | Critical | 45 min | QA Engineer
NF-005 | High Density Client Test | Connect 50+ clients to single AP and measure performance | Multiple test devices available | AP maintains stability with 50 concurrent clients | High | 60 min | QA Engineer
NF-006 | Video Conferencing Quality | Test video call quality across multiple APs with roaming | Video conferencing application (Teams/Zoom) | Video quality maintains HD with no artifacts during roam | High | 30 min | QA Engineer
NF-007 | Channel Utilization Check | Verify RF optimization distributes clients across channels | Multiple clients connected across APs | No channel exceeds 60% utilization | Medium | 20 min | Wireless Engineer
NF-008 | PoE Power Verification | Verify all APs receive adequate PoE power from switches | APs connected to EX4400 switches | All APs show full power with Class 6 PoE | High | 15 min | Network Engineer
NF-009 | Mist Cloud Latency | Measure dashboard responsiveness and API response time | Active Mist Cloud session | Dashboard loads within 3 seconds API responds within 500ms | Medium | 15 min | Wireless Engineer
NF-010 | Location Accuracy Test | Measure positioning accuracy at 10 different building locations | vBLE calibration completed | Average accuracy within 3 meters across all test points | Medium | 45 min | QA Engineer
NF-011 | SLE Baseline Validation | Verify SLE metrics meet target thresholds over 24-hour period | Production traffic flowing through network | Successful Connect SLE exceeds 99% target | Critical | 24 hrs | Wireless Engineer
NF-012 | Switch Uplink Redundancy | Test failover when primary switch uplink is disconnected | Redundant uplinks configured | Traffic continues via secondary uplink within 1 second | High | 15 min | Network Engineer

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Name | Description | Prerequisites | Expected Result | Priority | Duration | Owner
UAT-001 | Employee WiFi Connection | Employee connects laptop to Corporate SSID and accesses resources | Corporate SSID operational | Employee connects and accesses internal applications | Critical | 15 min | Business User
UAT-002 | Guest WiFi Experience | Visitor connects to Guest WiFi and accepts portal terms | Guest SSID with portal enabled | Guest connects within 30 seconds of portal acceptance | High | 10 min | Business User
UAT-003 | Conference Room Coverage | Verify WiFi coverage and video quality in all conference rooms | APs covering conference areas | Video calls work without quality issues in all rooms | Critical | 60 min | Business User
UAT-004 | Mobile Device Roaming | Walk through building while on video call without disconnection | Mobile device on Corporate SSID | Call maintains quality throughout building walk | High | 30 min | Business User
UAT-005 | Marvis Self-Service Query | IT admin uses Marvis to troubleshoot simulated user complaint | Marvis AI enabled for admin | Admin identifies root cause using natural language query | Medium | 20 min | IT Admin
UAT-006 | Dashboard Navigation | IT admin navigates Mist dashboard to view AP health and clients | Admin trained on dashboard | Admin locates required information within 2 minutes | Medium | 15 min | IT Admin
UAT-007 | Helpdesk Ticket Resolution | Helpdesk uses SLE data to diagnose connectivity complaint | Helpdesk trained on SLE interpretation | Helpdesk identifies issue using SLE failure reason | Medium | 20 min | Helpdesk Staff
UAT-008 | Wayfinding Mobile Test | Employee uses wayfinding app to navigate to meeting room | Wayfinding configured with destinations | Employee successfully navigates using app directions | Medium | 15 min | Business User
UAT-009 | Legacy AP Cutover Impact | Verify no service disruption during legacy AP decommissioning | Cutover plan approved and scheduled | Users experience no connectivity loss during cutover | Critical | 120 min | Network Manager
UAT-010 | Post-Cutover Validation | Verify all wireless services operational after legacy removal | Legacy APs decommissioned | All users connected to new infrastructure with no complaints | Critical | 60 min | Network Manager