## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Network Analytics
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | EO Project Manager | Not Started
Discovery | Network Infrastructure Assessment | 5 days | [START_DATE+1] | [START_DATE+6] | Project Kickoff | EO Network Engineer | Not Started
Discovery | Device Compatibility Analysis (IOS-XE 16.12+) | 5 days | [START_DATE+3] | [START_DATE+8] | Network Assessment | EO Network Engineer | Not Started
Discovery | DNA Center Requirements Gathering | 4 days | [START_DATE+5] | [START_DATE+9] | Network Assessment | EO Quarterback | Not Started
Discovery | Integration Requirements (AD/ServiceNow/NetBox) | 3 days | [START_DATE+6] | [START_DATE+9] | Requirements Gathering | EO Automation Engineer | Not Started
Foundation | DNA Center Appliance Rack & Stack | 3 days | [START_DATE+9] | [START_DATE+12] | Discovery Complete | EO Network Engineer | Not Started
Foundation | DNA Center HA Configuration | 5 days | [START_DATE+12] | [START_DATE+17] | Rack & Stack | EO Network Engineer | Not Started
Foundation | Active Directory Integration Setup | 3 days | [START_DATE+15] | [START_DATE+18] | DNA Center Config | EO Automation Engineer | Not Started
Foundation | Pilot Device Onboarding (50 devices) | 7 days | [START_DATE+17] | [START_DATE+24] | DNA Center Config | EO Network Engineer | Not Started
Foundation | Policy Framework Design | 5 days | [START_DATE+19] | [START_DATE+24] | Pilot Onboarding | EO Quarterback | Not Started
Analytics | Full Device Onboarding (150 devices) | 10 days | [START_DATE+24] | [START_DATE+34] | Pilot Complete | EO Network Engineer | Not Started
Analytics | AI Network Analytics Configuration | 7 days | [START_DATE+28] | [START_DATE+35] | Device Onboarding | EO Quarterback | Not Started
Analytics | Predictive Insights Enablement | 5 days | [START_DATE+32] | [START_DATE+37] | Analytics Config | EO Quarterback | Not Started
Analytics | Network Policy Automation (VLAN/ACL) | 7 days | [START_DATE+35] | [START_DATE+42] | Analytics Config | EO Automation Engineer | Not Started
Analytics | Dashboard and Reporting Setup | 5 days | [START_DATE+38] | [START_DATE+43] | Policy Automation | EO Network Engineer | Not Started
Integration | Application Experience Monitoring Setup | 7 days | [START_DATE+43] | [START_DATE+50] | Analytics Operational | EO Quarterback | Not Started
Integration | ServiceNow ITSM Integration | 7 days | [START_DATE+45] | [START_DATE+52] | App Monitoring | EO Automation Engineer | Not Started
Integration | NetBox IPAM Integration | 5 days | [START_DATE+50] | [START_DATE+55] | ServiceNow Integration | EO Automation Engineer | Not Started
Integration | Integration Testing and Validation | 5 days | [START_DATE+55] | [START_DATE+60] | All Integrations | EO Network Engineer | Not Started
Testing | Functional Testing | 5 days | [START_DATE+60] | [START_DATE+65] | Integration Complete | EO Network Engineer | Not Started
Testing | Performance and Load Testing | 4 days | [START_DATE+63] | [START_DATE+67] | Functional Testing | EO Quarterback | Not Started
Testing | Security Validation | 3 days | [START_DATE+65] | [START_DATE+68] | Performance Testing | Security Team | Not Started
Testing | User Acceptance Testing | 5 days | [START_DATE+68] | [START_DATE+73] | Security Validation | Network Operations | Not Started
Optimization | Policy Fine-tuning and Optimization | 5 days | [START_DATE+73] | [START_DATE+78] | UAT Complete | EO Quarterback | Not Started
Optimization | Team Training - DNA Center Admin | 8 hours | [START_DATE+78] | [START_DATE+79] | Optimization | EO Network Engineer | Not Started
Optimization | Team Training - AI Analytics Operations | 8 hours | [START_DATE+79] | [START_DATE+80] | Admin Training | EO Quarterback | Not Started
Optimization | Team Training - Policy Automation | 8 hours | [START_DATE+80] | [START_DATE+81] | Analytics Training | EO Automation Engineer | Not Started
Optimization | Team Training - Troubleshooting Workshop | 8 hours | [START_DATE+81] | [START_DATE+82] | Automation Training | EO Network Engineer | Not Started
Go-Live | Production Go-Live | 2 days | [START_DATE+82] | [START_DATE+84] | Training Complete | EO Project Manager | Not Started
Support | Hypercare Support Week 1 | 7 days | [START_DATE+84] | [START_DATE+91] | Go-Live | EO Network Engineer | Not Started
Support | Hypercare Support Week 2 | 7 days | [START_DATE+91] | [START_DATE+98] | Hypercare Week 1 | EO Network Engineer | Not Started
Support | Hypercare Support Weeks 3-4 | 14 days | [START_DATE+98] | [START_DATE+112] | Hypercare Week 2 | EO Network Engineer | Not Started
Closure | Knowledge Transfer Completion | 5 days | [START_DATE+105] | [START_DATE+110] | Hypercare | EO Project Manager | Not Started
Closure | Documentation Delivery | 3 days | [START_DATE+108] | [START_DATE+111] | Knowledge Transfer | EO Quarterback | Not Started
Closure | Project Closure and Lessons Learned | 2 days | [START_DATE+111] | [START_DATE+113] | Documentation | EO Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Foundation Complete | [START_DATE+28] | DNA Center HA deployed; 50 pilot devices onboarded; AD integration operational | EO Network Engineer | Not Started
M2 | Analytics Operational | [START_DATE+56] | All 200 devices onboarded; AI analytics enabled; Network policies automated | EO Quarterback | Not Started
M3 | Integrations Complete | [START_DATE+70] | ServiceNow and NetBox integrations live; Application monitoring configured | EO Automation Engineer | Not Started
M4 | Go-Live | [START_DATE+84] | Production operational; Team trained (32 hours); All tests passed | EO Project Manager | Not Started
M5 | Hypercare End | [START_DATE+112] | Support period complete; Knowledge transfer done; Lessons learned documented | EO Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | QB | NetEng | AutoEng | SecArch | NetOps | NetLead | AppSME | Client
Project Charter & Kickoff | A | C | C | I | I | I | C | I | C
Network Infrastructure Assessment | A | C | R | I | I | I | C | I | I
Device Compatibility Analysis | A | C | R | I | I | I | C | I | I
DNA Center Requirements | A | R | C | C | C | I | C | C | C
DNA Center HA Deployment | A | C | R | I | I | I | I | I | I
Active Directory Integration | A | C | I | R | C | I | I | I | C
Pilot Device Onboarding (50) | A | C | R | I | I | I | C | I | I
Policy Framework Design | A | R | C | C | C | I | C | I | I
Full Device Onboarding (150) | A | C | R | I | I | C | C | I | I
AI Analytics Configuration | A | R | C | I | I | I | C | I | I
Network Policy Automation | A | C | C | R | C | I | C | I | I
Application Experience Setup | A | R | C | I | I | I | I | R | C
ServiceNow Integration | A | C | I | R | I | C | I | I | C
NetBox Integration | A | C | I | R | I | C | I | I | C
Testing and Validation | A | C | R | C | C | C | C | I | I
Security Validation | A | I | C | I | R | I | C | I | C
User Acceptance Testing | A | C | I | I | I | R | C | C | R
Team Training (32 hours) | A | R | R | R | I | C | C | I | I
Production Go-Live | A | C | C | C | I | C | C | I | R
Hypercare Support | A | C | R | C | I | C | C | I | I
Legend:
R | A A A A A A A A A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on DNA Center objectives and AI analytics strategy | EO Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and major decisions on network transformation | EO Project Manager | Alternate Tuesdays
Project Status Meeting | Weekly | Core project team | Review progress and address blockers across all workstreams | EO Project Manager | Mondays 10:00
Technical Design Review | Weekly | Technical leads | DNA Center architecture decisions and integration challenges | EO Quarterback | Wednesdays 14:00
Device Onboarding Standup | Daily | Onboarding team | Device deployment progress and compatibility issues | EO Network Engineer | Daily 09:30
Risk & Issue Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | EO Project Manager | Alternate Fridays
Integration Review | Weekly | Integration team | ServiceNow/NetBox integration progress and API validation | EO Automation Engineer | Thursdays 11:00
Security Review | Bi-weekly | Security team and architects | Security controls and compliance validation | Security Architect | Alternate Wednesdays
Network Operations Sync | Weekly | Network operations team | AI analytics feedback and operational workflow validation | Network Lead | Fridays 14:00
Go-Live Readiness | Daily (2 weeks pre) | Go-live team | Deployment preparation and checklist review | EO Project Manager | Daily 09:00
Post Go-Live Review | Weekly (hypercare) | Support and operations | Production stability and AI analytics performance | EO Network Engineer | Mondays 11:00