## Cover
[DOCUMENT TITLE]
Level of Effort
JUNIPER - Network - Mist Ai Network
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | WiFi 6E Access Points | 50 Juniper AP45 APs | 50 APs single building | 150 APs multi-building | 500+ APs campus | Enterprise wireless deployment with Mist AI
Solution Scope | Wired Assurance | 4 EX4400 PoE switches | 4 EX4400 switches | 12 EX4400 switches | 30+ EX switches | Wired infrastructure with AI-driven management
Integration | SSIDs and VLANs | 3-5 wireless networks | 3-5 SSIDs (corp guest IoT) | 8-10 SSIDs multi-tenant | 15+ SSIDs complex segmentation | Wireless network segmentation and access control
Integration | External System Integrations | 2 integrations | 2 integrations (auth monitoring) | 4-6 systems | 8+ systems or complex protocols | RADIUS SIEM and authentication integration
Integration | Location Services | Indoor positioning enabled | vBLE for 1 building | vBLE for multi-building campus | Advanced wayfinding asset tracking | Virtual Bluetooth LE and location analytics
User Base | Concurrent Wireless Users | 500-1000 concurrent users | 500-1000 users | 2000-5000 users | 10000+ users | Peak concurrent wireless client capacity
User Base | Network Administrators | 3 wireless administrators | 2-3 administrators | 5-8 administrators | 12+ administrators | Wireless network administrators and operators
Data Volume | Access Point Count | 50 access points | 50 APs single site | 150 APs multi-site | 500+ APs campus | Total AP deployment for coverage and capacity
Data Volume | Client Device Count | 2000 total devices | 2000 devices | 8000 devices | 20000+ devices | Total wireless client device inventory
Technical Environment | Building Types | Office commercial building | Single building type | Multi-building campus | Complex campus multiple building types | Facility type and RF environment complexity
Technical Environment | Deployment Locations | Single building multi-floor | Single building | 2-3 buildings | 5+ buildings or campus | Geographic distribution for wireless deployment
Technical Environment | RF Environment | Standard office construction | Standard office low interference | High-density or industrial | Complex RF stadium healthcare | RF propagation and interference considerations
Security & Compliance | Authentication Methods | 802.1X RADIUS | Basic 802.1X + PSK | Advanced multi-factor PKI | Complex federation SSO | Enterprise wireless authentication architecture
Security & Compliance | Compliance Frameworks | Basic security SOC 2 | 1-2 basic standards | 3-4 industry standards | Multiple complex frameworks (HIPAA PCI) | Regulatory compliance for wireless security
Performance | Coverage Requirements | Standard office coverage | Standard office coverage | High-density conference rooms | Mission-critical 99.99% uptime | Wireless coverage density and performance
Performance | Client Experience SLEs | 99% successful connects | Standard SLEs 95% | Enhanced SLEs 98% | Premium SLEs 99.5%+ | Mist AI Service Level Expectations tracking
Environment | Deployment Environments | 2 environments (staging prod) | 2 environments | 3 environments (dev stage prod) | 4+ environments with lab | Environment management for wireless deployment

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Wireless Requirements Assessment, Facility Assessment, Network Integration Analysis)
Planning | PLANNING_MX | 1 | All Planning phase tasks (RF Site Survey, WLAN Architecture Design, Location Services Design, Implementation Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Switch Infrastructure Deployment, Mist Cloud Configuration, AP Installation, Authentication Integration, Marvis AI Activation, Location Services Setup, Wired Assurance Config)
Testing | TESTING_MX | 1 | All Testing phase tasks (RF Validation Testing, Client Connectivity Testing, Location Services Testing, Performance Testing, User Acceptance Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Legacy AP Decommissioning, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Mist Dashboard Training, Marvis AI Training, Documentation Development)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, SLE Baseline Establishment)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Wireless Requirements Assessment | Analyze current wireless infrastructure coverage and performance issues | EO Engineer | 32 |  |  | 200 |  |  | Document WiFi dead zones user complaints and capacity needs
Discovery | Facility Assessment | Review building layouts construction materials and coverage requirements | EO Engineer | 24 |  |  | 200 |  |  | Building floor plans and RF propagation analysis for AP placement
Discovery | Network Integration Analysis | Assess existing wired network VLANs and authentication infrastructure | EO Engineer | 16 |  |  | 175 |  |  | VLAN design DHCP scopes and RADIUS integration requirements
Planning | RF Site Survey | Conduct predictive RF site survey using Mist AI planning tools | EO Engineer | 40 |  |  | 200 |  | Facility Assessment | Deliverable: AP placement design for optimal coverage and capacity
Planning | WLAN Architecture Design | Design SSID strategy VLAN segmentation and security policies | EO Engineer | 32 |  |  | 200 |  | Network Integration Analysis | Corporate guest IoT and voice wireless networks architecture
Planning | Location Services Design | Design vBLE indoor positioning wayfinding and asset tracking | EO Engineer | 24 |  |  | 200 |  | RF Site Survey | Location-based services and occupancy analytics requirements
Planning | Implementation Planning | Develop AP installation schedule and cutover strategy | EO Engineer | 16 |  |  | 150 |  | WLAN Architecture Design | Deliverable: Minimize business disruption during wireless deployment
Development | Switch Infrastructure Deployment | Deploy and configure EX4400 PoE switches for AP power and connectivity | EO Engineer | 32 |  |  | 200 |  | Implementation Planning | 4 switches with uplinks to existing network and PoE capacity
Development | Mist Cloud Configuration | Configure Mist cloud with SSIDs VLANs RF policies and security settings | EO Engineer | 40 |  |  | 200 |  | Switch Infrastructure Deployment | WLAN profiles RF templates and wireless policy deployment
Development | AP Installation | Mount cable and deploy 50 Juniper AP45 WiFi 6E access points | EO Engineer | 100 |  |  | 150 |  | Mist Cloud Configuration | Physical installation across multiple buildings and floors
Development | Authentication Integration | Integrate Mist with RADIUS Active Directory or SSO for enterprise auth | EO Engineer | 24 |  |  | 200 |  | AP Installation | 802.1X configuration and user authentication testing validation
Development | Marvis AI Activation | Enable Marvis VNA for AI-driven troubleshooting and anomaly detection | EO Engineer | 16 |  |  | 200 |  | Authentication Integration | AI virtual assistant configuration and SLE baseline establishment
Development | Location Services Setup | Configure vBLE indoor positioning wayfinding maps and asset tracking | EO Engineer | 32 |  |  | 200 |  | Marvis AI Activation | Virtual BLE beacons location analytics and wayfinding setup
Development | Wired Assurance Config | Onboard EX4400 switches to Wired Assurance for unified management | EO Engineer | 16 |  |  | 180 |  | Location Services Setup | Wired network visibility and AI-driven switch operations
Testing | RF Validation Testing | Conduct coverage testing throughput validation and roaming verification | EO Engineer | 40 |  |  | 200 |  | Wired Assurance Config | Walk-through testing with spectrum analyzer and wireless client devices
Testing | Client Connectivity Testing | Test authentication client onboarding and application performance | EO Engineer | 24 |  |  | 175 |  | RF Validation Testing | Validate corporate guest IoT and voice wireless network connectivity
Testing | Location Services Testing | Validate vBLE accuracy wayfinding navigation and asset tracking | EO Engineer | 16 |  |  | 175 |  | Client Connectivity Testing | Indoor positioning accuracy and mobile app integration testing
Testing | Performance Testing | Conduct throughput testing with high-density client load | EO Engineer | 16 |  |  | 200 |  | Location Services Testing | Validate capacity and performance under real-world wireless conditions
Testing | User Acceptance Testing | Coordinate UAT with IT and business users for production readiness | EO Engineer | 24 |  |  | 150 |  | Performance Testing | End-user validation of wireless coverage performance and features
Deployment | Legacy AP Decommissioning | Decommission old wireless infrastructure and migrate to Mist APs | EO Engineer | 32 |  |  | 175 |  | User Acceptance Testing | Incremental AP cutover with minimal business disruption
Deployment | Go-Live Support | Provide on-site support during production cutover and initial operation | EO Engineer | 40 |  |  | 200 |  | Legacy AP Decommissioning | First week post-deployment support and wireless issue resolution
Training | Mist Dashboard Training | Train IT administrators on Mist cloud dashboard and configuration | EO Engineer | 16 |  |  | 200 |  | Go-Live Support | 2-day hands-on training for wireless network administrators
Training | Marvis AI Training | Train IT staff on Marvis VNA conversational AI and troubleshooting | EO Engineer | 8 |  |  | 200 |  | Mist Dashboard Training | AI-driven operations and proactive wireless monitoring training
Training | Documentation Development | Create as-built RF maps configuration guides and troubleshooting runbooks | EO Engineer | 32 |  |  | 150 |  | Marvis AI Training | Deliverable: Operational documentation and wireless knowledge transfer
Closeout | Knowledge Transfer | Transfer solution ownership to IT operations and support teams | EO Engineer | 16 |  |  | 175 |  | Documentation Development | Comprehensive handover including operational procedures and escalation
Closeout | SLE Baseline Establishment | Establish Service Level Expectation baselines for client experience monitoring | EO Engineer | 8 |  |  | 150 |  | Knowledge Transfer | Successful connects time to connect throughput roaming capacity SLEs
Management | Technical Leadership | Wireless architecture oversight and RF design review | EO Quarterback |  |  |  | 200 |  |  | 25% of engineering effort for wireless technical guidance and escalation
Management | Project Management | Project coordination stakeholder management and timeline oversight | EO Project Manager |  |  |  | 150 |  |  | 20% of engineering effort for wireless project delivery coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase-based multipliers in Estimate Settings based on wireless deployment scope

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Juniper Partner Services Credit | -8000 | Juniper Partner Network credit for wireless architecture and Mist AI deployment services
Implementation Discount | 0 | No implementation discount applicable
TOTAL