## Cover
[DOCUMENT TITLE]
Level of Effort
DELL - Cloud - Vxrail Hci
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Cluster Size | 4-node VxRail E560 cluster | 4-node entry | 6-node | 8-12 node | Cluster scale and VM capacity
Solution Scope | Storage Capacity | 40TB usable all-flash SSD | 20TB usable | 40TB usable | 80TB+ usable | vSAN storage with deduplication
Integration | vSphere Version | vSphere 8 Enterprise Plus | vSphere 7.0 | vSphere 8.0 | vSphere 8 + NSX | VMware software stack complexity
Integration | Backup Integration | Veeam Backup & Replication | No backup | Veeam or Dell IDPA | Enterprise backup + DR | Data protection scope
User Base | VM Count | 250 virtual machines | <100 VMs | 250 VMs | 500+ VMs | Virtual machine migration scale
User Base | Admin Team | 3-5 virtualization administrators | 1-2 admins | 3-5 admins | 6+ admins | Team size for training and support
Data Volume | Storage Type | All-flash SSD vSAN | Hybrid SSD+HDD | All-flash SSD | All-NVMe performance | Performance tier and capacity
Data Volume | VM Size | Average 500GB per VM | Small VMs (100GB) | Medium (500GB) | Large (1TB+) | VM storage consumption
Technical Environment | Current Virtualization | VMware vSphere 7.0 on traditional SAN | vSphere 6.x | vSphere 7.x | Multi-hypervisor | Migration complexity
Technical Environment | Legacy Infrastructure | EMC Unity or NetApp SAN | Single SAN | Multi-vendor SAN | Complex legacy | Migration source complexity
Technical Environment | Network Fabric | 25GbE ToR switches for vSAN | 10GbE network | 25GbE network | 100GbE fabric | Network bandwidth and latency
Security & Compliance | Data Sensitivity | Internal business data | Public data | Confidential data | Regulated (HIPAA PCI) | Data classification and controls
Security & Compliance | Encryption | vSAN encryption at rest | No encryption | vSAN encryption | vSAN + VM encryption | Security and compliance requirements
Performance | VM Density | 60 VMs per node average | Low density | Medium density | High density | Consolidation ratio
Performance | vSAN Performance | Mixed workload 10K IOPS per VM | Low IOPS | Mixed workload | High IOPS (databases) | Performance requirements
Environment | Migration Approach | Phased vMotion migration | Forklift cutover | Phased vMotion | Parallel run | Migration risk and approach

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (VM Assessment vSphere Inventory SAN Baseline)
Planning | PLANNING_MX | 1 | All Planning phase tasks (VxRail Sizing vSAN Design Network Architecture)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (VxRail Installation vSphere Configuration vSAN Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Performance Testing vMotion Validation HA Failover)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (VM Migration SAN Decommission)
Training | TRAINING_MX | 1 | All Training phase tasks (vSphere Training vSAN Administration)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer Performance Baseline)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | VM Inventory | Inventory VMs workloads and resource consumption | EO Engineer | 24 | 1 |  | 150 |  |  | Includes VM sizing and capacity planning
Discovery | SAN Baseline | Document current SAN infrastructure and costs | EO Engineer | 16 |  |  | 150 |  |  | Customer must provide SAN support contracts
Discovery | vSphere Assessment | Assess vSphere version and configuration | EO Engineer | 16 |  |  | 150 |  |  | Identifies vSphere upgrade requirements
Discovery | Network Survey | Survey data center network and rack resources | EO Engineer | 8 |  |  | 140 |  |  | Validates 25GbE network and rack space
Planning | VxRail Sizing | Size VxRail cluster nodes and capacity | EO Engineer | 32 |  |  | 200 |  | VM Inventory | Deliverable: VxRail sizing with node configuration
Planning | vSAN Design | Design vSAN storage policies and capacity | EO Engineer | 24 |  |  | 200 |  | VxRail Sizing | vSAN storage policy and FTT configuration
Planning | Network Design | Design vSphere distributed switching and vSAN network | EO Engineer | 16 |  |  | 175 |  | Network Survey | Network diagram with vSAN and vMotion VLANs
Planning | Migration Planning | Develop VM migration plan and timeline | EO Engineer | 24 |  |  | 175 |  | VM Inventory | Deliverable: Migration timeline with dependencies
Development | VxRail Procurement | Order VxRail E560 nodes and switches | EO Engineer | 8 |  |  | 150 |  | VxRail Sizing | Coordinate Dell sales and track delivery
Development | VxRail Installation | Dell ProDeploy rack installation and cabling | EO Engineer | 24 |  |  | 160 |  | VxRail Procurement | ProDeploy on-site installation and power
Development | vSphere Configuration | Configure vCenter and vSphere cluster | EO Engineer | 32 |  |  | 175 |  | VxRail Installation | DRS HA and distributed switching setup
Development | vSAN Configuration | Configure vSAN storage policies and health | EO Engineer | 24 |  |  | 175 |  | vSphere Configuration | vSAN disk groups and storage policies
Development | Backup Integration | Integrate Veeam backup with VxRail | EO Engineer | 16 |  |  | 160 |  | vSAN Configuration | Veeam backup repository and job configuration
Testing | Performance Testing | Benchmark vSAN IOps and latency | EO Engineer | 16 |  |  | 150 |  | vSAN Configuration | IOmeter validation of vSAN performance
Testing | HA Failover Testing | Test vSphere HA and node failover | EO Engineer | 8 |  |  | 150 |  | Performance Testing | Validate N+1 HA and automatic failover
Testing | Pilot VM Migration | Migrate 10-20 pilot VMs via vMotion | EO Engineer | 16 |  |  | 150 |  | Performance Testing | Customer must identify pilot VMs
Testing | Backup Testing | Test Veeam backup and restore | EO Engineer | 8 |  |  | 140 |  | Pilot VM Migration | Validate backup success and recovery
Deployment | VM Migration | Phased vMotion migration of all VMs | EO Engineer | 48 |  |  | 175 |  | Pilot VM Migration | 20-50 VMs per weekend migration window
Deployment | Application Validation | Validate application connectivity post-migration | EO Engineer | 16 |  |  | 150 |  | VM Migration | Application team smoke testing
Deployment | SAN Decommission | Decommission legacy SAN infrastructure | EO Engineer | 8 |  |  | 140 |  | Application Validation | Coordinate SAN support cancellation
Training | vSphere Training | Train team on vSphere 8 features | EO Engineer | 16 |  |  | 150 |  | Application Validation | vSphere 8 DRS HA and distributed switching
Training | vSAN Training | Train team on vSAN administration and troubleshooting | EO Engineer | 16 |  |  | 175 |  | vSphere Training | vSAN health monitoring and capacity management
Training | Documentation | Create runbooks and architecture documentation | EO Engineer | 16 |  |  | 140 |  | vSAN Training | Deliverable: As-built docs and troubleshooting guides
Closeout | Knowledge Transfer | Transfer VxRail ownership to virtualization team | EO Engineer | 8 |  |  | 150 |  | Documentation | Comprehensive handover
Closeout | Performance Baseline | Establish vSAN performance baseline | EO Engineer | 4 |  |  | 140 |  | Knowledge Transfer | Baseline IOps latency and throughput
Management | Technical Leadership | Quarterback VMware architecture review | EO Quarterback |  |  |  | 200 |  |  | vSphere and vSAN architecture guidance
Management | Project Management | Project coordination and vendor management | EO Project Manager |  |  |  | 175 |  |  | Dell coordination migration planning
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | Update phase multipliers based on VM count

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Dell Partner Discount | -20000 | Dell Titanium Partner discount on VxRail hardware (negotiate 5-10%)
Implementation Discount | 0 | No implementation discount applicable
TOTAL