# Statement of Work

Dell Technologies - Dell VxRail HCI Platform

| Client: | [Client Name] |
| --- | --- |
| Date: | November 22, 2025 |
| Consulting Company: | Your Consulting Company |
| Submitted By: | [Consultant Name ¦ Email ¦ Phone] |
| Opportunity No: | OPP-2025-001 |
| Version: | 1.0 |

# Table of Contents

1 Introduction
    1.1 Purpose
        1.1.1 Scope
2 Table Content
3 Image Section
4 Additional Content
5 Sign-Off

# List of Figures

Figure 1: Sample Architecture Diagram

# List of Tables

Table 1: Sample Deliverables Table

# 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for implementing Dell VxRail HCI Platform for [Client Name]. This engagement will deliver on-premises AI/ML computing infrastructure through Dell Precision 7960 workstations with NVIDIA RTX A6000 GPUs and PowerScale shared storage to reduce cloud GPU costs by 60-70% and achieve data sovereignty.

Project Duration: 6 weeks

# 2 Background & Objectives

## 2.1 Current State

[Client Name] currently spends approximately $58,000/month on cloud GPU instances (AWS p4d.24xlarge) for AI/ML model training across 10 data scientists. Key challenges include:

• High Cloud Costs: $693K annual spend on cloud GPU compute creating budget pressure

• Data Transfer Bottlenecks: Multi-terabyte datasets taking hours to transfer to/from cloud storage

• Data Sovereignty Concerns: Sensitive training data required to remain on-premises for compliance

• Limited GPU Memory: Cloud instance limits preventing training of larger models

• Productivity Loss: Dataset download waits and network latency reducing data scientist productivity

## 2.2 Business Objectives

• Reduce Cloud Costs: Eliminate cloud GPU spend through on-premises Dell Precision workstations with RTX A6000 GPUs achieving 60-70% cost reduction vs AWS p4d baseline

• Improve Training Performance: Reduce model training time by 50% through local NVMe storage eliminating dataset transfer latency and providing dedicated 48GB GPU memory per workstation

• Enable Data Sovereignty: Keep all AI training datasets on-premises to meet compliance requirements and eliminate cloud data residency concerns

• Increase Productivity: Provide dedicated high-performance workstations allowing data scientists to iterate faster and train larger models without cloud quota limitations

• Support Team Growth: Establish scalable on-premises infrastructure supporting current 10-person team with capacity for future expansion to 25+ data scientists

• Foundation for AI Platform: Build foundation for expanding AI infrastructure to support distributed training and MLOps capabilities

## 2.3 Success Metrics

• 60%+ reduction in AI infrastructure costs within 12 months (vs cloud baseline)

• 50% reduction in model training time (vs current cloud performance)

• 100% data sovereignty compliance (all datasets on-premises)

• 95%+ GPU utilization across workstation fleet

• 10 data scientists fully equipped and trained within 6 weeks

• ROI payback within 3-6 months

# 3 Scope of Work

## 3.1 In Scope

The following services and deliverables are included in this SOW:

• AI workload assessment and infrastructure sizing

• Dell Precision workstation and PowerScale NAS procurement coordination

• Data center infrastructure validation (power, cooling, network)

• Hardware installation and OS/GPU driver configuration

• ML framework stack setup (PyTorch, TensorFlow, CUDA)

• Shared storage configuration and dataset migration

• Performance benchmarking and validation

• User and administrator training

• Knowledge transfer and documentation

### 3.1.1 Scope Parameters

This engagement is sized based on the following parameters:

| Category | Parameter | Scope |
| --- | --- | --- |
| Solution Scope | Cluster Size | 4-node VxRail E560 cluster |
| Solution Scope | Storage Capacity | 40TB usable all-flash SSD |
| Integration | vSphere Version | vSphere 8 Enterprise Plus |
| Integration | Backup Integration | Veeam Backup & Replication |
| User Base | VM Count | 250 virtual machines |
| User Base | Admin Team | 3-5 virtualization administrators |
| Data Volume | Storage Type | All-flash SSD vSAN |
| Data Volume | VM Size | Average 500GB per VM |
| Technical Environment | Current Virtualization | VMware vSphere 7.0 on traditional SAN |
| Technical Environment | Legacy Infrastructure | EMC Unity or NetApp SAN |
| Technical Environment | Network Fabric | 25GbE ToR switches for vSAN |
| Security & Compliance | Data Sensitivity | Internal business data |
| Security & Compliance | Encryption | vSAN encryption at rest |
| Performance | VM Density | 60 VMs per node average |
| Performance | vSAN Performance | Mixed workload 10K IOPS per VM |
| Environment | Migration Approach | Phased vMotion migration |

Table 1: Engagement Scope Parameters

Table: Engagement Scope Parameters

Note: Changes to these parameters may require scope adjustment and additional investment.

## 3.2 Out of Scope

These items are not in scope unless added via change control:

• Rack cabinets and PDU procurement (client responsibility)

• Electrical infrastructure upgrades or circuit installation

• Network switch procurement (only configuration included)

• Custom ML model development or algorithm optimization

• Data center facilities management

• Managed services beyond 6-week engagement

## 3.3 Activities

### 3.3.1 Phase 1 – Planning & Procurement (Weeks 1-2)

During this initial phase, the team will finalize specifications and coordinate hardware procurement.

Key activities:

• Review AI workload requirements and validate GPU sizing

• Confirm power, cooling, and rack space availability

• Submit Dell hardware purchase order (workstations, GPUs, storage)

• Prepare data center space and network cabling

• Plan dataset migration from cloud to PowerScale NAS

• Develop implementation timeline and resource schedule

Deliverable: Implementation Plan & Hardware Order Confirmation

### 3.3.2 Phase 2 – Deployment & Configuration (Weeks 3-4)

In this phase, hardware is installed and core infrastructure is configured.

Key activities:

• Dell ProDeploy rack installation and cabling

• Ubuntu 22.04 LTS installation on all workstations

• NVIDIA driver, CUDA 12.2, and cuDNN installation

• PowerScale NAS configuration with NFS shares

• 10GbE network configuration and validation

• ML framework installation (PyTorch, TensorFlow, Jupyter)

• Datadog monitoring agent deployment

Deliverable: Configured AI Infrastructure

### 3.3.3 Phase 3 – Validation & Training (Weeks 5-6)

The solution undergoes performance validation and team training.

Key activities:

• GPU benchmark testing (PyTorch/TensorFlow performance)

• Storage throughput validation (NVMe and PowerScale)

• Sample model training end-to-end testing

• Dataset migration from AWS S3 to PowerScale

• 2-day hands-on training: CUDA optimization and GPU profiling

• Administrator training: Linux, GPU drivers, PowerScale management

• Production go-live with first real-world training workloads

Deliverable: Performance Validation Report & Training Materials

# 4 Deliverables & Timeline

## 4.1 Deliverables

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | Implementation Plan | Document | Week 2 | Client IT Lead |
| 2 | Configured AI Infrastructure | Infrastructure | Week 4 | Technical Lead |
| 3 | Performance Validation Report | Document | Week 6 | Data Science Lead |
| 4 | Training Materials & Runbooks | Document | Week 6 | Client Team |
| 5 | As-Built Documentation | Document | Week 6 | IT Operations |

Table 2: Project Deliverables and Acceptance Criteria

## 4.2 Project Milestones

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 - Hardware Ordered | Dell purchase order submitted | Week 2 |
| M2 - Hardware Delivered | All equipment on-site | Week 3 |
| M3 - Infrastructure Configured | Workstations and storage operational | Week 4 |
| M4 - Validation Complete | Performance benchmarks passed | Week 5 |
| M5 - Training Complete | Team trained and productive | Week 6 |

Table 3: Project Milestones and Timeline

# 5 Roles & Responsibilities

## 5.1 Client Responsibilities

• Provide data center space with adequate power and cooling

• Install rack cabinets and PDUs (if rack-mount configuration)

• Provide 10GbE network infrastructure and VLAN configuration

• Assign technical lead and team for implementation support

• Provide representative training datasets for validation

• Approve hardware specifications and purchase order

• Participate in knowledge transfer and training sessions

## 5.2 Vendor Responsibilities

• Coordinate Dell hardware procurement and delivery

• Install and configure Ubuntu, CUDA, and ML frameworks

• Configure PowerScale NAS with NFS shares and permissions

• Benchmark GPU and storage performance

• Migrate sample datasets from cloud to PowerScale

• Conduct training workshops for users and administrators

• Deliver documentation and operational runbooks

• Provide 6-week implementation support

# 6 Architecture & Design

## 6.1 Solution Architecture

The Dell Precision AI Workstation infrastructure consists of three layers:

Workstation Compute Layer:

• 10x Dell Precision 7960 Tower workstations

• Dual Intel Xeon Gold 6430 processors (64 cores total)

• 512GB DDR5 RAM for large-scale preprocessing

• 4TB NVMe SSD achieving 7000MB/s read performance

• NVIDIA RTX A6000 48GB GPU with 10752 CUDA cores

• Ubuntu 22.04 LTS with CUDA 12.2 and cuDNN

• PyTorch, TensorFlow, Jupyter Lab, VS Code

Shared Storage Layer:

• Dell PowerScale F600 NAS appliance

• 100TB usable capacity for team dataset repository

• NFS/SMB file sharing with user quotas

• 10GbE network connectivity for high-speed access

Monitoring & Management:

• Datadog infrastructure monitoring

• GPU utilization and temperature tracking

• Storage capacity and performance metrics

• Centralized logging for troubleshooting

Figure 1: Architecture Diagram

## 6.2 Network Design

• 10GbE network fabric connecting workstations to PowerScale NAS

• Dedicated storage VLAN for dataset traffic isolation

• 1GbE management network for out-of-band access

• Firewall rules for SSH access and monitoring agents

## 6.3 Data Flow

1. Data scientists access workstations via SSH or remote desktop

2. Training datasets stored centrally on PowerScale NAS (NFS mounts)

3. Dataset loaded from PowerScale to local NVMe for training

4. GPU executes training workload with CUDA acceleration

5. Model checkpoints saved to PowerScale for team sharing

6. Datadog collects GPU metrics and performance telemetry

# 7 Security & Compliance

## 7.1 Access Control

• SSH key-based authentication for workstation access

• LDAP/Active Directory integration for centralized user management

• Sudo access restricted to administrators

• File-level permissions on PowerScale NAS shares

## 7.2 Data Protection

• Encryption at rest: LUKS encryption on workstation NVMe drives

• Encryption in transit: TLS for all network communication

• PowerScale snapshots for data recovery

• No sensitive data transmitted to cloud services

## 7.3 Compliance

• Data sovereignty: All training data remains on-premises

• Audit logging: SSH access logs and file access audit trail

• Patch management: Monthly security updates for Ubuntu and NVIDIA drivers

# 8 Testing & Validation

## 8.1 Performance Testing

• GPU Benchmark: PyTorch and TensorFlow training performance vs specifications

• Storage Throughput: NVMe local storage and PowerScale NAS read/write speeds

• Network Bandwidth: 10GbE connectivity validation between workstations and storage

• End-to-End Training: Sample model training with representative datasets

## 8.2 Acceptance Criteria

• GPU utilization achieves 80%+ during training workloads

• Local NVMe storage achieves 7000MB/s+ read performance

• PowerScale NAS achieves 1GB/s+ aggregate throughput

• All 10 workstations operational with CUDA and ML frameworks

• Sample model training completes successfully

• Users trained and able to execute training workloads independently

# 9 Handover & Support

## 9.1 Knowledge Transfer

• 2-day hands-on training workshop for data scientists

• CUDA optimization techniques

• Distributed training best practices

• GPU profiling and performance tuning

• 1-day administrator training

• Ubuntu and GPU driver management

• PowerScale NAS administration

• Datadog monitoring and alerting

## 9.2 Documentation

• Solution architecture diagram

• Installation and configuration runbooks

• GPU optimization best practices guide

• Troubleshooting procedures

• PowerScale backup and recovery procedures

## 9.3 Support Period

• 6-week hypercare support during initial deployment

• Email and phone support during business hours

• Remote troubleshooting for technical issues

• Escalation to Dell ProSupport for hardware failures

## 9.4 Post-Implementation

After the 6-week engagement:

• Client IT team assumes operational responsibility

• Dell ProSupport Plus provides 24x7 hardware support

• Vendor available for additional consulting as needed

• Recommended quarterly performance reviews

# 10 Investment Summary

## 10.1 Total Investment

| Cost Category | Year 1 List | AWS/Partner Credits | Year 1 Net | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Services | $42,000 | $0 | $42,000 | $0 | $0 | $42,000 |
| Hardware | $219,640 | $0 | $219,640 | $0 | $0 | $219,640 |
| Networking | $38,240 | $0 | $38,240 | $0 | $0 | $38,240 |
| Software | $109,000 | $0 | $109,000 | $27,000 | $27,000 | $163,000 |
| Support & Maintenance | $29,400 | $0 | $29,400 | $29,400 | $29,400 | $88,200 |
| TOTAL INVESTMENT | $876,560 | ($378,000) | $498,560 | ($265,200) | ($265,200) | ($31,840) |

Table 4: Total Investment Summary

Table: Total Investment Summary

## 10.2 Professional Services Breakdown

Professional services cost: $34,000 (after $4,000 Dell ProDeploy credit)

Detailed breakdown available in Level of Effort estimate.

## 10.3 Payment Terms

• 25% upon SOW signature

• 50% upon hardware delivery (Week 3)

• 25% upon final acceptance (Week 6)

# 11 Terms & Conditions

## 11.1 Change Management

Changes to scope, timeline, or deliverables require written change order approved by both parties. Changes may impact timeline and investment.

## 11.2 Assumptions

• Client provides data center space with adequate power and cooling

• Client network infrastructure supports 10GbE connectivity

• Dell hardware delivered within 2-3 weeks of purchase order

• Client team available for implementation coordination and training

• Representative training datasets provided for validation

## 11.3 Client Obligations

• Timely decision-making and approvals

• Access to facilities and systems

• Availability of technical resources

• Hardware purchase order approval within 1 week

## 11.4 Risk Factors

• Hardware delivery delays may impact timeline

• Power or cooling constraints may require facility upgrades

• Network infrastructure limitations may reduce performance

• Dataset migration may take longer for multi-terabyte volumes

## 11.5 Warranty

• Dell ProSupport Plus provides hardware warranty and support

• Professional services guaranteed for 30 days post-acceptance

• Software configuration supported during 6-week hypercare period

# 12 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

eoframework.org