## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Intelligent Document Processing
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test ID | Test Phase | Test Type | Test Category | Test Description | Test Objective | Test Data Requirements | Expected Result | Pass Criteria | Priority | Owner | Dependencies | Duration | Automation Level | Tools Required | Status | Notes
TST-001 | Unit Testing | Functional | API Testing | Test document upload API endpoint | Validate API accepts various document formats | Sample PDF JPEG PNG documents | HTTP 200 response with job ID | Successful upload with valid job ID returned | Critical | EO Delivery Engineer (Platform Implementation) | Document processing API | 2 days | Automated | Pytest AWS SDK | Not Started | Test various file sizes and formats
TST-002 | Unit Testing | Functional | API Testing | Test document processing status API | Validate status tracking throughout processing | Document processing job IDs | Accurate status updates | Status changes from submitted to completed | High | EO Delivery Engineer (Platform Implementation) | TST-001 | 1 day | Automated | Pytest | Not Started | Include error status handling
TST-003 | Unit Testing | Functional | AI/ML Testing | Test Textract OCR accuracy | Validate Amazon Textract text extraction | High-quality PDF samples | >95% text extraction accuracy | OCR accuracy meets threshold | Critical | EO Delivery Engineer (Infrastructure) | Textract integration | 3 days | Semi-automated | AWS Textract SDK | Not Started | Use diverse document samples
TST-004 | Unit Testing | Functional | AI/ML Testing | Test document classification model | Validate custom classification model accuracy | Labeled document samples | >95% classification accuracy | Model correctly identifies document types | Critical | EO Engineer (Data Science) | Trained classification model | 5 days | Automated | SageMaker testing framework | Not Started | Test with holdout validation set
TST-005 | Unit Testing | Functional | AI/ML Testing | Test data extraction accuracy | Validate structured data extraction from documents | Invoice contract form samples | >95% field extraction accuracy | Correctly extract all required fields | Critical | EO Engineer (Data Science) | TST-003 TST-004 | 4 days | Semi-automated | Custom validation scripts | Not Started | Compare against ground truth data
TST-006 | Integration Testing | Functional | System Integration | Test end-to-end document processing | Validate complete processing workflow | Real business documents | Successful processing from upload to results | Complete workflow functions correctly | Critical | EO Engineer (QA) | All unit tests complete | 5 days | Semi-automated | Selenium API testing tools | Not Started | Include error handling scenarios
TST-007 | Integration Testing | Functional | External Integration | Test ERP system integration | Validate data flow to external ERP system | Processed invoice data | Data successfully sent to ERP | ERP receives correctly formatted data | High | EO Delivery Engineer (Platform Implementation) | ERP API access | 3 days | Automated | API testing framework | Not Started | Test data mapping accuracy
TST-008 | Integration Testing | Functional | External Integration | Test notification system integration | Validate email/SMS notifications | Processing completion events | Notifications sent successfully | Users receive timely notifications | Medium | EO Delivery Engineer (Platform Implementation) | SNS configuration | 2 days | Automated | AWS SNS testing | Not Started | Test various notification scenarios
TST-009 | Performance Testing | Non-Functional | Load Testing | Test system performance under normal load | Validate system handles expected document volume | 1000 documents of various types | Process all documents within SLA | <10 seconds average processing time | High | EO Engineer (Performance) | TST-006 | 3 days | Automated | JMeter AWS performance tools | Not Started | Monitor resource utilization
TST-010 | Performance Testing | Non-Functional | Stress Testing | Test system performance under peak load | Validate system scalability limits | 5000+ documents concurrent processing | System maintains performance or gracefully degrades | Auto-scaling functions correctly | High | EO Engineer (Performance) | TST-009 | 2 days | Automated | Load testing tools | Not Started | Test auto-scaling behavior
TST-011 | Performance Testing | Non-Functional | Volume Testing | Test large document processing | Validate handling of large document files | Documents >20MB in size | Successfully process large documents | Large files processed within extended SLA | Medium | EO Engineer (Performance) | TST-009 | 2 days | Manual | Manual document upload | Not Started | Test memory and timeout handling
TST-012 | Security Testing | Security | Authentication Testing | Test API authentication mechanisms | Validate API security controls | Valid and invalid API keys | Unauthorized access blocked | Only valid keys grant access | Critical | EO Engineer (Security) | API implementation | 2 days | Automated | Security testing tools | Not Started | Test various attack vectors
TST-013 | Security Testing | Security | Authorization Testing | Test role-based access controls | Validate user permissions | Different user roles and permissions | Users access only authorized functions | RBAC functions correctly | Critical | EO Engineer (Security) | User management system | 3 days | Manual | Manual role testing | Not Started | Test privilege escalation scenarios
TST-014 | Security Testing | Security | Data Protection Testing | Test data encryption and protection | Validate data security measures | Sensitive document samples | Data encrypted at rest and in transit | All data properly protected | Critical | EO Engineer (Security) | Encryption implementation | 2 days | Manual | Security audit tools | Not Started | Verify encryption standards compliance
TST-015 | Security Testing | Security | Vulnerability Testing | Test system for security vulnerabilities | Identify potential security weaknesses | Penetration testing scenarios | No critical vulnerabilities found | Security scan results acceptable | High | EO Engineer (Security) | TST-012 TST-013 TST-014 | 5 days | Automated | Vulnerability scanners | Not Started | External security audit recommended
TST-016 | User Acceptance Testing | Functional | Business Process Testing | Test invoice processing workflow | Validate business user can process invoices | Real invoice samples | Invoices processed according to business rules | Business workflow functions correctly | Critical | EO Sales Engineer (Business Analysis) | TST-006 | 5 days | Manual | Production-like environment | Not Started | Include business validation scenarios
TST-017 | User Acceptance Testing | Functional | Business Process Testing | Test contract analysis workflow | Validate contract processing meets legal requirements | Real contract samples | Contracts analyzed with required accuracy | Legal requirements satisfied | High | EO Sales Engineer (Business Analysis) | TST-016 | 3 days | Manual | Legal review process | Not Started | Legal team validation required
TST-018 | User Acceptance Testing | Functional | Usability Testing | Test web interface usability | Validate user interface meets usability standards | Various user personas | Users can efficiently complete tasks | High user satisfaction scores | High | EO Engineer (QA) | Web interface development | 3 days | Manual | Usability testing protocols | Not Started | Include accessibility testing
TST-019 | System Testing | Functional | Regression Testing | Test system after changes | Validate changes don't break existing functionality | Previous test scenarios | All existing functionality works | No regression in existing features | High | EO Engineer (QA Lead) | Any system changes | Ongoing | Automated | Regression test suite | Not Started | Run after each major change
TST-020 | System Testing | Non-Functional | Disaster Recovery Testing | Test system recovery procedures | Validate disaster recovery capabilities | Simulated failure scenarios | System recovers within RTO/RPO | DR procedures function correctly | Medium | EO Engineer (Support) | DR implementation | 2 days | Manual | DR testing procedures | Not Started | Test backup and recovery processes
TST-021 | AI/ML Testing | Functional | Model Validation Testing | Test model accuracy with new data | Validate model performance on unseen data | Fresh document samples | Model maintains accuracy standards | Accuracy remains >95% | Critical | EO Engineer (Data Science) | Model deployment | Ongoing | Semi-automated | Model validation framework | Not Started | Continuous model monitoring
TST-022 | AI/ML Testing | Functional | Model Bias Testing | Test model for bias and fairness | Validate model doesn't exhibit bias | Diverse document samples | No significant bias detected | Fair performance across document types | Medium | EO Engineer (Data Science) | TST-021 | 3 days | Manual | Bias detection tools | Not Started | Important for model ethics
TST-023 | AI/ML Testing | Functional | Confidence Score Testing | Test model confidence scoring | Validate confidence scores are accurate | Documents with known difficulty | Confidence scores correlate with accuracy | Appropriate confidence thresholds set | High | EO Engineer (Data Science) | TST-005 | 2 days | Automated | Confidence analysis scripts | Not Started | Critical for human review routing
TST-024 | Compatibility Testing | Non-Functional | Browser Compatibility | Test web interface across browsers | Validate cross-browser functionality | Multiple browser versions | Consistent functionality across browsers | All supported browsers work correctly | Medium | Frontend Developer | Web interface development | 2 days | Manual | Multiple browser testing | Not Started | Test major browser versions
TST-025 | Compatibility Testing | Non-Functional | Mobile Compatibility | Test mobile interface functionality | Validate mobile responsiveness | Various mobile devices | Interface works on mobile devices | Responsive design functions correctly | Medium | Frontend Developer | TST-024 | 2 days | Manual | Mobile device testing | Not Started | Test various screen sizes
TST-026 | Operational Testing | Non-Functional | Monitoring Testing | Test monitoring and alerting systems | Validate monitoring captures system health | Simulated system events | Monitoring alerts function correctly | All alerts trigger appropriately | High | DevOps Engineer | Monitoring implementation | 2 days | Semi-automated | Monitoring tools | Not Started | Test all alerting scenarios
TST-027 | Operational Testing | Non-Functional | Backup Testing | Test backup and restore procedures | Validate data backup functionality | System data samples | Data backed up and restored successfully | Backup/restore procedures work | High | DevOps Engineer | Backup implementation | 1 day | Manual | Backup tools | Not Started | Test restore procedures
TST-028 | Compliance Testing | Compliance | GDPR Compliance | Test GDPR compliance features | Validate data subject rights implementation | Personal data samples | GDPR rights can be exercised | Data protection compliance verified | Critical | Compliance Officer | Privacy implementation | 3 days | Manual | Compliance audit tools | Not Started | Include right to erasure testing
TST-029 | Compliance Testing | Compliance | Audit Trail Testing | Test audit logging functionality | Validate comprehensive audit trail | User activity scenarios | All activities properly logged | Complete audit trail captured | High | Compliance Officer | Logging implementation | 2 days | Automated | Log analysis tools | Not Started | Test log integrity and completeness
TST-030 | Go-Live Testing | Functional | Production Readiness | Test production environment readiness | Validate production system is ready | Production configuration | Production system fully functional | All production criteria met | Critical | QA Lead | Production deployment | 3 days | Manual | Production environment | Not Started | Final validation before go-live