## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Disaster Recovery Web Application
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Task ID | Phase | Task Name | Description | Owner | Start Date | End Date | Duration Days | Predecessor Tasks | Status | Progress % | Priority | Milestone | Dependencies | Deliverables | Delivery_Documents | Effort Hours | Notes
PRJ-001 | Planning | Project Kickoff | Formal project initiation and team alignment | EO Project Manager | [START_DATE] | [START_DATE+1] | 1 |  | Not Started | 0 | Critical | Yes | Stakeholder availability | Project charter and team assignments | 8 | Executive sponsor approval required
PRJ-002 | Planning | Requirements Gathering | Collect and document detailed business and technical requirements | EO Sales Engineer | [START_DATE+1] | [START_DATE+5] | 4 | PRJ-001 | Not Started | 0 | High | No | Stakeholder interviews | Requirements specification document | 32 | Include all stakeholder groups
PRJ-003 | Planning | Solution Architecture Design | Design technical architecture and integration approach | EO Quarterback | [START_DATE+3] | [START_DATE+10] | 7 | PRJ-002 | Not Started | 0 | High | Yes | Technical requirements | Architecture documentation and diagrams | 56 | Review with technical governance board
PRJ-004 | Planning | Infrastructure Planning | Plan and design infrastructure requirements | EO Quarterback | [START_DATE+8] | [START_DATE+15] | 7 | PRJ-003 | Not Started | 0 | High | No | Architecture design | Infrastructure specification and sizing | 40 | Include capacity planning and scaling
PRJ-005 | Planning | Risk Assessment | Identify and assess project risks with mitigation strategies | EO Engineer | [START_DATE+10] | [START_DATE+12] | 2 | PRJ-003 | Not Started | 0 | Medium | No | Project scope | Risk register and mitigation plans | 16 | Regular risk review meetings scheduled
PRJ-006 | Design | Detailed Design | Create detailed technical specifications and design documents | EO Quarterback | [START_DATE+15] | [START_DATE+25] | 10 | PRJ-004 | Not Started | 0 | High | Yes | Architecture approval | Detailed technical specifications | 80 | Include interface specifications
PRJ-007 | Design | Security Design | Design security controls and compliance framework | EO Quarterback | [START_DATE+18] | [START_DATE+23] | 5 | PRJ-003 | Not Started | 0 | High | No | Architecture design | Security design document | 40 | Compliance review required
PRJ-008 | Design | Integration Design | Design integration points and data flow | EO Engineer | [START_DATE+20] | [START_DATE+27] | 7 | PRJ-006 | Not Started | 0 | High | No | Technical specifications | Integration specification document | 56 | API documentation and testing approach
PRJ-009 | Build | Environment Setup | Provision and configure development and test environments | EO Engineer | [START_DATE+25] | [START_DATE+32] | 7 | PRJ-004 | Not Started | 0 | High | Yes | Infrastructure approval | Development and test environments | 56 | Automated provisioning preferred
PRJ-010 | Build | Core Development | Develop core application functionality and features | EO Engineer | [START_DATE+30] | [START_DATE+50] | 20 | PRJ-006 | Not Started | 0 | Critical | No | Environment setup | Core application components | 320 | Follow coding standards and best practices
PRJ-011 | Build | Integration Development | Develop integration components and APIs | EO Engineer | [START_DATE+35] | [START_DATE+47] | 12 | PRJ-008 | Not Started | 0 | High | No | Core development started | Integration components and APIs | 96 | Include error handling and monitoring
PRJ-012 | Build | Security Implementation | Implement security controls and authentication | EO Engineer | [START_DATE+38] | [START_DATE+48] | 10 | PRJ-007 | Not Started | 0 | High | No | Security design approval | Security implementation | 80 | Security testing throughout development
PRJ-013 | Test | Unit Testing | Execute comprehensive unit testing of all components | EO Engineer | [START_DATE+40] | [START_DATE+52] | 12 | PRJ-010 | Not Started | 0 | High | No | Core development | Unit test results and coverage reports | 96 | Achieve minimum 80% code coverage
PRJ-014 | Test | Integration Testing | Test integration points and data flow | EO Engineer | [START_DATE+50] | [START_DATE+60] | 10 | PRJ-011 | Not Started | 0 | High | No | Integration development | Integration test results | 80 | Include negative testing scenarios
PRJ-015 | Test | System Testing | End-to-end system testing and validation | EO Engineer | [START_DATE+55] | [START_DATE+70] | 15 | PRJ-013 | Not Started | 0 | Critical | Yes | Unit testing completion | System test results and defect reports | 120 | Include performance and load testing
PRJ-016 | Test | Security Testing | Comprehensive security testing and vulnerability assessment | EO Engineer | [START_DATE+60] | [START_DATE+67] | 7 | PRJ-012 | Not Started | 0 | High | No | Security implementation | Security test results and remediation plan | 56 | External security audit may be required
PRJ-017 | Test | User Acceptance Testing | Business user testing and sign-off | EO Sales Engineer | [START_DATE+70] | [START_DATE+80] | 10 | PRJ-015 | Not Started | 0 | Critical | Yes | System testing completion | UAT results and business sign-off | 40 | Include training for test users
PRJ-018 | Deploy | Production Environment Setup | Provision and configure production infrastructure | EO Engineer | [START_DATE+75] | [START_DATE+82] | 7 | PRJ-009 | Not Started | 0 | High | No | Environment specifications | Production environment ready | 56 | Include monitoring and alerting setup
PRJ-019 | Deploy | Pre-Deployment Testing | Final testing in production-like environment | EO Engineer | [START_DATE+80] | [START_DATE+85] | 5 | PRJ-017 | Not Started | 0 | High | No | UAT completion | Pre-deployment test results | 40 | Smoke testing and final validation
PRJ-020 | Deploy | Production Deployment | Deploy solution to production environment | EO Engineer | [START_DATE+85] | [START_DATE+87] | 2 | PRJ-018 | Not Started | 0 | Critical | Yes | Production environment ready | Deployed production system | 16 | Follow change management procedures
PRJ-021 | Deploy | Post-Deployment Validation | Validate production deployment and functionality | EO Engineer | [START_DATE+87] | [START_DATE+89] | 2 | PRJ-020 | Not Started | 0 | High | No | Production deployment | Production validation report | 16 | Include performance monitoring validation
PRJ-022 | Deploy | User Training Delivery | Deliver training to end users and administrators | EO Engineer | [START_DATE+75] | [START_DATE+90] | 15 | PRJ-017 | Not Started | 0 | High | No | UAT completion | Training completion certificates | 60 | Include hands-on practical sessions
PRJ-023 | Deploy | Go-Live Support | Provide intensive support during initial production use | EO Engineer | [START_DATE+89] | [START_DATE+96] | 7 | PRJ-021 | Not Started | 0 | High | No | Production validation | Go-live support reports | 56 | 24/7 support for first week
PRJ-024 | Closure | Hypercare Period | Extended support and monitoring during stabilization | EO Engineer | [START_DATE+96] | [START_DATE+126] | 30 | PRJ-023 | Not Started | 0 | Medium | No | Go-live completion | Hypercare completion report | 120 | Monitor system stability and user adoption
PRJ-025 | Closure | Project Documentation | Finalize all project documentation and handover | EO Project Manager | [START_DATE+90] | [START_DATE+100] | 10 | PRJ-022 | Not Started | 0 | Medium | No | All deliverables complete | Complete project documentation package | 40 | Include lessons learned and recommendations
PRJ-026 | Closure | Project Closure | Formal project closure and team release | EO Project Manager | [START_DATE+126] | [START_DATE+128] | 2 | PRJ-024 | Not Started | 0 | Medium | Yes | Hypercare completion | Project closure report and sign-off | 8 | Celebrate project success with team