## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Onpremise To Cloud Migration
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Status Report | Executive Sponsors | High-level migration status and key decisions | Weekly | Executive Dashboard | EO Project Manager | Email distribution list |  | "Migration health, wave progress, risks, budget status" | Executive Sponsor and CTO | Executive | Report delivered on time and decisions made | Active | [DATE] | Executive summary with migration KPIs and cost metrics
COMM-002 | Migration Steering Committee | Project Steering Committee | Strategic migration direction and issue resolution | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | "Migration strategy, major risks, budget, timeline adjustments" | Executive Sponsor and IT Leadership | Strategic | Meeting attendance >80% and decisions documented | Active | [DATE] | Decision-making authority for migration scope and priorities
COMM-003 | Migration Team Standup | Core Migration Team | Daily coordination and impediment removal | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | "Wave progress, blockers, daily migration tasks" | Migration Engineers and Cloud Architects | Operational | Daily attendance >90% and blockers resolved | Active | [DATE] | Focus on migration dependencies and coordination
COMM-004 | Cloud Architecture Review | Technical Stakeholders | AWS architecture design review and approval | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Architecture decisions, AWS service selection, security design" | Cloud Architect and AWS Specialists | Technical | Design decisions made and AWS best practices followed | Active | [DATE] | Include AWS Well-Architected Framework reviews
COMM-005 | Migration Risk Review | Risk Management Team | Migration risk assessment and mitigation planning | Bi-weekly | Risk Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Migration risks, dependency issues, rollback planning" | Migration PM and Risk Committee | Management | Risk register updated and mitigations on track | Active | [DATE] | Focus on migration-specific risks and dependencies
COMM-006 | Business Stakeholder Update | Business Users | Migration impact and readiness communication | Weekly | Business Meeting | EO Sales Engineer | Meeting invitation | 60 minutes | "Migration schedule, application changes, user impact" | Business Stakeholders and App Owners | Business | User awareness and readiness for migration waves | Active | [DATE] | Include application-specific migration timelines
COMM-007 | AWS Environment Review | Cloud Operations Team | AWS infrastructure progress and configuration | Bi-weekly | Cloud Review Meeting | EO Quarterback | Video conference | 75 minutes | "Landing zone progress, security config, monitoring setup" | Cloud Ops Team and AWS TAM | Technical | AWS environments ready and security validated | Active | [DATE] | Include AWS service configurations and cost optimization
COMM-008 | Migration Wave Coordination | Wave Teams | Individual wave planning and execution coordination | Daily (during waves) | Wave Standup | EO Engineer | Video conference | 30 minutes | "Wave status, application dependencies, cutover planning" | Wave Team Members and App Owners | Wave | Wave milestones met and applications migrated successfully | Active | [DATE] | Intensive coordination during active migration waves
COMM-009 | Data Migration Update | Data Team | Database and data migration progress | Weekly | Data Call | EO Engineer | Conference call | 45 minutes | "Data sync status, validation results, cutover readiness" | Data Engineers and DBA Team | Technical | Data migration completed with zero data loss | Active | [DATE] | Include data validation and synchronization metrics
COMM-010 | Security and Compliance Review | Security Team | Cloud security compliance and risk assessment | Bi-weekly | Security Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Security assessments, compliance validation, vulnerability management" | Security Team and Compliance Officer | Security | Security requirements met and compliance validated | Active | [DATE] | Include AWS security services and compliance frameworks
COMM-011 | Network Connectivity Update | Network Team | Hybrid network connectivity and performance | Weekly | Network Call | EO Engineer | Conference call | 30 minutes | "Connectivity status, bandwidth utilization, routing optimization" | Network Team and Cloud Engineers | Technical | Network connectivity stable and performance optimized | Active | [DATE] | Include AWS Direct Connect and VPN performance
COMM-012 | Change Control Board | Change Control Board | Migration change request review and approval | As Needed | Change Meeting | EO Engineer | Meeting invitation | 60 minutes | "Migration changes, impact assessment, approval decisions" | Change Control Board Members | Governance | Migration changes processed within SLA | Active | [DATE] | Follow migration-specific change management process
COMM-013 | Training and Enablement | Training Stakeholders | Cloud skills training and readiness | Bi-weekly | Training Call | EO Engineer | Conference call | 30 minutes | "Training progress, cloud certification, knowledge transfer" | Training Team and Operations Managers | Operational | Team cloud readiness and certification targets met | Active | [DATE] | Include AWS training and certification progress
COMM-014 | Vendor Coordination | AWS and Vendor Partners | AWS TAM and vendor integration coordination | Weekly | Vendor Call | EO Engineer | Conference call | 45 minutes | "AWS support, vendor deliverables, integration progress" | AWS TAM and Vendor Representatives | Vendor | Vendor commitments met and AWS support effective | Active | [DATE] | Track AWS Professional Services and partner SLAs
COMM-015 | Testing and Validation | Quality Assurance Team | Migration testing progress and quality metrics | Weekly | QA Meeting | EO Engineer | Meeting invitation | 45 minutes | "Test execution, performance validation, rollback testing" | QA Team and Performance Engineers | Quality | Migration quality gates met and performance validated | Active | [DATE] | Include migration-specific testing and validation results
COMM-016 | Cost Optimization Review | FinOps Team | AWS cost monitoring and optimization | Weekly | Cost Review | EO Quarterback | Meeting invitation | 30 minutes | "AWS cost analysis, right-sizing, reserved instance planning" | FinOps Team and Cloud Architects | Financial | AWS costs optimized and within budget targets | Active | [DATE] | Include AWS cost explorer and optimization recommendations
COMM-017 | Application Readiness | Application Teams | Application migration readiness and validation | Daily (pre-wave) | App Readiness Call | EO Engineer | Video conference | 30 minutes | "App dependencies, data cutover, user acceptance testing" | App Owners and Business Users | Application | Applications ready for migration and validated | Active | [DATE] | Critical coordination before each application migration
COMM-018 | Go-Live Coordination | Go-Live Team | Migration wave go-live planning and execution | Hourly (during cutover) | Go-Live War Room | EO Engineer | War room coordination | 15 minutes | "Cutover status, rollback decisions, issue escalation" | All Wave Team Members | Critical | Successful cutover with minimal downtime | Planned | [DATE] | Intensive coordination during production cutover
COMM-019 | Post-Migration Review | Migration Team | Post-migration review and optimization | Weekly (4 weeks post) | Review Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Migration performance, optimization opportunities, lessons learned" | Core Migration Team and Operations | Review | Migration benefits realized and optimizations identified | Planned | [DATE] | Include cloud cost analysis and performance optimization
COMM-020 | Issue Escalation | Incident Response Team | Critical migration issue communication and resolution | As Needed | Emergency Call | EO Sales Engineer | Emergency notification | Variable | "Issue description, business impact, resolution actions" | Incident Response Team and Management | Emergency | Migration issues resolved within SLA | Active | [DATE] | Follow migration incident management procedures
COMM-021 | AWS Support Coordination | AWS Technical Support | AWS technical support and guidance coordination | As Needed | AWS Support Call | EO Quarterback | AWS support channels | Variable | "Technical guidance, service limits, architecture validation" | AWS TAM and Support Engineers | AWS | AWS support responsive and technical guidance effective | Active | [DATE] | Leverage AWS Technical Account Manager and support
COMM-022 | Business Continuity Update | Business Continuity Team | Business impact assessment and continuity planning | Weekly | BC Meeting | EO Sales Engineer | Meeting invitation | 45 minutes | "Business impact, continuity plans, disaster recovery testing" | BC Team and Business Leaders | Business | Business continuity maintained during migration | Active | [DATE] | Include disaster recovery testing and business impact analysis
COMM-023 | Cloud Operations Handover | Operations Teams | Migration to operations transition planning | Bi-weekly | Handover Meeting | EO Engineer | Meeting invitation | 60 minutes | "Operations readiness, runbook review, support transition" | Cloud Ops and Migration Teams | Transition | Smooth transition to operations with documented procedures | Planned | [DATE] | Include cloud operations training and knowledge transfer
COMM-024 | Stakeholder All-Hands | All Migration Stakeholders | General migration updates and milestone communication | Monthly | All-Hands Meeting | EO Project Manager | Town hall meeting | 45 minutes | "Migration progress, upcoming waves, team recognition" | All Migration Stakeholders | Informational | Stakeholder engagement and migration awareness maintained | Active | [DATE] | Include migration achievements and cloud benefits realization