# Statement Of Work

AWS Cloud Migration - On-Premise to Cloud

| Client Name: | [Client Name] |
| --- | --- |
| Date: | [Month DD, YYYY] |
| Consulting Company: | EO Framework Consulting |
| Submitted By: | [Vendor Contact Name] info@eoframework.com |
| Opportunity No: | OPP-MIGRATION-2025-0001 |
| Version | 1.0 |

# Table of Contents

Table of Contents	2

List of Figures	2

1 Section Header 1	3

1.1 Section Sub-Header 1	3

1.1.1 Section Sub-Header 2	3

1.2 Section Sub-Header 5	3

2 Section Header 2 - Table Content	3

2.1 Table Section 1	3

2.2 Table Section 2	3

3 Section Header 3 - Image Section	4

3.1 Image Content	4

4 Section Header 4	4

4.1 Additional Sub-Section	5

5 Sign-Off	5

# List of Tables

Table 1: Project Deliverables and Acceptance Criteria	3
Table 2: Project Milestones and Timeline	4
Table 3: Roles and Responsibilities (RACI Matrix)	5
Table 4: Tooling Overview	6
Table 5: Pricing And Investment Summary	7

# List of Figures

Figure 1: Solution Architecture Diagram	11

## 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for migration of [#] workloads from [on-prem/data center/cloud provider] to Amazon Web Services (AWS).

## 2 Background & Objectives

### 2.1 Background

Client currently hosts [#] applications on [VMware/Hyper-V/Physical servers] across [#] environments. Challenges include:

• [e.g., scaling]

• [e.g., end-of-life hardware]

• [e.g., data center contract expiration]

### 2.2 Objectives

• Migrate [#] workloads to AWS using proven tooling such as AWS MGN and DMS.

• Improve security posture using VPC segmentation, IAM controls, GuardDuty, etc.

• Reduce TCO by leveraging managed services (e.g., RDS, ECS Fargate).

• Enable DR across AZs or regions where applicable.

### 2.3 Success Metrics

• Zero high-severity issues during cutover

• App latency < [X ms] post-migration

• 99.9% uptime during the stabilization period

• 20–35% cost reduction vs. on-prem within 12 months

## 3 Scope of Work

### 3.1 In Scope

• Workload discovery & dependency analysis (via AWS Application Discovery Service)

• AWS Landing Zone deployment (Control Tower or Terraform)

• VPC, subnet, routing, and shared services setup

• Workload migration using AWS MGN / CloudEndure

• RDS migration (if part of replatform strategy)

• Cutover, DNS updates, and validation

• Knowledge transfer and documentation

### 3.2 Activities

#### 3.2.1 Phase 1 – Discovery & Assessment

During this initial phase, the Vendor will perform a comprehensive assessment of the Client’s infrastructure and application landscape. This includes analyzing existing workloads, identifying dependencies, and determining the most appropriate migration strategy for each workload.

Key activities:

• Comprehensive infrastructure discovery and inventory

• Application portfolio analysis and dependency mapping

• Migration readiness assessment using AWS MAP framework

• AWS architecture design and landing zone planning

• Migration wave planning and prioritization

• Cost estimation and right-sizing recommendations

This phase concludes with a Migration Assessment Report that outlines the proposed plan, scope, risks, and timeline.

#### 3.2.2 Phase 2 – Landing Zone & Infrastructure Deployment

In this phase, the foundational AWS infrastructure is provisioned and configured based on AWS best practices. This includes account structure, network setup, security controls, monitoring, and access management.

Key activities:

• AWS Landing Zone implementation with account provisioning

• Network connectivity setup using VPN or Direct Connect

• Centralized logging and monitoring via CloudWatch, CloudTrail, and security services

• IAM roles, SSO, MFA policies based on least-privilege model

• Baseline security configuration using AWS Config, GuardDuty, and SCPs

• Implementation of automated backup strategies and disaster recovery setup

By the end of this phase, the Client will have a secure, production-ready AWS environment for hosting migrated workloads.

#### 3.2.3 Phase 3 – Migration Execution (in waves)

Migration of workloads will occur in well-defined waves based on business priority and workload complexity. Each wave follows a repeatable factory approach with automated processes for consistency and risk reduction.

Key activities:

• Migration factory setup with CI/CD and automation tooling

• Database migrations using AWS DMS or native tools (e.g., RMAN, SQL)

• Application migration via rehost, replatform, or refactor strategies

• Incremental or real-time data sync between source and target systems

• DNS updates, endpoint reconfiguration

• Resource right-sizing and performance optimization

After each wave, the Vendor will coordinate validation and sign-off with the Client before proceeding.

#### 3.2.4 Phase 4 – Testing & Cutover

In the Testing and Cutover phase, migrated workloads undergo thorough functional, performance, and failover validation to ensure they meet required SLAs and compliance standards. Test cases and scripts will be executed based on Client-defined acceptance criteria.

Key activities:

• Smoke testing and sanity checks for each migrated workload

• Performance benchmarking vs. on-premise baselines

• Failover and resiliency testing (Multi-AZ, DR)

• Final synchronization of data (if using DMS)

• DNS cutover, user acceptance testing (UAT), and go-live readiness review

Cutover will be coordinated with all relevant stakeholders and executed during an approved maintenance window, with well-documented rollback procedures in place.

#### 3.2.5 Phase 5 – Handover & Post-Migration Support

Following successful migration and cutover, the focus shifts to ensuring operational continuity and knowledge transfer. The Vendor will provide a period of hypercare support and equip the Client’s team with the documentation, tools, and processes needed for ongoing maintenance and optimization.

Activities include:

• Delivery of as-built documentation (including architecture diagrams, IAM permissions, monitoring setup, etc.)

• Runbook and SOPs for day-to-day operations

• Live or recorded knowledge transfer sessions for Ops and Application teams

• Cost optimization recommendations (based on AWS Trusted Advisor and Cost Explorer)

• Optional transition to a managed services model for 24/7 support, if contracted

## 4 Out of Scope

### 4.1 Exclusions

These items are not in scope unless added via change control:

• Application refactoring (code-level changes)

• On-prem hardware recycling or disposal

• Managed services post-migration (unless separately contracted)

• Training for non-IT end users

## 5 Deliverables

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | Migration Assessment Report | Document | [Date] | [Client Lead] |
| 2 | AWS Landing Zone Source Code | IaC/Code | [Date] | [AWS Architect] |
| 3 | Migration Runbook & Cutover Plan | Document | [Date] | [Ops Lead] |
| 4 | As-Built Diagrams & Documentation | Document | [Date] | [Client Lead] |
| 5 | Knowledge Transfer Sessions | Live/Recorded | [Date] | [Client Team] |

Table 1: Project Deliverables and Acceptance Criteria

## 6 Project Plan & Timeline

### 6.1 Milestones

| Milestone | Target Date |
| --- | --- |
| M1: Assessment Complete | [Date] |
| M2: Landing Zone Ready | [Date] |
| M3: Wave 1 App Migration | [Date] |
| Go-Live | [Date] |
| Hypercare End | [Date] |

Table 2: Project Milestones and Timeline

## 7 Roles & Responsibilities (RACI)

| Task/Role | Vendor PM | Vendor Arch | Vendor DevOps | Client IT | Client Sec | AWS SA |
| --- | --- | --- | --- | --- | --- | --- |
| Discovery & Dependency Mapping | A | R | R | C | I | I |
| AWS Account & Landing Zone | C | A | R | I | I | C |
| Network Setup (VPC, Routing) | C | A | R | C | C | C |
| Migration Wave Design | A | R | C | R | C | I |
| Database Migration | C | R | R | C | I | I |
| Application Cutover Execution | R | R | R | A | C | I |
| IAM & Security Configuration | C | C | R | I | A | C |
| Monitoring Configuration (CW, X-Ray) | C | R | R | C | I | I |
| Hypercare Post-Migration Support | A | R | R | C | I | I |
| Knowledge Transfer | R | R | C | A | I | I |

Table 3: Roles and Responsibilities (RACI Matrix)

Legend:  
R = Responsible | A = Accountable | C = Consulted | I = Informed

## 8 AWS Architecture & Accounts

### 8.1 Architecture Overview

The proposed AWS architecture is designed to provide a secure, scalable, and compliant foundation for current and future workloads. The architecture aligns with AWS best practices, including the Well-Architected Framework, and uses automation where possible to streamline deployment, security, and ongoing operations.

Figure 1: Solution Architecture Diagram

### 8.2 Architecture Type – Multi-account Landing Zone

The deployment will follow a multi-account architecture using an AWS Landing Zone model. This approach enforces clear separation of environments (e.g., Dev, QA, Prod, Shared Services) and allows for granular SC (Service Control Policies), billing segmentation, and enhanced security boundary enforcement.

Landing zone setup includes:

• AWS Organizations with consolidated billing and root management account

• Standardized baseline policies (SCPs, Guardrails)

• Account vending and configuration via AWS Control Tower or custom Terraform modules

This design enables future scaling with centralized governance, improving isolation and reducing blast radius.

### 8.3 Application Hosting

Depending on the workload pattern and migration strategy, applications will be hosted using best-fit AWS compute options:

• EC2 (Elastic Compute Cloud) for rehosted VMs or applications requiring custom OS-level control

• ECS or Fargate for containerized workloads

• Lambda for serverless or event-driven workloads

All compute services will be deployed in private subnets for optimal security and managed using infrastructure-as-code (IaC).

### 8.4 Networking

The networking architecture will be implemented using AWS Virtual Private Cloud (VPC) components, adhering to a hub-and-spoke or shared VPC design:

• VPCs created per environment or workload type

• Subnets segmented by tier (web, app, data) across multiple Availability Zones (AZs)

• Routing configured via route tables and NAT gateways

• Transit Gateway (TGW) or VPC peering used for inter-VPC communication

• Hybrid connectivity via AWS VPN or Direct Connect (DX), enabling integration with on-prem systems

### 8.5 Observability

A centralized observability framework ensures operational continuity and rapid incident response:

• CloudWatch Logs and Metrics

• X-Ray for application tracing

• GuardDuty for threat detection

• Logs will be aggregated in a central logging account using AWS Organizations practices

### 8.6 Backup & Disaster Recovery

All critical data and workloads will be protected through:

• Automated backups via AWS Backup

• Cross-AZ replication for high availability

• Optional cross-region replication for disaster recovery (DR) scenarios

• DR strategies aligned to Client’s defined RTO/RPO goals

## 9 Assumptions

### 9.1 General Assumptions

• Client provides timely access to applications, SMEs, and target systems.

• IAM roles are provisioned with appropriate permissions before migration waves start.

• On-prem network connectivity will be handled via DX or VPN.

• All required AWS accounts are permitted for project use.

## 10 Dependencies

### 10.1 Project Dependencies

• Approval for AWS Organizations setup

• Third-party application vendor support (if required for migration)

• DNS access and domain control during cutover

• Required firewall/NAT rules established prior to migration

## 11 AWS Security, Compliance & Governance

The migration and target AWS environment will be architected and validated to meet the Client’s security, compliance, and governance requirements. Vendor will adhere to AWS's Shared Responsibility Model and industry-standard security frameworks during implementation.

### 11.1 Identity & Access Management

• IAM roles designed using least-privilege access

• Role-based access control (RBAC) aligned with Client’s internal teams

• Optional identity federation integration (e.g. Azure AD, Okta)

### 11.2 Monitoring & Threat Detection

• GuardDuty enabled across accounts for real-time threat detection

• AWS Config and CloudTrail enabled for audit logging and change detection

• Optional integration with SIEM tools like Splunk, Datadog, or ELK

### 11.3 Compliance & Auditing

• Policies configured for adherence to standards such as SOC2, ISO27001, HIPAA, etc.

• Continuous assessment using Security Hub and Trusted Advisor

• Optional support for GovCloud for regulatory compliance

### 11.4 Encryption & Key Management

• KMS-managed keys for in-transit and at-rest encryption

• Optional BYOK or CloudHSM deployment

• TLS enforcement for all data channels

### 11.5 Governance

• Use of Service Control Policies (SCPs) to enforce mandatory security posture

• AWS tagging strategy applied for cost allocation, ownership, and automation

• IaC policy enforcement using tools such as Conftest or AWS CodePipeline

## 12 Environments & Access

### 12.1 Environments

• Dev, QA, Stage, Prod

### 12.2 Access Policies

• MFA required

• SSO federation preferred

• No direct SSH — use SSM Session Manager

## 13 Testing & Validation

Comprehensive testing and validation will take place throughout the migration lifecycle to ensure functionality, performance, security, and resilience of all workloads on AWS.

### 13.1 Functional Validation

• End-to-end application validation via UI, API, or batch-level testing

• Validation against business workflows and user stories

### 13.2 Performance & Load Testing

• Benchmark comparison between on-prem and AWS target states

• Stress testing using tools like JMeter or Locust

### 13.3 Security Testing

• Validation of IAM policies, encryption, and compliance requirements

• Optional penetration testing and vulnerability scanning

### 13.4 Disaster Recovery & Resilience Tests

• Failover testing (Multi-AZ, Multi-region if applicable)

• RTO/RPO validation

### 13.5 User Acceptance Testing (UAT)

• Performed in coordination with Client stakeholders

• Test data and environment setup managed by Vendor

### 13.6 Go-Live Readiness

A Go-Live Readiness Checklist will be delivered including:

• Security and compliance sign-offs

• Functional benchmark validation

• Data integrity checks

• Issue log closure

## 14 Migration Strategy & Tools

The migration approach will follow AWS’s “7 Rs” migration pattern framework, selecting the appropriate strategy (Rehost, Replatform, Repurchase, Refactor, Retire, Retain) for each workload based on business and technical drivers.

### 14.1 Example Migration Patterns

• Rehost (Lift & Shift) using AWS MGN

• Replatform to AWS RDS or containers

• Refactor via modularization to AWS Lambda or ECS

### 14.2 Tooling Overview

| Category | AWS Tools | Third-party Options |
| --- | --- | --- |
| Server Migration | AWS MGN, CloudEndure | RackWare, Zerto |
| Database Migration | AWS DMS, SCT | Azure Database Migration Tool |
| File/Data Migration | DataSync, Snowball, S3 | Rsync, Robocopy |
| IaC | CloudFormation, CDK | Terraform, Pulumi |
| CI/CD Automation | CodePipeline, CodeBuild | Jenkins, GitHub Actions |
| Monitoring | CloudWatch, X-Ray | Datadog, New Relic |

Table 4: Tooling Overview

## 15 Data Migration Plan

### 15.1 Data Strategy

• AWS DMS with CDC (Change Data Capture) for minimal downtime

• Validation through record counts and checksum comparison

### 15.2 Security & Compliance

• KMS encryption enabled in-transit and at-rest

• Data classification aligned with Client’s internal policies

## 16 Cutover Plan & Go-Live Readiness

### 16.1 Cutover Checklist

• DNS switch sequencing

• Disable legacy database writes

• Application and endpoint reconfiguration

• Health check monitoring

### 16.2 Rollback Strategy

• Reverse DNS

• Re-enable legacy data writes

• Rollback to earlier snapshot or AMI

## 17 Handover & Managed Services Transition

### 17.1 Handover Artifacts

• As-Built documentation

• Cloud cost estimation & optimization recommendations

• IAM and account governance model

• Monitoring & alert setup reference

### 17.2 Knowledge Transfer

• [X] live sessions

• Recorded materials hosted in shared portal

# 1 Pricing & Investment Summary

| Cost Category | Year 1 | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- |
| Professional Services | $364,000 | $0 | $0 | $364,000 |
| Infrastructure & Materials | $375,532 | $25,282 | $25,282 | $426,097 |
| TOTAL SOLUTION INVESTMENT | $739,532 | $25,282 | $25,282 | $790,097 |

Table 5: Pricing And Investment Summary

## 1.1 Cost Components

Professional Services: Labor costs for migration assessment, wave planning, landing zone setup, application migration, database migration, testing, cutover, and knowledge transfer. Detailed breakdown provided in level-of-effort-estimate.xlsx.

Infrastructure & Materials: AWS cloud services (EC2, RDS, S3, VPN, ALB, CloudFront, ElastiCache), software licenses (Datadog, PagerDuty, Terraform Cloud), and support contracts. Detailed breakdown including AWS service consumption estimates, software licensing, and support contracts is provided in the accompanying Cost Breakdown workbook (cost-breakdown.xlsx).

## 1.2 Payment Terms

### 1.2.1 Pricing Model

• Fixed price or Time & Materials (T&M)

• Milestone-based payments per Deliverables table

### 1.2.2 Payment Schedule

• 25% upon SOW execution and project kickoff

• 30% upon completion of Assessment and Wave 1 migration

• 30% upon completion of Wave 2-3 migrations

• 15% upon successful cutover and hypercare completion

## 1.3 Invoicing & Expenses

### 1.3.1 Invoicing

• Monthly invoicing

• Net 30 payment terms

### 1.3.2 Expenses

• Reimbursable at cost with prior approval

## 1.4 Terms & Conditions

All migration services will be delivered in accordance with the executed Master Services Agreement (MSA) or equivalent contractual document between Vendor and Client.

### 1.4.1 Scope Changes

• Change Requests required for any scope, schedule, or cost adjustments

### 1.4.2 Intellectual Property

• Client retains all ownership of migrated assets, applications, and cloud configs

• Vendor retains proprietary scripts and accelerators unless otherwise agreed

### 1.4.3 Service Levels

• Deliverables based on best effort unless otherwise specified in SLAs

• Hypercare period of [X] weeks included with option to extend via managed services

### 1.4.4 Liability

• Liability caps as agreed in MSA

• Excludes confidentiality or IP infringement breach

### 1.4.5 Confidentiality

• All exchanged artifacts under NDA protection

### 1.4.6 Termination

• Mutually terminable per MSA terms, subject to payment for completed work

### 1.4.7 Governing Law

• Agreement governed under the laws of [State/Region]

## 1.5 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Signature: ____________________ | Signature: ____________________ |
| Name: ____________________ | Name: ____________________ |
| Title: ____________________ | Title: ____________________ |
| Date: ____________________ | Date: ____________________ |

This Statement of Work constitutes the complete agreement between the parties for the cloud migration services described herein and supersedes all prior negotiations, representations, or agreements relating to the subject matter.

_______________________________________________

www.eoframework.org