## Cover
[DOCUMENT TITLE]
Level of Effort
CISCO - Ai - Network Analytics
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Primary Features/Capabilities | DNA Center for 200 devices | DNA Center for 200 devices | DNA Center for 500 devices | DNA Center for 1000+ devices | Network automation and assurance
Solution Scope | Customization Level | Standard DNA Center deployment | Standard DNA Center deployment | Custom policy templates and workflows | Extensive custom integrations and automation | Configuration vs custom development
Integration | External System Integrations | 2 systems (AD + ITSM) | 2 systems (AD + ITSM) | 4 systems (AD ITSM IPAM monitoring) | 6+ systems including SIEM and orchestration | ServiceNow NetBox integration
Integration | Data Sources | Network devices only | Network devices only | Network + IPAM + monitoring data | Network + IPAM + monitoring + external CMDBs | Device discovery and telemetry
User Base | Total Users | 10 network administrators | 10 network administrators | 25 network team members | 50+ distributed team members | DNA Center users and operators
User Base | User Roles | 2 roles (admin + viewer) | 2 roles (admin + viewer) | 4 roles with delegation | 6+ roles with complex RBAC | Role-based access control
Data Volume | Data Processing Volume | 200 devices telemetry | 200 devices telemetry | 500 devices high-frequency telemetry | 1000+ devices with NetFlow | Network assurance and analytics data
Data Volume | Data Storage Requirements | 500 GB (90-day retention) | 500 GB (90-day retention) | 2 TB (1-year retention) | 5+ TB (multi-year retention) | Telemetry logs and analytics data
Technical Environment | Deployment Regions | Single data center | Single data center | 2 data centers with HA | Multi-site with geographic redundancy | DNA Center deployment architecture
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | DNA Center uptime SLA
Technical Environment | Infrastructure Complexity | Basic campus network | Basic campus network | Campus + branch + data center | Complex multi-domain fabric architecture | Network topology complexity
Security & Compliance | Security Requirements | Basic 802.1X and encryption | Basic 802.1X and encryption | TrustSec segmentation + ISE | Advanced TrustSec + compliance automation | Network security and access control
Security & Compliance | Compliance Frameworks | Basic logging | Basic logging | PCI DSS or HIPAA | Multiple regulatory frameworks | Compliance automation requirements
Performance | Performance Requirements | Standard telemetry | Standard telemetry | Enhanced analytics and reporting | Real-time analytics with AI insights | Network assurance performance
Environment | Deployment Environments | Production only | Production only | Lab + production | Lab + staging + production + DR | Testing and validation environments

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Network Assessment, Device Inventory, Requirements Gathering, Integration Analysis)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Architecture Design, Policy Framework, Migration Planning, Training Plan)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (DNA Center Deployment, Device Onboarding, Policy Configuration, Integration Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Lab Testing, Pilot Validation, Policy Testing, Failover Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Device Migration, Policy Rollout, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Operations Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline, Operational Handoff)
Management | MANAGEMENT_MX | 0.25 | Project management and technical leadership (25% of total engineering effort)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Estimated Hours | Rate | Cost Estimate | Dependencies | Risk Level | Notes
Discovery | Network Assessment | Assess current network infrastructure and Cisco device inventory |  | 40 | 200 |  |  | Medium | 200 devices analysis and capacity planning
Discovery | DNA Center Requirements | Gather DNA Center requirements and use case definition |  | 32 | 200 |  |  | Medium | Policy framework and automation goals
Discovery | Integration Analysis | Analyze integration requirements for AD ITSM and IPAM |  | 24 | 225 |  |  | Medium | ServiceNow and NetBox integration planning
Discovery | Application Inventory | Identify critical applications for monitoring and SLA policies |  | 16 | 175 |  |  | Low | Office 365 SAP VoIP applications
Planning | Solution Architecture | Design DNA Center architecture and HA deployment |  | 48 | 225 |  | Network Assessment | Medium | Primary and secondary DNA Center nodes
Planning | Network Policy Framework | Design authentication authorization and assurance policies |  | 40 | 200 |  | Requirements | Medium | 802.1X TrustSec and compliance policies
Planning | Migration Strategy | Plan phased device onboarding and migration approach |  | 32 | 200 |  | Assessment | Medium | Pilot sites and rollout waves
Planning | Training Plan | Develop training curriculum for administrators and operators |  | 16 | 175 |  |  | Low | Hands-on labs and certification prep
Development | DNA Center Deployment | Deploy and configure DNA Center appliances |  | 60 | 200 |  | Architecture Design | Medium | HA pair installation and base configuration
Development | Device Discovery | Discover and onboard 200 network devices |  | 80 | 175 |  | DNA Center Setup | Medium | Automated discovery and manual addition
Development | Policy Configuration | Configure network policies templates and automation |  | 60 | 200 |  | Policy Framework | Medium | Authentication VLAN assignment ACLs
Development | AI Analytics Setup | Configure AI network analytics and assurance features |  | 40 | 225 |  | Device Onboarding | Medium | Predictive insights and anomaly detection
Development | Integration Setup | Integrate with AD ServiceNow and NetBox |  | 40 | 200 |  | Policy Config | Medium | Identity source ITSM and IPAM integration
Development | Application Monitoring | Configure application experience monitoring |  | 32 | 200 |  | AI Analytics | Low | Office 365 Webex SAP monitoring
Testing | Lab Validation | Test DNA Center policies in lab environment |  | 32 | 175 |  | Policy Config | Medium | GNS3 or physical lab testing
Testing | Pilot Deployment | Deploy to 20 pilot devices for validation |  | 40 | 175 |  | Lab Validation | Medium | IT department or friendly site
Testing | Policy Testing | Validate authentication authorization and analytics |  | 32 | 175 |  | Pilot Deployment | Medium | End-to-end workflow testing
Testing | Failover Testing | Test DNA Center HA and device failover scenarios |  | 24 | 200 |  | Pilot Success | Medium | Controller failover and network resilience
Deployment | Production Deployment | Deploy remaining 180 devices to DNA Center |  | 80 | 175 |  | Testing Complete | Medium | Phased rollout by site or device type
Deployment | Policy Rollout | Enable enforcement policies across network |  | 40 | 200 |  | Device Migration | High | Gradual policy enforcement
Deployment | Monitoring Activation | Activate assurance monitoring and alerting |  | 24 | 175 |  | Policy Rollout | Medium | CloudWatch and ITSM integration
Deployment | Go-Live Support | Provide hypercare support during stabilization |  | 48 | 150 |  | Production Rollout | Medium | 4-week post-deployment support
Training | Administrator Training | Train DNA Center administrators on operations |  | 24 | 175 |  | Deployment Complete | Low | Policy management and troubleshooting
Training | Operations Training | Train network team on assurance and analytics |  | 16 | 150 |  | Admin Training | Low | Dashboard usage and incident response
Training | Documentation | Create runbooks and operational documentation |  | 32 | 150 |  |  | Low | SOPs troubleshooting guides best practices
Closeout | Knowledge Transfer | Transfer solution to operations team |  | 16 | 175 |  | Training Complete | Low | Operational handoff and escalation procedures
Closeout | Performance Baseline | Establish performance baselines and KPIs |  | 16 | 175 |  | Go-Live | Low | MTTR uptime and automation metrics
Management | Technical Leadership | Technical quarterback and architecture oversight |  |  | 225 |  |  | Medium | 25% of total engineering effort
Management | Project Management | Project coordination and stakeholder management |  |  | 175 |  |  | Low | 20% of total engineering effort
|  |  | TOTAL HOURS |  | TOTAL COST |  |  |  | Total DNA Center implementation cost

## Credits
CREDITS
Category | Credit Type | Credit Amount | Credit Comments
Hardware | Cisco SmartNet Renewal | -5000 | Existing SmartNet contract renewal credit applied
Software | DNA License Promotion | -20000 | Year 1 DNA Advantage license 33% discount promotion
Professional Services | Implementation Services | 0 | No professional services credits available
Support & Maintenance | Annual Support Credit | 0 | No support renewal credits available