## Cover
[DOCUMENT TITLE]
Level of Effort
CISCO - Network - Sd Wan Enterprise
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Primary Features/Capabilities | SD-WAN for 25 branch offices | SD-WAN for 25 sites | SD-WAN for 50 sites | SD-WAN for 100+ sites | Branch office count and scope
Solution Scope | Customization Level | Standard SD-WAN deployment | Standard policies | Custom application policies and QoS | Extensive custom routing and security | Configuration vs customization
Integration | External System Integrations | 2 systems (cloud + monitoring) | 2 systems | 4 systems (cloud monitoring ITSM IPAM) | 6+ systems including orchestration | Cloud and management integration
Integration | Data Sources | WAN telemetry only | WAN telemetry | WAN + application + security data | WAN + app + security + external feeds | Performance and security data
User Base | Total Users | 5 network engineers | 5 engineers | 10 network team members | 20+ distributed WAN team | vManage and SD-WAN operators
User Base | User Roles | 2 roles (admin + operator) | 2 roles | 4 roles with regional delegation | 6+ roles with complex RBAC | Role-based access control
Data Volume | Data Processing Volume | 25 sites WAN traffic | 25 sites | 50 sites WAN traffic | 100+ sites WAN traffic | SD-WAN overlay traffic volume
Data Volume | Data Storage Requirements | 200 GB (90-day logs) | 200 GB | 500 GB (1-year logs) | 2+ TB (multi-year logs) | vManage telemetry and logs
Technical Environment | Deployment Regions | Single region | Single region | 2 regions | Multi-region global deployment | Geographic distribution
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | WAN uptime SLA
Technical Environment | Infrastructure Complexity | Basic hub-spoke WAN | Basic hub-spoke | Regional hubs with mesh | Complex multi-tier WAN architecture | WAN topology complexity
Security & Compliance | Security Requirements | Basic VPN encryption | Basic encryption | Integrated firewall + IPS | Advanced security + SASE integration | WAN security architecture
Security & Compliance | Compliance Frameworks | Basic logging | Basic logging | PCI DSS or SOC 2 | Multiple regulatory frameworks | Compliance automation requirements
Performance | Performance Requirements | Standard application routing | Standard routing | Application-aware routing + SLA | Advanced TE and performance optimization | Traffic engineering sophistication
Environment | Deployment Environments | Production only | Production only | Lab + production | Lab + staging + production | Testing and validation environments

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (WAN Assessment, Circuit Analysis, Requirements Gathering)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Architecture Design, Policy Design, Migration Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Controller Deployment, Router Configuration, Policy Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Lab Testing, Pilot Validation, Performance Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Site Deployment, MPLS Cutover, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Team Training, Documentation, Knowledge Transfer)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Operational Handoff, Performance Baseline, MPLS Decommission)
Management | MANAGEMENT_MX | 0.25 | Project management and technical leadership (25% of total engineering effort)
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
LEVEL OF EFFORT
Phase | Work Package | Task Description | Resource Type | Estimated Hours | Rate | Cost Estimate | Dependencies | Risk Level | Notes
Discovery | WAN Assessment | Assess current MPLS WAN architecture and costs |  | 40 | 225 |  |  | Medium | MPLS circuits bandwidth and costs
Discovery | Circuit Availability Analysis | Analyze broadband and LTE availability at sites |  | 32 | 200 |  |  | High | Circuit procurement feasibility
Discovery | Application Inventory | Identify critical applications and SLA requirements |  | 32 | 200 |  |  | Medium | Office 365 SAP VoIP performance needs
Discovery | Traffic Analysis | Analyze WAN traffic patterns and bandwidth usage |  | 24 | 175 |  |  | Medium | NetFlow analysis and capacity planning
Planning | SD-WAN Architecture | Design SD-WAN architecture for 25 sites |  | 60 | 225 |  | Assessment | Medium | vManage vSmart vBond controller design
Planning | Routing Policy Design | Design application-aware routing and SLA policies |  | 48 | 225 |  | Application Inventory | High | SaaS optimization and QoS policies
Planning | Security Architecture | Design SD-WAN security and firewall policies |  | 32 | 225 |  | Architecture | Medium | VPN encryption and firewall rules
Planning | Migration Strategy | Plan MPLS to SD-WAN migration approach |  | 40 | 200 |  | Routing Design | High | Pilot sites and phased rollout
Development | Controller Deployment | Deploy vManage vSmart vBond controllers |  | 40 | 225 |  | Architecture | Medium | Virtual controllers in data center
Development | Hub Router Configuration | Configure 2 hub routers at data centers |  | 40 | 200 |  | Controllers | Medium | ISR 4451 dual-hub configuration
Development | Routing Policy Configuration | Configure application routing and SLA policies |  | 60 | 200 |  | Policy Design | High | Office 365 SaaS ERP VoIP policies
Development | Security Policy Configuration | Configure firewall and security policies |  | 40 | 200 |  | Routing Policies | Medium | Zone-based firewall and IPS
Development | Cloud Integration | Configure cloud on-ramps for AWS/Azure (optional) |  | 30 | 225 |  | Security Policies | Low | Direct cloud connectivity setup
Development | Branch Router Preconfiguration | Preconfigure 25 ISR branch routers for ZTP |  | 50 | 200 |  | Policy Config | Medium | Zero-touch provisioning templates
Testing | Lab Validation | Test SD-WAN policies in lab environment |  | 32 | 200 |  | Config Complete | Medium | GNS3 or CML testing
Testing | Pilot Site Deployment | Deploy 3 pilot sites for validation |  | 60 | 200 |  | Lab Testing | High | Low-risk site validation
Testing | Performance Testing | Test application performance and SLA compliance |  | 40 | 200 |  | Pilot Deploy | High | Office 365 VoIP and ERP testing
Testing | Failover Testing | Test WAN circuit failover scenarios |  | 24 | 175 |  | Performance Tests | Medium | Broadband to LTE failover
Deployment | Site Deployment Wave 1 | Deploy 10 sites (Wave 1) |  | 60 | 175 |  | Testing Complete | Medium | Circuit installation and ZTP
Deployment | Site Deployment Wave 2 | Deploy 12 remaining sites (Wave 2) |  | 60 | 175 |  | Wave 1 Success | Medium | Final site rollout
Deployment | MPLS Cutover | Decommission MPLS circuits site-by-site |  | 40 | 175 |  | All Sites Deployed | High | Validate SD-WAN before MPLS disconnect
Deployment | Hypercare Support | Provide post-deployment stabilization support |  | 60 | 150 |  | Deployment Complete | Medium | 4-week hypercare period
Training | vManage Training | Train team on vManage operations and monitoring |  | 24 | 175 |  | Deployment | Low | Policy management and dashboards
Training | Troubleshooting Training | Train team on SD-WAN troubleshooting |  | 16 | 175 |  | vManage Training | Low | Packet trace and path analysis
Training | Documentation | Create runbooks SOPs and architecture docs |  | 32 | 150 |  |  | Low | Operational procedures and diagrams
Closeout | Knowledge Transfer | Transfer SD-WAN to operations team |  | 16 | 175 |  | Training Complete | Low | Operational handoff and escalation
Closeout | Performance Baseline | Establish WAN performance baselines and SLAs |  | 16 | 175 |  | Hypercare | Low | Application SLA compliance metrics
Closeout | MPLS Decommission Completion | Complete MPLS circuit disconnections |  | 16 | 150 |  | MPLS Cutover | Medium | Final circuit cancellations and validation
Management | Technical Leadership | Technical quarterback and architecture oversight |  |  | 225 |  |  | Medium | 25% of total engineering effort
Management | Project Management | Project coordination and stakeholder management |  |  | 175 |  |  | Low | 20% of total engineering effort
|  |  | TOTAL HOURS |  | TOTAL COST |  |  |  | Total SD-WAN implementation cost

## Credits
CREDITS
Category | Credit Type | Credit Amount | Credit Comments
Hardware | Router Trade-In Credit | -8000 | Legacy router trade-in credit
Software | SD-WAN License Promotion | -15000 | Year 1 SD-WAN license 25% discount promotion
WAN Circuits | Circuit Installation Waiver | -12000 | Year 1 broadband circuit installation fees waived by provider
Professional Services | Implementation Services | 0 | No professional services credits available