Implementation Guide

**Solution Name:** AWS Intelligent Document Processing

Generated: November 03, 2025

Solution: Intelligent Document Processing

Version: 1.0

Document Version: 1.0

Date: November 03, 2025

Prepared by: EO Framework Consulting

Client: Sample Client

Project: Intelligent Document Processing Implementation

SOW Number: SOW-2025-001

Table of Contents

1  Project Information 	3

2  Executive Summary 	4

2.1  Project Overview 	5

2.2  Implementation Scope 	6

2.3  Timeline Overview 	7

3  Prerequisites 	8

3.1  Technical Prerequisites 	9

3.2  Skills and Expertise Requirements 	10

3.3  Organizational Prerequisites 	11

3.4  Environmental Setup 	12

3.5  Planning and Documentation Requirements 	13

4  Implementation Phases 	14

4.1  Phase 1: Infrastructure Foundation (Months 1-2) 	15

4.1.1  Objectives 	16

4.1.2  Activities 	17

4.1.3  Deliverables 	18

4.1.4  Success Criteria 	19

4.2  Phase 2: AI Services Deployment (Months 3-4) 	20

4.2.1  Objectives 	21

4.2.2  Activities 	22

4.2.3  Deliverables 	23

4.2.4  Success Criteria 	24

4.3  Phase 3: System Integration (Months 5-6) 	25

4.3.1  Objectives 	26

4.3.2  Activities 	27

4.3.3  Deliverables 	28

4.3.4  Success Criteria 	29

5  Technical Implementation Details 	30

5.1  Infrastructure Configuration 	31

5.1.1  VPC and Networking 	32

5.1.2  S3 Bucket Configuration 	33

5.2  AI Service Configuration 	34

5.2.1  Amazon Textract Setup 	35

5.2.2  Amazon Comprehend Integration 	36

5.3  Deployment Procedures 	37

5.3.1  CloudFormation Deployment 	38

5.3.2  Deployment Commands 	39

6  Testing Strategy 	40

6.1  Unit Testing 	41

6.2  Integration Testing 	42

6.3  Performance Testing 	43

7  Security Implementation 	44

7.1  IAM Policies 	45

7.2  Encryption Configuration 	46

8  Quality Assurance 	47

8.1  Code Quality Gates 	48

8.2  Acceptance Criteria 	49

9  Deployment Checklist 	50

9.1  Pre-Deployment 	51

9.2  Deployment Day 	52

9.3  Post-Deployment 	53

10  Implementation Troubleshooting 	54

10.1  Common Implementation Issues 	55

10.1.1  Configuration Issues 	56

10.1.2  AI/ML Service Integration Issues 	57

10.1.3  Network and Connectivity Issues 	58

10.1.4  Performance Issues 	59

10.2  Escalation Procedures 	60

## 1  Project Information

## 2  Executive Summary

### 2.1  Project Overview

This implementation guide provides step-by-step procedures for deploying the AWS Intelligent Document Processing solution, enabling automated document analysis, data extraction, and workflow integration using AI/ML services.

### 2.2  Implementation Scope

In Scope: Document processing automation, AI model deployment, system integration

Out of Scope: Legacy system migration, custom model development (Phase 1)

Dependencies: AWS account setup, client system APIs, user training

### 2.3  Timeline Overview

Project Duration: 6 months

Go-Live Date: [Target date]

Key Milestones: Infrastructure (Month 2), AI Services (Month 4), Full Deployment (Month 6)

## 3  Prerequisites

### 3.1  Technical Prerequisites

[ ] AWS Enterprise Account with appropriate service limits and administrative access

[ ] VPC setup with public/private subnets across 2+ AZs

[ ] IAM roles and policies configured for AI services (Textract, Comprehend, SageMaker, Bedrock)

[ ] Network connectivity between client and AWS environments with sufficient bandwidth

[ ] SSL certificates for API endpoints and secure communications

[ ] Service quotas validated for Amazon Textract, Comprehend, and SageMaker

[ ] Security access controls and firewall configurations approved

[ ] Compute resources sized for expected AI/ML workloads

[ ] Storage capacity for document repositories and model artifacts

### 3.2  Skills and Expertise Requirements

[ ] Lead Architect: 5+ years cloud architecture experience with AI/ML solutions

[ ] Implementation Engineers: 3+ years AWS experience with hands-on ML and Python/Node.js skills

[ ] Security Specialist: 3+ years security and compliance experience

[ ] Operations Team: 2+ years production support experience with AWS services

[ ] Team members trained on AWS AI services and document processing workflows

### 3.3  Organizational Prerequisites

[ ] Project team assigned with clear roles and responsibilities

[ ] Executive sponsorship confirmed with change management support

[ ] Budget approved for implementation and operational costs ($75K-$200K implementation + ongoing operational costs)

[ ] Document samples available for testing and validation (1,000+ labeled documents per type)

[ ] Integration specifications for existing systems and APIs

[ ] Compliance frameworks identified (SOC 2, ISO 27001, GDPR, HIPAA as applicable)

[ ] Security policies and data classification requirements documented

### 3.4  Environmental Setup

[ ] Development environment configured for initial testing with AI service access

[ ] Testing environment prepared for integration validation and model training

[ ] Staging environment ready for user acceptance testing with production-like data

[ ] Production environment provisioned with monitoring, logging, and alerting

[ ] Backup and disaster recovery infrastructure prepared

[ ] Network connectivity tested including VPN/dedicated connections

### 3.5  Planning and Documentation Requirements

[ ] Current state architecture documented including existing document processing workflows

[ ] Network topology and security diagrams prepared

[ ] Integration requirements and dependencies mapped

[ ] Risk assessment completed with mitigation strategies

[ ] Change management and approval processes established

[ ] User acceptance testing procedures and criteria defined

[ ] CI/CD pipeline configured for automated deployment

## 4  Implementation Phases

### 4.1  Phase 1: Infrastructure Foundation (Months 1-2)

#### 4.1.1  Objectives

Establish secure, scalable AWS infrastructure

Configure core services and networking

Implement security baseline and monitoring

#### 4.1.2  Activities

| Activity | Owner | Duration | Dependencies |
|----------|-------|----------|-------------|
| AWS Account Setup | DevOps Team | 3 days | AWS Enterprise Agreement |
| VPC and Network Configuration | Network Team | 5 days | Security requirements |
| IAM Roles and Policies | Security Team | 3 days | Access requirements |
| S3 Buckets and Lifecycle Policies | DevOps Team | 2 days | Data retention policies |
| CloudWatch and Monitoring Setup | Operations Team | 4 days | Monitoring requirements |

#### 4.1.3  Deliverables

[ ] AWS infrastructure deployed and documented

[ ] Security baseline implemented and validated

[ ] Network connectivity tested and confirmed

[ ] Monitoring and alerting operational

[ ] Infrastructure documentation complete

#### 4.1.4  Success Criteria

All infrastructure components pass security scan

Network connectivity achieves <50ms latency

Monitoring captures all required metrics

Security controls meet compliance requirements

### 4.2  Phase 2: AI Services Deployment (Months 3-4)

#### 4.2.1  Objectives

Deploy and configure Amazon Textract for OCR

Implement Amazon Comprehend for NLP analysis

Set up Amazon A2I for human review workflows

Validate AI accuracy with sample documents

#### 4.2.2  Activities

| Activity | Owner | Duration | Dependencies |
|----------|-------|----------|-------------|
| Textract Configuration | AI Team | 5 days | Document samples |
| Comprehend Setup | AI Team | 3 days | Entity requirements |
| A2I Workflow Implementation | AI Team | 7 days | Review process design |
| Lambda Function Development | Development Team | 10 days | Business logic |
| Accuracy Testing and Validation | QA Team | 5 days | Test documents |

#### 4.2.3  Deliverables

[ ] Textract configured for document types

[ ] Comprehend entities and sentiment analysis operational

[ ] A2I workflows for quality assurance deployed

[ ] Lambda orchestration functions implemented

[ ] AI accuracy validation completed

#### 4.2.4  Success Criteria

Textract achieves >99% accuracy on machine-printed text

Comprehend correctly identifies required entities

A2I workflows process low-confidence documents

Processing time averages <30 seconds per document

### 4.3  Phase 3: System Integration (Months 5-6)

#### 4.3.1  Objectives

Integrate with existing ERP and CRM systems

Implement end-to-end automation workflows

Deploy production monitoring and operations

Complete user training and knowledge transfer

#### 4.3.2  Activities

| Activity | Owner | Duration | Dependencies |
|----------|-------|----------|-------------|
| API Gateway Configuration | Integration Team | 5 days | System specifications |
| ERP/CRM Integration Development | Integration Team | 15 days | Client system access |
| End-to-End Testing | QA Team | 10 days | Complete system |
| Production Deployment | DevOps Team | 5 days | Testing completion |
| User Training and Handover | Training Team | 10 days | Documentation |

#### 4.3.3  Deliverables

[ ] API integrations with all required systems

[ ] End-to-end automation workflows operational

[ ] Production environment deployed and validated

[ ] User training completed and documented

[ ] Operations procedures implemented

#### 4.3.4  Success Criteria

All system integrations pass acceptance testing

End-to-end workflows process documents without manual intervention

Production environment meets all performance requirements

Users demonstrate proficiency in system operation

## 5  Technical Implementation Details

### 5.1  Infrastructure Configuration

#### 5.1.1  VPC and Networking

#### 5.1.2  S3 Bucket Configuration

### 5.2  AI Service Configuration

#### 5.2.1  Amazon Textract Setup

#### 5.2.2  Amazon Comprehend Integration

### 5.3  Deployment Procedures

#### 5.3.1  CloudFormation Deployment

#### 5.3.2  Deployment Commands

## 6  Testing Strategy

### 6.1  Unit Testing

### 6.2  Integration Testing

### 6.3  Performance Testing

## 7  Security Implementation

### 7.1  IAM Policies

### 7.2  Encryption Configuration

## 8  Quality Assurance

### 8.1  Code Quality Gates

Code Coverage: Minimum 80% test coverage

Security Scan: No critical vulnerabilities

Performance: Sub-30 second processing time

Documentation: Complete API and operational docs

### 8.2  Acceptance Criteria

[ ] All functional requirements implemented and tested

[ ] Performance requirements met (accuracy >99%, speed <30s)

[ ] Security requirements validated

[ ] Integration with all specified systems complete

[ ] User acceptance testing passed

[ ] Operations documentation complete

## 9  Deployment Checklist

### 9.1  Pre-Deployment

[ ] Infrastructure deployed and tested

[ ] Application code deployed to staging

[ ] Integration testing completed

[ ] Performance testing passed

[ ] Security testing completed

[ ] User acceptance testing signed off

[ ] Operations procedures documented

[ ] Backup and recovery tested

### 9.2  Deployment Day

[ ] Final code deployment to production

[ ] Database migration (if required)

[ ] DNS cutover and validation

[ ] Smoke testing of critical paths

[ ] Performance monitoring activated

[ ] User notification sent

[ ] Support team briefed

### 9.3  Post-Deployment

[ ] Production monitoring confirmed

[ ] Performance metrics validated

[ ] User feedback collected

[ ] Issue log maintained

[ ] Knowledge transfer completed

[ ] Project closure documentation

## 10  Implementation Troubleshooting

### 10.1  Common Implementation Issues

#### 10.1.1  Configuration Issues

Symptoms: Service startup errors, parameter validation failures, deployment failures
Quick Resolution:

Validate configuration against provided templates in configuration.csv

Check AWS service quotas and limits

Verify IAM roles and permissions for AI services

Review CloudFormation/CDK deployment logs

#### 10.1.2  AI/ML Service Integration Issues

Symptoms: Model endpoints not accessible, accuracy below targets, processing timeouts
Quick Resolution:

Verify SageMaker endpoint status and auto-scaling configuration

Check Textract and Comprehend service limits and quotas

Validate document formats and size limits

Review model training data quality and coverage

#### 10.1.3  Network and Connectivity Issues

Symptoms: API timeouts, SSL certificate errors, DNS resolution failures
Quick Resolution:

Test network connectivity between environments

Verify security group rules for AI service endpoints

Check VPC endpoints and NAT Gateway configurations

Validate SSL certificate installation and expiration

#### 10.1.4  Performance Issues

Symptoms: Slow document processing, high latency, timeout errors
Quick Resolution:

Scale Lambda concurrency and memory allocation

Optimize SageMaker endpoint auto-scaling policies

Review DynamoDB read/write capacity settings

Implement CloudFront caching for static resources

### 10.2  Escalation Procedures

Level 1 Issues (< 2 hours): Configuration, permission, basic connectivity

Level 2 Issues (2-4 hours): Performance optimization, complex integrations

Level 3 Issues (> 4 hours): Architecture changes, security incidents

Required Information for Escalation:

Detailed error messages and symptoms

Environment details and recent changes

Relevant log excerpts from CloudWatch

Current system metrics and performance data

Document Version: 1.0
Last Updated: January 2025
Maintained By: AI Solutions Implementation Team