# Implementation Guide

AWS Cloud Migration - Implementation Guide

| Client Name: | [Client Company Name] |
| --- | --- |
| Date: | [MM/DD/YYYY] |
| Consulting Company: | [Consulting Company Name] |
| Submitted By: | [Full Name] [email@example.com] [Phone: (555) 123-4567] |
| Version: | 1.0 |

# Table of Contents

Table of Contents	1

List of Figures	1

1    Section Header 1	1

1.1    Section Sub-Header 1	1

1.1.1    Section Sub-Header 2	1

1.1.1.1    Section Sub-Header 3	1

1.1.1.2    Section Sub-Header 4	1

1.2    Section Sub-Header 5	1

2    Section Header 2 - Table Content	1

2.1    Table Section 1	1

2.2    Table Section 2	1

3    Section Header 3 - Image Section	1

3.1    Image Content	1

4    Section Header 4	1

4.1    Additional Sub-Section	1

5    Approvals and Signatures	1

## 1 Document Information

Solution: AWS On-Premise to Cloud Migration  
Version: 1.0  
Date: January 2025  
Audience: Implementation Teams, Migration Engineers, Project Managers

## 2 Overview

This implementation guide provides comprehensive step-by-step instructions for executing an enterprise cloud migration to AWS. The guide follows a proven methodology that minimizes risk, ensures data integrity, and maximizes business value throughout the migration process.

### 2.1 Implementation Phases

Phase 1: Discovery and Assessment (Weeks 1-4)

Phase 2: Foundation and Preparation (Weeks 5-8)

Phase 3: Migration Wave Execution (Weeks 9-20)

Phase 4: Optimization and Closure (Weeks 21-24)

### 2.2 Key Principles

• Risk Minimization: Phased approach with comprehensive testing

• Zero Data Loss: Multiple validation and backup procedures

• Business Continuity: Minimal disruption to business operations

• Automation First: Leverage AWS native migration tools

• Continuous Validation: Testing and verification at every step

## 3 Prerequisites Verification

Before beginning implementation, ensure all prerequisites from the prerequisites document are satisfied:

### 3.1 Organizational Readiness

• [ ] Executive sponsorship confirmed and communicated

• [ ] Migration team assembled with defined roles

• [ ] Budget approved and allocated

• [ ] Timeline agreed upon by all stakeholders

• [ ] Change management process established

### 3.2 Technical Prerequisites

• [ ] AWS accounts configured with appropriate permissions

• [ ] Network connectivity planned (Direct Connect or VPN)

• [ ] Source environment inventory completed

• [ ] Application dependencies mapped

• [ ] Performance baselines established

### 3.3 Security and Compliance

• [ ] Security framework approved

• [ ] Compliance requirements documented

• [ ] Encryption strategy defined

• [ ] Access control procedures established

• [ ] Audit trail requirements confirmed

## 4 Phase 1: Discovery and Assessment

### 4.1 Step 1.1: Environment Discovery

#### 4.1.1 Deploy AWS Application Discovery Service

#### 4.1.2 Install Discovery Agents

For Linux Servers:

For Windows Servers:

#### 4.1.3 Configure Agentless Discovery (VMware)

### 4.2 Step 1.2: Data Collection and Analysis

#### 4.2.1 Monitor Discovery Progress

#### 4.2.2 Analyze Discovery Data

### 4.3 Step 1.3: Application Portfolio Analysis

#### 4.3.1 Analyze Application Dependencies

## 5 Phase 2: Foundation and Preparation

### 5.1 Step 2.1: AWS Landing Zone Setup

#### 5.1.1 Deploy AWS Control Tower

#### 5.1.2 Create Migration-Specific Accounts

### 5.2 Step 2.2: Network Infrastructure Setup

#### 5.2.1 Deploy VPC and Networking

#### 5.2.2 Configure NAT Gateways and Routing

### 5.3 Step 2.3: Security Infrastructure

#### 5.3.1 Create Security Groups

#### 5.3.2 Set Up KMS Encryption

### 5.4 Step 2.4: Migration Services Setup

#### 5.4.1 Initialize AWS Application Migration Service (MGN)

#### 5.4.2 Set Up AWS Database Migration Service (DMS)

#### 5.4.3 Configure AWS Server Migration Service (SMS)

## 6 Phase 3: Migration Wave Execution

### 6.1 Step 3.1: Wave 1 - Foundation Services Migration

#### 6.1.1 Migrate DNS and Directory Services

#### 6.1.2 Set Up Monitoring Infrastructure

### 6.2 Step 3.2: Application Server Migration Process

#### 6.2.1 Install and Configure MGN Agents

#### 6.2.2 Monitor Replication Progress

### 6.3 Step 3.3: Database Migration Process

#### 6.3.1 Set Up Database Migration Tasks

### 6.4 Step 3.4: Testing and Validation

#### 6.4.1 Create Automated Testing Framework

## 7 Phase 4: Optimization and Closure

### 7.1 Step 4.1: Performance Optimization

#### 7.1.1 Right-sizing and Cost Optimization

### 7.2 Step 4.2: Security Hardening

#### 7.2.1 Implement Security Best Practices

### 7.3 Step 4.3: Knowledge Transfer and Documentation

#### 7.3.1 Create Migration Documentation

## 8 Project Closure and Handover

### 8.1 Final Migration Report

## 9 Summary

This implementation guide provides a comprehensive, step-by-step approach to executing an enterprise cloud migration to AWS. The guide includes:

### 9.1 Key Deliverables

• Automated Discovery: Scripts for infrastructure and application discovery

• Migration Tools Setup: Complete configuration of MGN, DMS, and SMS services

• Testing Framework: Comprehensive validation and testing procedures

• Optimization Tools: Performance and cost optimization analysis

• Security Hardening: Implementation of security best practices

• Documentation: Complete operational runbooks and knowledge transfer

### 9.2 Success Factors

• Phased Approach: Risk-managed execution across multiple waves

• Automation First: Leveraging AWS native tools for efficiency

• Continuous Validation: Testing at every stage to ensure quality

• Comprehensive Monitoring: Full visibility into migration progress

• Knowledge Transfer: Proper documentation and team training

### 9.3 Next Steps

Operations Handover: Transition to operational support team

Continuous Optimization: Regular review and optimization cycles

Skills Development: Ongoing AWS training and certification

Innovation Planning: Leverage cloud capabilities for business innovation

## 10 Implementation Troubleshooting

### 10.1 Common Migration Issues and Solutions

#### 10.1.1 AWS Migration Service (MGN) Issues

Symptoms: Agent installation failures, replication not starting, agent disconnected
Quick Resolution:

• Verify AWS credentials and IAM permissions for MGN service

• Check network connectivity to AWS MGN endpoints

• Validate source server requirements and compatibility

• Review agent installation logs: `sudo tail -f /var/log/aws-replication-agent.log`

• Reinstall agent with proper parameters if needed

#### 10.1.2 Database Migration Service (DMS) Issues

Symptoms: Replication task failures, data inconsistencies, connection timeouts
Quick Resolution:

• Verify DMS replication instance capacity and configuration

• Check source and target database connectivity and permissions

• Review DMS task logs for specific error messages

• Validate network security groups and firewall rules

• Test database connections independently

#### 10.1.3 Network Connectivity Issues

Symptoms: VPN connection failures, Direct Connect issues, routing problems
Quick Resolution:

• Test basic connectivity: `ping`, `telnet`, `nslookup`

• Verify security group rules and NACLs

• Check VPC endpoints and NAT Gateway configurations

• Validate DNS resolution and certificate chains

• Review CloudWatch VPC Flow Logs for traffic analysis

#### 10.1.4 Performance and Capacity Issues

Symptoms: Slow migration performance, resource exhaustion, auto-scaling issues
Quick Resolution:

• Check CloudWatch metrics for CPU, memory, and network utilization

• Review auto-scaling policies and thresholds

• Validate resource quotas and service limits

• Optimize instance types and storage configurations

• Implement performance tuning recommendations

### 10.2 Migration-Specific Diagnostics

#### 10.2.1 MGN Agent Diagnostics

#### 10.2.2 DMS Task Monitoring

#### 10.2.3 Migration Wave Validation

• Verify all dependencies are resolved before proceeding

• Test application functionality in target environment

• Validate data integrity and consistency

• Check performance against baseline metrics

• Confirm backup and recovery procedures

### 10.3 Escalation Procedures

• Level 1 Issues (< 4 hours): Configuration errors, permission issues, basic connectivity

• Level 2 Issues (4-8 hours): Complex network issues, performance optimization, data inconsistencies

• Level 3 Issues (> 8 hours): Architecture problems, security incidents, major data corruption

Escalation Information Required:

• Detailed error messages and logs

• Migration wave and server details

• Recent changes or modifications

• Current migration status and metrics

• Impact assessment and affected systems

Document Version: 1.0
Last Updated: January 2025
Next Review: April 2025
Maintained By: Migration Implementation Team