## Cover
Roles
Delivery Document
Generated: | November 06, 2025
Solution: | Onpremise To Cloud Migration
Purpose: | Data table for roles
Version: | 1.0

## Roles
Role | Team | Team Member | Responsible Tasks | Accountable For | Consulted On | Informed Of | Primary Skills Required | Backup Person | Availability % | Contact Information | Escalation Path | Start Date | End Date | Notes
EO Project Manager | Project Management | [MPM Name] | Overall migration coordination and delivery | Migration success and timeline adherence | All major migration decisions | All project communications | PMP certification and cloud migration experience | Senior Project Manager | 100 | [EMAIL] | [MANAGER] | Project Start | Project End | Single point of accountability for migration delivery using EO Framework™ methodology
EO Sales Engineer (Solution Architecture) | Architecture | [CA Name] | AWS architecture design and cloud migration strategy | Cloud architecture quality and AWS best practices compliance | Cloud design decisions | Architecture reviews and AWS service selection | AWS Solution Architect certification and cloud architecture | Principal Cloud Architect | 100 | [EMAIL] | Architecture Manager | Assessment Phase | Optimization Complete | Technical authority for AWS cloud design using EO Framework™ principles
EO Sales Engineer (Solution Architecture) | Migration | [MA Name] | Migration strategy design and wave planning | Migration approach and dependency management | Migration wave sequencing | Migration strategy and risk assessments | Migration methodology and dependency analysis | Senior Migration Consultant | 100 | [EMAIL] | Migration Director | Assessment Phase | Migration Complete | Designs comprehensive migration approach following EO Framework™ methodology
EO Sales Engineer (Solution Architecture) | AWS | [AWS-SA Name] | AWS technical guidance and best practices | AWS service recommendations and technical support | AWS service selection and optimization | AWS updates and service recommendations | AWS expertise and solution architecture | AWS Professional Services | 40 | [EMAIL] | AWS Account Manager | Project Start | Project End | Provides AWS technical leadership and guidance aligned with EO Framework™ standards
EO Delivery Engineer (Technical Leadership) | Migration | [AML Name] | Application migration execution and coordination | Application migration success and quality | Application migration approaches | Application migration progress and issues | Application migration tools and methodologies | Senior Migration Engineer | 100 | [EMAIL] | EO Sales Engineer (Solution Architecture) | Migration Phase | Migration Complete | Leads hands-on application migration activities using EO Framework™ quality standards
EO Delivery Engineer (Infrastructure) | Data Migration | [DMS Name] | Database and data migration execution | Data migration integrity and zero data loss | Data migration strategies and tooling | Data migration progress and validation results | AWS DMS and database migration expertise | Senior Data Engineer | 100 | [EMAIL] | Data Architect | Migration Phase | Data Migration Complete | Ensures comprehensive and accurate data migration following EO Framework™ standards
EO Engineer (Security) | Security | [CSA Name] | Cloud security architecture and compliance framework | Cloud security posture and compliance validation | Cloud security requirements and controls | Security assessments and compliance status | AWS security services and compliance frameworks | Principal Security Architect | 60 | [EMAIL] | Security Manager | Assessment Phase | Security Implementation Complete | Designs secure AWS architecture with EO Framework™ standards
EO Delivery Engineer (Platform Implementation) | Infrastructure | [CE Name] | AWS infrastructure implementation and configuration | AWS environment setup and operational readiness | AWS service configuration and optimization | AWS infrastructure changes and deployments | AWS services administration and infrastructure as code | Senior Cloud Engineer | 100 | [EMAIL] | EO Sales Engineer (Solution Architecture) | Implementation Phase | Handover Complete | Implements and maintains AWS cloud infrastructure following EO Framework™ methodology
EO Delivery Engineer (Infrastructure) | Network | [NE Name] | Hybrid network connectivity and AWS networking | Network connectivity and performance | Network architecture and routing design | Network changes and connectivity issues | AWS networking services and hybrid connectivity | Senior Network Engineer | 80 | [EMAIL] | Network Manager | Implementation Phase | Migration Complete | Establishes and maintains network connectivity following EO Framework™ standards
EO Delivery Engineer (Platform Implementation) | Migration | [ME Name] | Technical migration execution and automation | Migration task execution and quality | Migration tooling and automation | Migration progress and technical issues | AWS migration tools and automation scripting | EO Sales Engineer (Solution Architecture) | 100 | [EMAIL] | EO Delivery Engineer (Technical Leadership) | Migration Phase | Migration Complete | Executes technical migration tasks and automation using EO Framework™ methodology
EO Sales Engineer (Business Analysis) | Business | [BA Name] | Migration requirements and business impact analysis | Business requirements completeness and stakeholder alignment | Business requirements and impact assessment | Requirements changes and business readiness | Business analysis and cloud migration impact assessment | Senior Business Analyst | 80 | [EMAIL] | Business Manager | Assessment Phase | UAT Complete | Analyzes business impact and requirements for migration using EO Framework™ approach
EO Engineer (QA) | Quality Assurance | [QAE Name] | Migration testing and validation | Migration testing completeness and quality standards | Test planning and validation strategies | Test results and migration quality metrics | Migration testing and cloud application testing | EO Engineer (QA Lead) | 100 | [EMAIL] | QA Manager | Testing Phase | Migration Complete | Tests and validates migrated applications and systems using EO Framework™ quality standards
EO Engineer (Performance) | Performance | [PE Name] | Cloud performance testing and optimization | Application performance in cloud environment | Performance optimization strategies | Performance metrics and optimization results | Cloud performance testing and AWS optimization | Senior Performance Engineer | 60 | [EMAIL] | Performance Manager | Testing Phase | Optimization Complete | Ensures optimal cloud application performance using EO Framework™ standards
EO Delivery Engineer (Infrastructure) | DevOps | [DO Name] | Migration automation and CI/CD pipeline setup | Migration automation and deployment reliability | Infrastructure automation and tooling | Automation progress and pipeline deployments | AWS DevOps tools and infrastructure automation | Senior DevOps Engineer | 100 | [EMAIL] | DevOps Manager | Implementation Phase | Operations Handover | Automates migration processes and deployment pipelines following EO Framework™ methodology
EO Engineer (Support) | Operations | [COM Name] | Cloud operations setup and team preparation | Cloud operations readiness and service delivery | Operations procedures and support model | Operations readiness and service metrics | AWS operations and cloud service management | Senior Operations Manager | 80 | [EMAIL] | Operations Director | Planning Phase | Operations Established | Establishes ongoing cloud operations capability using EO Framework™ methodology
EO Delivery Engineer (Infrastructure) | Database | [DBA Name] | Database migration and cloud database optimization | Database migration success and performance | Database architecture and optimization | Database migration progress and performance metrics | AWS database services and database migration | Senior DBA | 80 | [EMAIL] | Data Manager | Migration Phase | Database Optimization Complete | Manages database migration and cloud database operations following EO Framework™ standards
EO Engineer (Security) | Security | [SE Name] | Cloud security implementation and testing | Security control implementation and validation | Security testing and compliance validation | Security implementation progress and findings | AWS security services and security testing | EO Engineer (Security) | 80 | [EMAIL] | EO Engineer (Security) | Implementation Phase | Security Validation Complete | Implements and validates cloud security controls using EO Framework™ standards
EO Sales Engineer (Business Analysis) | Financial Operations | [FA Name] | Cloud cost management and optimization | Cost optimization and financial governance | Cost optimization strategies and Reserved Instance planning | Cost metrics and optimization recommendations | AWS cost management and financial analysis | Senior FinOps Analyst | 60 | [EMAIL] | Finance Manager | Implementation Phase | Cost Optimization Complete | Manages cloud costs and financial optimization using EO Framework™ methodology
EO Engineer (Training) | Training | [TS Name] | Cloud training program delivery and enablement | Training effectiveness and cloud competency development | Training content and delivery methods | Training progress and competency achievements | AWS training and cloud operations education | Senior Training Manager | 80 | [EMAIL] | Training Director | Pre-Migration | Training Complete | Delivers comprehensive cloud training and certification programs using EO Framework™ methodology
EO Engineer (Change Management) | Change Management | [CM Name] | Migration change management and communication | User adoption and organizational change readiness | Change management strategy and communication planning | Change impacts and adoption progress | Change management and cloud adoption strategies | Senior Change Manager | 80 | [EMAIL] | Change Director | Assessment Phase | Adoption Complete | Manages organizational change and user adoption for cloud migration using EO Framework™ approach
EO Sales Engineer (Business Analysis) | Business | [BS Name] | Business requirements validation and acceptance | Business value realization and migration acceptance | Migration business impact and acceptance criteria | Migration progress and business deliverables | Business domain expertise and cloud business value | Business Manager | 30 | [EMAIL] | Business Director | Assessment Phase | Benefits Realization | Represents business interests and validates migration outcomes using EO Framework™ approach
EO Sales Engineer (Business Analysis) | Application | [AO Name] | Application-specific requirements and validation | Application migration acceptance and business validation | Application migration approach and testing | Application migration status and acceptance | Business application expertise and functional requirements | Business Process Owner | 40 | [EMAIL] | EO Sales Engineer (Business Analysis) | Assessment Phase | Application Migration Complete | Owns business applications and validates migration success using EO Framework™ methodology
EO Quarterback | Executive | [ES Name] | Strategic direction and migration investment | Migration funding and strategic business alignment | Major migration decisions and scope changes | Executive updates and milestone achievements | Executive leadership and cloud strategy | C-Level Executive | 15 | [EMAIL] | CEO/CTO | Project Start | Benefits Realization | Provides executive support and strategic guidance aligned with EO Framework™ methodology
Infrastructure Decommissioning Lead | Infrastructure | [IDL Name] | On-premise infrastructure decommissioning | Safe decommissioning and asset recovery | Decommissioning procedures and data destruction | Decommissioning progress and asset disposal | Infrastructure decommissioning and data destruction | Senior Infrastructure Manager | 60 | [EMAIL] | Infrastructure Director | Post-Migration | Decommissioning Complete | Manages safe decommissioning of on-premise infrastructure
Cloud Optimization Specialist | Optimization | [COS Name] | Post-migration cloud optimization and right-sizing | Cloud resource optimization and cost efficiency | Optimization strategies and right-sizing recommendations | Optimization progress and cost savings achieved | AWS cost optimization and resource management | Cloud Architect | 40 | [EMAIL] | FinOps Manager | Post-Migration | Optimization Complete | Optimizes cloud resources for cost and performance efficiency