## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Multi Cloud Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff | 3 days | Month 1 Week 1 | Month 1 Week 1 | None | Project Manager | Not Started
Phase 1 | Multi-Cloud Infrastructure Assessment | 10 days | Month 1 Week 1 | Month 1 Week 2 | Project Kickoff | Solution Architect | Not Started
Phase 1 | Terraform Cloud Architecture Design | 10 days | Month 1 Week 2 | Month 1 Week 4 | Assessment Complete | Solution Architect | Not Started
Phase 1 | HashiCorp Vault Architecture Design | 7 days | Month 1 Week 3 | Month 1 Week 4 | TFC Architecture | Security Architect | Not Started
Phase 1 | AWS EKS Cluster Deployment | 10 days | Month 2 Week 1 | Month 2 Week 2 | Architecture Approved | DevOps Engineer | Not Started
Phase 1 | Terraform Cloud Installation on EKS | 7 days | Month 2 Week 2 | Month 2 Week 3 | EKS Ready | DevOps Engineer | Not Started
Phase 1 | RDS PostgreSQL Backend Setup | 5 days | Month 2 Week 2 | Month 2 Week 3 | EKS Ready | DevOps Engineer | Not Started
Phase 1 | HashiCorp Vault HA Deployment | 10 days | Month 2 Week 3 | Month 3 Week 1 | TFC Operational | DevOps Engineer | Not Started
Phase 1 | VCS Integration with GitHub | 5 days | Month 2 Week 4 | Month 3 Week 1 | TFC Operational | DevOps Engineer | Not Started
Phase 1 | RBAC and SSO Configuration | 5 days | Month 3 Week 1 | Month 3 Week 2 | VCS Integration | Security Engineer | Not Started
Phase 1 | Pilot Workspace Migration (25) | 10 days | Month 3 Week 2 | Month 3 Week 4 | Platform Ready | Infrastructure Team | Not Started
Phase 1 | Pilot Validation and Testing | 5 days | Month 3 Week 4 | Month 3 Week 4 | Pilot Migration | QA Team | Not Started
Phase 2 | Sentinel Policy Framework Design | 10 days | Month 4 Week 1 | Month 4 Week 2 | Pilot Complete | Security Architect | Not Started
Phase 2 | Security Policies Development (20) | 15 days | Month 4 Week 2 | Month 4 Week 4 | Policy Framework | Security Engineer | Not Started
Phase 2 | Cost Governance Policies (15) | 10 days | Month 4 Week 3 | Month 5 Week 1 | Security Policies | Platform Engineer | Not Started
Phase 2 | Compliance Policies SOC2/ISO (15) | 10 days | Month 5 Week 1 | Month 5 Week 2 | Cost Policies | Compliance Team | Not Started
Phase 2 | Vault Dynamic Credentials - AWS | 7 days | Month 4 Week 1 | Month 4 Week 2 | Vault Operational | Security Engineer | Not Started
Phase 2 | Vault Dynamic Credentials - Azure | 7 days | Month 4 Week 2 | Month 4 Week 3 | AWS Credentials | Security Engineer | Not Started
Phase 2 | Vault Dynamic Credentials - GCP | 7 days | Month 4 Week 3 | Month 4 Week 4 | Azure Credentials | Security Engineer | Not Started
Phase 2 | Workspace Migration Wave 2 (50) | 15 days | Month 5 Week 1 | Month 5 Week 3 | Policies Ready | Infrastructure Team | Not Started
Phase 2 | Workspace Migration Wave 3 (25) | 10 days | Month 5 Week 3 | Month 6 Week 1 | Wave 2 Complete | Infrastructure Team | Not Started
Phase 2 | CI/CD Pipeline Integration | 10 days | Month 5 Week 2 | Month 5 Week 4 | Workspaces Migrated | DevOps Engineer | Not Started
Phase 2 | ServiceNow Integration | 7 days | Month 5 Week 4 | Month 6 Week 1 | CI/CD Integration | Integration Team | Not Started
Phase 2 | Policy Advisory Mode Testing | 10 days | Month 6 Week 1 | Month 6 Week 2 | All Policies | QA Team | Not Started
Phase 2 | Policy Mandatory Enforcement | 5 days | Month 6 Week 3 | Month 6 Week 4 | Advisory Testing | Security Team | Not Started
Phase 3 | Consul Service Mesh Design | 7 days | Month 7 Week 1 | Month 7 Week 2 | Phase 2 Complete | Solution Architect | Not Started
Phase 3 | Consul Deployment on EKS | 10 days | Month 7 Week 2 | Month 7 Week 4 | Consul Design | DevOps Engineer | Not Started
Phase 3 | Service Discovery Configuration | 7 days | Month 7 Week 4 | Month 8 Week 1 | Consul Deployed | Platform Engineer | Not Started
Phase 3 | Consul Connect Encryption Setup | 5 days | Month 8 Week 1 | Month 8 Week 2 | Service Discovery | Security Engineer | Not Started
Phase 3 | Drift Detection Configuration | 5 days | Month 7 Week 3 | Month 7 Week 4 | Phase 2 Complete | DevOps Engineer | Not Started
Phase 3 | Scheduled Runs Automation | 5 days | Month 7 Week 4 | Month 8 Week 1 | Drift Detection | DevOps Engineer | Not Started
Phase 3 | Monitoring Dashboard Setup | 7 days | Month 8 Week 1 | Month 8 Week 2 | Platform Complete | Operations Team | Not Started
Phase 3 | Integration Testing | 10 days | Month 8 Week 2 | Month 8 Week 4 | All Components | QA Team | Not Started
Phase 3 | Performance Testing | 7 days | Month 8 Week 3 | Month 8 Week 4 | Integration Testing | QA Team | Not Started
Phase 3 | Security Testing | 7 days | Month 8 Week 3 | Month 8 Week 4 | Integration Testing | Security Team | Not Started
Phase 3 | User Acceptance Testing | 10 days | Month 8 Week 4 | Month 9 Week 2 | All Testing | Business Users | Not Started
Phase 4 | Administrator Training | 5 days | Month 9 Week 1 | Month 9 Week 2 | UAT Complete | Training Team | Not Started
Phase 4 | Operator Training | 3 days | Month 9 Week 2 | Month 9 Week 2 | Admin Training | Training Team | Not Started
Phase 4 | Documentation Delivery | 5 days | Month 9 Week 2 | Month 9 Week 3 | Training Complete | Project Manager | Not Started
Phase 4 | Go-Live Preparation | 3 days | Month 9 Week 3 | Month 9 Week 3 | Documentation | Operations Team | Not Started
Phase 4 | Production Go-Live | 2 days | Month 9 Week 4 | Month 9 Week 4 | Go-Live Prep | Project Manager | Not Started
Phase 4 | Hypercare Support | 30 days | Month 10 Week 1 | Month 10 Week 4 | Go-Live | Support Team | Not Started
Phase 4 | Project Closure | 3 days | Month 10 Week 4 | Month 10 Week 4 | Hypercare Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | Month 1 Week 1 | Stakeholder alignment complete and project charter signed | Project Manager | Not Started
M2 | Assessment Complete | Month 1 Week 2 | Multi-cloud infrastructure documented with 100+ workspace inventory | Solution Architect | Not Started
M3 | Terraform Cloud Operational | Month 2 Week 3 | Platform deployed on EKS with VCS integration functional | DevOps Engineer | Not Started
M4 | Pilot Workspaces Migrated | Month 3 Week 4 | 25 workspaces migrated with state validation complete | Infrastructure Team | Not Started
M5 | Vault Integration Complete | Month 4 Week 4 | Dynamic credentials operational for AWS Azure GCP | Security Engineer | Not Started
M6 | Sentinel Policies Deployed | Month 6 Week 4 | 50 policies enforced across all workspaces with 95%+ compliance | Security Team | Not Started
M7 | 100 Workspaces Migrated | Month 6 Week 1 | All workspaces migrated with policy enforcement active | Infrastructure Team | Not Started
M8 | Consul Service Mesh Live | Month 8 Week 2 | Cross-cloud service discovery and Connect operational | DevOps Engineer | Not Started
M9 | Go-Live | Month 9 Week 4 | Full platform operational with all capabilities enabled | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | SecArch | DevOps | Infra | QA | Ops | Client
Project Charter and Kickoff | A | C | C | I | I | I | I | C
Multi-Cloud Assessment | C | R | C | C | A | I | I | C
Terraform Cloud Architecture | A | R | C | C | I | I | I | I
Vault Architecture Design | A | C | R | C | I | I | I | C
EKS Cluster Deployment | A | C | I | R | C | I | I | I
Terraform Cloud Installation | A | C | I | R | I | I | C | I
HashiCorp Vault Deployment | A | C | R | A | I | I | I | C
VCS and SSO Integration | A | C | C | R | I | I | I | C
Pilot Workspace Migration | A | C | I | C | R | C | I | I
Sentinel Policy Development | A | C | R | C | I | C | I | C
Dynamic Credentials Setup | A | I | R | A | I | I | I | C
Full Workspace Migration | A | C | I | C | R | C | I | I
CI/CD Pipeline Integration | A | C | I | R | C | I | I | I
Consul Service Mesh Deployment | A | R | C | A | I | I | I | I
Integration Testing | A | C | C | C | C | R | I | I
Security Testing | A | I | A | C | I | R | I | C
User Acceptance Testing | A | I | I | I | I | C | I | R
Administrator Training | A | C | C | R | I | I | C | C
Documentation Delivery | A | R | C | C | C | I | C | I
Go-Live Deployment | A | C | C | R | C | I | A | C
Hypercare Support | A | C | C | R | C | I | A | I
Project Closure | R | C | I | I | I | I | I | A
Legend:
R | C A A A A A A A A A A A A A A A A A A A R: Responsible - Does the work
A | C A A A A A A A A A A A A A A A A A A A R: Accountable - Ultimate ownership
C | C A A A A A A A A A A A A A A A A A A A R: Consulted - Provides input
I | C A A A A A A A A A A A A A A A A A A A R: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on objectives | Project Manager | Day 1
Steering Committee | Monthly | Executive sponsors and PMO | Strategic direction and issue escalation | Project Manager | First Monday
Project Status | Weekly | Core project team | Review progress risks and blockers | Project Manager | Mondays 10:00
Technical Review | Weekly | Technical leads and architects | Architecture decisions and technical issues | Solution Architect | Wednesdays 14:00
Security Review | Bi-weekly | Security team and architects | Security controls and compliance validation | Security Architect | Alternate Thursdays
Migration Checkpoint | Weekly | Migration team | Workspace migration progress and validation | Infrastructure Lead | Tuesdays 11:00
Policy Review | Bi-weekly | Security and DevOps teams | Sentinel policy effectiveness and tuning | Security Engineer | Alternate Fridays
Training Sessions | As scheduled | End users and administrators | Platform training delivery | Training Team | As scheduled
Go-Live Readiness | Daily (pre-launch) | Go-live team | Go-live preparation and checklist review | Project Manager | Daily 09:00
Hypercare Standup | Daily (post-launch) | Support team | Issue triage and resolution tracking | Support Lead | Daily 09:00