## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Terraform Enterprise
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Phase 1 | Project Kickoff | 3 days | Month 1 Week 1 | Month 1 Week 1 | None | Project Manager | Not Started
Phase 1 | Terraform OSS Assessment | 7 days | Month 1 Week 1 | Month 1 Week 2 | Project Kickoff | Solution Architect | Not Started
Phase 1 | TFE Architecture Design | 7 days | Month 1 Week 2 | Month 1 Week 3 | Assessment Complete | Solution Architect | Not Started
Phase 1 | AWS Infrastructure Setup | 5 days | Month 1 Week 3 | Month 1 Week 4 | Architecture Approved | DevOps Engineer | Not Started
Phase 1 | EKS Cluster Deployment | 7 days | Month 1 Week 4 | Month 2 Week 1 | AWS Infra Ready | DevOps Engineer | Not Started
Phase 1 | RDS PostgreSQL Setup | 5 days | Month 2 Week 1 | Month 2 Week 2 | EKS Ready | DevOps Engineer | Not Started
Phase 1 | Terraform Enterprise Installation | 5 days | Month 2 Week 2 | Month 2 Week 2 | RDS Ready | DevOps Engineer | Not Started
Phase 1 | VCS Integration with GitHub | 3 days | Month 2 Week 3 | Month 2 Week 3 | TFE Operational | DevOps Engineer | Not Started
Phase 1 | RBAC Configuration | 3 days | Month 2 Week 3 | Month 2 Week 4 | VCS Integration | Security Engineer | Not Started
Phase 1 | Pilot Workspace Migration (10) | 5 days | Month 2 Week 4 | Month 3 Week 1 | Platform Ready | Infrastructure Team | Not Started
Phase 1 | Development Workspace Migration (20) | 7 days | Month 3 Week 1 | Month 3 Week 2 | Pilot Complete | Infrastructure Team | Not Started
Phase 1 | Staging Workspace Migration (10) | 5 days | Month 3 Week 2 | Month 3 Week 3 | Dev Migration | Infrastructure Team | Not Started
Phase 1 | Production Workspace Migration (10) | 7 days | Month 3 Week 3 | Month 3 Week 4 | Staging Migration | Infrastructure Team | Not Started
Phase 2 | Sentinel Policy Framework Design | 5 days | Month 3 Week 4 | Month 4 Week 1 | Workspaces Migrated | Security Architect | Not Started
Phase 2 | Security Policies Development (18) | 10 days | Month 4 Week 1 | Month 4 Week 3 | Policy Framework | Security Engineer | Not Started
Phase 2 | Cost Governance Policies (12) | 7 days | Month 4 Week 2 | Month 4 Week 3 | Security Policies | Platform Engineer | Not Started
Phase 2 | Compliance Policies SOC2/ISO (10) | 7 days | Month 4 Week 3 | Month 4 Week 4 | Cost Policies | Compliance Team | Not Started
Phase 2 | HashiCorp Vault Integration | 10 days | Month 4 Week 1 | Month 4 Week 3 | TFE Operational | Security Engineer | Not Started
Phase 2 | Dynamic AWS Credentials Config | 5 days | Month 4 Week 3 | Month 4 Week 4 | Vault Integrated | Security Engineer | Not Started
Phase 2 | Private Module Registry Setup | 5 days | Month 4 Week 4 | Month 5 Week 1 | TFE Operational | DevOps Engineer | Not Started
Phase 2 | Module Development (15 modules) | 10 days | Month 5 Week 1 | Month 5 Week 3 | Registry Ready | Platform Engineer | Not Started
Phase 2 | CI/CD Pipeline Integration | 7 days | Month 5 Week 1 | Month 5 Week 2 | Workspaces Ready | DevOps Engineer | Not Started
Phase 2 | Policy Advisory Mode Testing | 5 days | Month 5 Week 2 | Month 5 Week 3 | All Policies Ready | QA Team | Not Started
Phase 2 | Policy Mandatory Enforcement | 3 days | Month 5 Week 3 | Month 5 Week 4 | Advisory Testing | Security Team | Not Started
Phase 3 | Self-Service Workflow Config | 5 days | Month 5 Week 4 | Month 6 Week 1 | Policies Enforced | Platform Engineer | Not Started
Phase 3 | Approval Gates Setup | 3 days | Month 6 Week 1 | Month 6 Week 1 | Self-Service Config | Platform Engineer | Not Started
Phase 3 | Drift Detection Configuration | 3 days | Month 6 Week 1 | Month 6 Week 2 | Platform Complete | DevOps Engineer | Not Started
Phase 3 | Cost Estimation Integration | 3 days | Month 6 Week 1 | Month 6 Week 2 | Platform Complete | Platform Engineer | Not Started
Phase 3 | Monitoring Dashboard Setup | 5 days | Month 6 Week 1 | Month 6 Week 2 | Platform Complete | Operations Team | Not Started
Phase 3 | Integration Testing | 5 days | Month 6 Week 2 | Month 6 Week 3 | All Components | QA Team | Not Started
Phase 3 | User Acceptance Testing | 5 days | Month 6 Week 3 | Month 6 Week 3 | Integration Testing | Business Users | Not Started
Phase 3 | Administrator Training | 3 days | Month 6 Week 3 | Month 6 Week 4 | UAT Complete | Training Team | Not Started
Phase 3 | Documentation Delivery | 3 days | Month 6 Week 4 | Month 6 Week 4 | Training Complete | Project Manager | Not Started
Phase 3 | Go-Live | 2 days | Month 6 Week 4 | Month 6 Week 4 | All Complete | Project Manager | Not Started
Phase 4 | Hypercare Support | 30 days | Month 7 Week 1 | Month 7 Week 4 | Go-Live | Support Team | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | Month 1 Week 1 | Stakeholder alignment complete and project charter signed | Project Manager | Not Started
M2 | Assessment Complete | Month 1 Week 2 | Terraform OSS inventory documented with 50 workspaces identified | Solution Architect | Not Started
M3 | TFE Operational | Month 2 Week 2 | Platform deployed on EKS with VCS integration functional | DevOps Engineer | Not Started
M4 | 50 Workspaces Migrated | Month 3 Week 4 | All workspaces migrated with state validation complete | Infrastructure Team | Not Started
M5 | Sentinel Policies Deployed | Month 5 Week 4 | 40 policies enforced across all workspaces with 100% compliance | Security Team | Not Started
M6 | Vault Integration Complete | Month 4 Week 4 | Dynamic AWS credentials operational for all workspaces | Security Engineer | Not Started
M7 | Private Registry Operational | Month 5 Week 3 | 15 modules published and available for workspace consumption | DevOps Engineer | Not Started
M8 | Go-Live | Month 6 Week 4 | Full platform operational with self-service and governance enabled | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | SecArch | DevOps | Infra | QA | Ops | Client
Project Charter and Kickoff | A | C | C | I | I | I | I | C
Terraform OSS Assessment | C | R | C | C | A | I | I | C
TFE Architecture Design | A | R | C | C | I | I | I | I
AWS Infrastructure Setup | A | C | I | R | C | I | I | I
EKS and RDS Deployment | A | C | I | R | I | I | C | I
Terraform Enterprise Installation | A | C | I | R | I | I | I | I
VCS Integration | A | C | I | R | I | I | I | C
RBAC Configuration | A | C | R | A | I | I | I | C
Workspace Migration | A | C | I | C | R | C | I | I
Sentinel Policy Development | A | C | R | C | I | C | I | C
Vault Integration | A | I | R | A | I | I | I | C
Private Module Registry | A | C | I | R | C | I | I | I
CI/CD Pipeline Integration | A | C | I | R | C | I | I | I
Integration Testing | A | C | C | C | C | R | I | I
User Acceptance Testing | A | I | I | I | I | C | I | R
Administrator Training | A | C | C | R | I | I | C | C
Documentation Delivery | A | R | C | C | C | I | C | I
Go-Live Deployment | A | C | C | R | C | I | A | C
Hypercare Support | A | C | C | R | C | I | A | I
Legend:
R | C A A A A A A A A A A A A A A A A A: Responsible - Does the work
A | C A A A A A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | C A A A A A A A A A A A A A A A A A: Consulted - Provides input
I | C A A A A A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on objectives | Project Manager | Day 1
Steering Committee | Monthly | Executive sponsors and PMO | Strategic direction and issue escalation | Project Manager | First Monday
Project Status | Weekly | Core project team | Review progress risks and blockers | Project Manager | Mondays 10:00
Technical Review | Weekly | Technical leads and architects | Architecture decisions and technical issues | Solution Architect | Wednesdays 14:00
Migration Checkpoint | Weekly | Migration team | Workspace migration progress and validation | Infrastructure Lead | Tuesdays 11:00
Policy Review | Bi-weekly | Security and DevOps teams | Sentinel policy effectiveness and tuning | Security Engineer | Alternate Fridays
Training Sessions | As scheduled | End users and administrators | Platform training delivery | Training Team | As scheduled
Hypercare Standup | Daily (post-launch) | Support team | Issue triage and resolution tracking | Support Lead | Daily 09:00