## Cover
Test Plan
Generated: | November 28, 2025
Solution: | Terraform Enterprise
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Category | Test Type | Test Name | Description | Pre-conditions | Expected Results | Priority | Environment | Assigned Tester | Status | Pass/Fail | Notes | Requirements Traced
FT-001 | Platform | Integration | VCS Integration | Verify GitHub webhook triggers TFE runs on commit | TFE operational and GitHub connected | Commit triggers plan within 30 seconds | High | Staging | Platform Team | Not Started |  | Validate webhook delivery | SOW-VCS-001
FT-002 | Platform | Integration | Workspace State Management | Verify state locking prevents concurrent modifications | Workspace with active run | Second run queues until first completes | High | Staging | Platform Team | Not Started |  | Test concurrent run handling | SOW-STATE-001
FT-003 | Platform | Functional | Remote State Migration | Verify state migration from S3/local to TFE | Existing state file available | State migrated with zero resource drift | Critical | Staging | Migration Team | Not Started |  | Validate resource count | SOW-MIGRATE-001
FT-004 | Vault | Integration | Dynamic AWS Credentials | Verify Vault generates valid AWS credentials | Vault AWS secrets engine configured | Credentials valid for AWS API calls | Critical | Staging | Security Team | Not Started |  | Test credential generation | SOW-VAULT-001
FT-005 | Sentinel | Functional | Security Policy Enforcement | Verify security policies block non-compliant infra | Security policy set attached to workspace | Non-compliant plan fails policy check | Critical | Staging | Security Team | Not Started |  | Test encryption rules | SOW-POLICY-001
FT-006 | Sentinel | Functional | Cost Policy Enforcement | Verify cost policies prevent over-provisioning | Cost policy set attached to workspace | Oversized resources fail policy check | High | Staging | Platform Team | Not Started |  | Test instance sizing | SOW-POLICY-002
FT-007 | Sentinel | Functional | Tagging Policy Enforcement | Verify tagging policies require mandatory tags | Tagging policy set active | Resources without tags fail policy | High | Staging | Platform Team | Not Started |  | Test required tags | SOW-POLICY-003
FT-008 | Platform | Functional | Self-Service Workspace Creation | Verify operators can create workspaces via UI | Operator role assigned to user | Workspace created with proper settings | Medium | Staging | Platform Team | Not Started |  | Test RBAC | SOW-RBAC-001
FT-009 | Platform | Functional | Approval Gate Workflow | Verify production changes require approval | Approval gate configured on workspace | Run requires explicit approval to apply | High | Staging | Platform Team | Not Started |  | Test approval flow | SOW-APPROVE-001
FT-010 | Platform | Integration | Slack Notification Integration | Verify run status notifications sent to Slack | Slack webhook configured | Run status posted to channel | Medium | Staging | Platform Team | Not Started |  | Test notification content | SOW-INT-001
FT-011 | Registry | Functional | Module Publishing | Verify modules publish to private registry | Module in connected repository | Module available with version in registry | Medium | Staging | Platform Team | Not Started |  | Test module publish | SOW-MODULE-001
FT-012 | Registry | Functional | Module Consumption | Verify workspaces can consume private modules | Module published to registry | Workspace can reference private module | Medium | Staging | Platform Team | Not Started |  | Test module usage | SOW-MODULE-002
FT-013 | Platform | Functional | Cost Estimation | Verify cost estimation displays change costs | Workspace with AWS provider | Cost estimate shown before apply | Medium | Staging | Platform Team | Not Started |  | Test cost accuracy | SOW-COST-001
FT-014 | Platform | Functional | Drift Detection | Verify drift detection identifies manual changes | Resource modified outside Terraform | Drift detected and reported | Medium | Staging | Platform Team | Not Started |  | Test drift accuracy | SOW-DRIFT-001
FT-015 | Platform | Functional | Run Triggers | Verify run triggers chain workspace executions | Run trigger configured between workspaces | Source workspace triggers target | Medium | Staging | Platform Team | Not Started |  | Test trigger chain | SOW-TRIGGER-001
FT-016 | Platform | Functional | Variable Management | Verify sensitive variables masked in logs | Sensitive variable configured | Variable value not visible in run logs | High | Staging | Security Team | Not Started |  | Test masking | SOW-VAR-001
FT-017 | Platform | Integration | CI/CD Pipeline Integration | Verify GitHub Actions can trigger TFE runs | GitHub Actions workflow configured | Pipeline triggers TFE run via API | High | Staging | DevOps Team | Not Started |  | Test API integration | SOW-CICD-001
FT-018 | Platform | Functional | AWS Infrastructure Provisioning | Verify TFE can provision AWS resources | Workspace with AWS provider and credentials | AWS resources created successfully | Critical | Staging | Platform Team | Not Started |  | Test provisioning | SOW-AWS-001

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Category | Test Type | Test Name | Description | Pre-conditions | Expected Results | Priority | Environment | Assigned Tester | Status | Pass/Fail | Notes | Requirements Traced
NFT-001 | Performance | Load | Concurrent Run Capacity | Verify platform handles 10 concurrent runs | Platform operational with test workspaces | 10 runs execute without queue timeout | Critical | Performance | QA Team | Not Started |  | Test run queue capacity | SOW-PERF-001
NFT-002 | Performance | Load | Vault Credential Generation | Verify Vault handles credential requests under load | Vault operational with AWS secrets engine | 50 credential requests per minute | High | Performance | Security Team | Not Started |  | Test Vault throughput | SOW-PERF-002
NFT-003 | Performance | Response | API Response Time | Verify API response times meet SLA | Platform under normal load | API responses under 2 seconds p95 | High | Performance | QA Team | Not Started |  | Test API latency | SOW-PERF-003
NFT-004 | Performance | Load | State File Operations | Verify large state file operations complete | Workspace with 200+ resources | State operations complete under 30 seconds | Medium | Performance | QA Team | Not Started |  | Test state handling | SOW-PERF-004
NFT-005 | Availability | Failover | EKS Node Failure Recovery | Verify platform recovers from node failure | Platform operational on 3-node EKS | Service restored within 5 minutes | Critical | DR | Operations Team | Not Started |  | Test EKS auto-healing | SOW-HA-001
NFT-006 | Availability | Failover | RDS Failover | Verify RDS fails over to standby | RDS Multi-AZ operational | Database available within 2 minutes | Critical | DR | Operations Team | Not Started |  | Test RDS failover | SOW-HA-002
NFT-007 | Security | Penetration | Platform Security Assessment | Verify platform security controls | Platform operational with auth | No critical vulnerabilities identified | Critical | Security | Security Team | Not Started |  | External security scan | SOW-SEC-001
NFT-008 | Security | Access | RBAC Enforcement | Verify role permissions enforced | Users with different roles | Users can only access permitted resources | Critical | Staging | Security Team | Not Started |  | Test role boundaries | SOW-SEC-002
NFT-009 | Security | Audit | Audit Log Completeness | Verify all actions logged | Platform operational with users | All authentication and changes logged | High | Staging | Security Team | Not Started |  | Test audit coverage | SOW-SEC-003
NFT-010 | Security | Encryption | Data Encryption Validation | Verify encryption at rest and in transit | Platform operational | All data encrypted per policy | Critical | Staging | Security Team | Not Started |  | Test TLS and KMS | SOW-SEC-004
NFT-011 | Disaster Recovery | Backup | Backup and Restore | Verify backup and restore procedures | Backups configured and running | Full restore completes within RTO | High | DR | Operations Team | Not Started |  | Test DR procedures | SOW-DR-001
NFT-012 | Scalability | Scale | Workspace Scaling | Verify platform scales to 50+ workspaces | Platform with initial workspaces | 50 workspaces operational | High | Performance | QA Team | Not Started |  | Test workspace limits | SOW-SCALE-001
NFT-013 | Compliance | Audit | SOC2 Control Validation | Verify SOC2 controls implemented | Platform operational | All SOC2 controls pass audit | High | Production | Compliance Team | Not Started |  | Map controls | SOW-COMP-001
NFT-014 | Compliance | Audit | ISO27001 Control Validation | Verify ISO27001 controls implemented | Platform operational | All ISO27001 controls pass audit | High | Production | Compliance Team | Not Started |  | Map controls | SOW-COMP-002
NFT-015 | Monitoring | Alerting | Alert Configuration Validation | Verify alerts trigger appropriately | Monitoring configured with alerts | Alerts fire for simulated conditions | Medium | Staging | Operations Team | Not Started |  | Test alert accuracy | SOW-MON-001
NFT-016 | Performance | Response | Plan Execution Time | Verify plan execution meets targets | Workspace with typical configuration | Plan completes under 3 minutes | Medium | Performance | QA Team | Not Started |  | Test plan speed | SOW-PERF-005

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Category | Test Type | Test Name | Description | Pre-conditions | Expected Results | Priority | Environment | Assigned Tester | Status | Pass/Fail | Notes | Requirements Traced
UAT-001 | Workflow | End-to-End | Infrastructure Provisioning Workflow | Verify complete workflow from code commit to resource | VCS connected and policies active | Infrastructure provisioned via GitOps | Critical | UAT | DevOps Team | Not Started |  | Test full flow | SOW-UAT-001
UAT-002 | Workflow | End-to-End | Self-Service Workspace Creation | Verify operators can self-serve workspace creation | Operator role and training complete | Workspace created without admin help | High | UAT | Infrastructure Team | Not Started |  | Test self-service | SOW-UAT-002
UAT-003 | Workflow | End-to-End | Dynamic Credential Workflow | Verify dynamic credentials accessible in runs | Vault integration active | Terraform run uses dynamic credentials | Critical | UAT | DevOps Team | Not Started |  | Test credentials | SOW-UAT-003
UAT-004 | Workflow | End-to-End | Policy Violation Handling | Verify users understand policy failure feedback | Sentinel policies active | Users can interpret and fix violations | High | UAT | DevOps Team | Not Started |  | Test policy feedback | SOW-UAT-004
UAT-005 | Workflow | End-to-End | Production Change Approval | Verify approval workflow for production changes | Approval gates active | Change approved before apply | Critical | UAT | Operations Team | Not Started |  | Test approval workflow | SOW-UAT-005
UAT-006 | Operations | End-to-End | Run Troubleshooting | Verify operators can diagnose failed runs | Operator access and training | Issue identified from logs and state | High | UAT | Operations Team | Not Started |  | Test troubleshooting | SOW-UAT-006
UAT-007 | Operations | End-to-End | State Recovery | Verify state recovery from previous version | State versioning active | State recovered from previous version | High | UAT | Operations Team | Not Started |  | Test recovery | SOW-UAT-007
UAT-008 | Governance | End-to-End | Compliance Reporting | Verify compliance reports generated | Sentinel policies and dashboards | Compliance status visible in dashboard | Medium | UAT | Compliance Team | Not Started |  | Test reporting | SOW-UAT-008
UAT-009 | Governance | End-to-End | Cost Visibility | Verify cost estimation accuracy | Cost policies active | Cost estimates match actual spend | Medium | UAT | Finance Team | Not Started |  | Test cost estimation | SOW-UAT-009
UAT-010 | Registry | End-to-End | Module Usage Workflow | Verify teams can use private modules | Module registry operational | Teams can discover and use modules | Medium | UAT | DevOps Team | Not Started |  | Test module workflow | SOW-UAT-010
UAT-011 | Training | Validation | Administrator Competency | Verify admins can perform all platform tasks | Admin training complete | All admin tasks completed independently | High | UAT | IT Team | Not Started |  | Competency test | SOW-UAT-011
UAT-012 | Training | Validation | Operator Competency | Verify operators can perform daily tasks | Operator training complete | All operator tasks completed | High | UAT | DevOps Team | Not Started |  | Competency test | SOW-UAT-012