## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Ci Cd Automation
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | EO Project Manager | Not Started
Discovery | Network Automation Assessment | 4 days | [START_DATE+1] | [START_DATE+5] | Project Kickoff | EO DevOps Architect | Not Started
Discovery | CI/CD Tool Inventory | 3 days | [START_DATE+3] | [START_DATE+6] | Network Assessment | EO DevOps Engineer | Not Started
Discovery | Cisco Platform Evaluation | 4 days | [START_DATE+5] | [START_DATE+9] | Tool Inventory | EO DevOps Architect | Not Started
Discovery | Gap Analysis and Design | 3 days | [START_DATE+8] | [START_DATE+11] | Platform Evaluation | EO DevOps Architect | Not Started
Foundation | Cisco DNA Center Setup | 4 days | [START_DATE+11] | [START_DATE+15] | Discovery Complete | EO DevOps Engineer | Not Started
Foundation | Cisco NSO Configuration | 5 days | [START_DATE+14] | [START_DATE+19] | DNA Center Setup | EO DevOps Engineer | Not Started
Foundation | GitLab Enterprise Integration | 4 days | [START_DATE+18] | [START_DATE+22] | NSO Configuration | EO DevOps Engineer | Not Started
Foundation | API Framework Development | 5 days | [START_DATE+21] | [START_DATE+26] | GitLab Integration | EO DevOps Engineer | Not Started
Foundation | Security Framework Setup | 3 days | [START_DATE+25] | [START_DATE+28] | API Framework | EO Security Engineer | Not Started
Automation | Terraform Module Development | 6 days | [START_DATE+28] | [START_DATE+34] | Foundation Complete | EO DevOps Engineer | Not Started
Automation | Ansible Playbook Library | 6 days | [START_DATE+32] | [START_DATE+38] | Terraform Modules | EO DevOps Engineer | Not Started
Automation | CI/CD Pipeline Development | 5 days | [START_DATE+36] | [START_DATE+41] | Ansible Playbooks | EO DevOps Engineer | Not Started
Automation | Self-Service Portal Build | 4 days | [START_DATE+40] | [START_DATE+44] | Pipeline Development | EO DevOps Engineer | Not Started
Automation | Testing Framework Setup | 3 days | [START_DATE+43] | [START_DATE+46] | Portal Build | EO QA Engineer | Not Started
Integration | Network Device Onboarding | 5 days | [START_DATE+46] | [START_DATE+51] | Automation Complete | EO Network Engineer | Not Started
Integration | Application Team Onboarding | 6 days | [START_DATE+50] | [START_DATE+56] | Device Onboarding | EO DevOps Engineer | Not Started
Integration | SIEM and Monitoring Integration | 3 days | [START_DATE+54] | [START_DATE+57] | Team Onboarding | EO Security Engineer | Not Started
Integration | ITSM Workflow Integration | 3 days | [START_DATE+56] | [START_DATE+59] | SIEM Integration | EO DevOps Engineer | Not Started
Testing | Functional Testing | 4 days | [START_DATE+59] | [START_DATE+63] | Integration Complete | EO QA Engineer | Not Started
Testing | Performance Testing | 3 days | [START_DATE+62] | [START_DATE+65] | Functional Testing | EO QA Engineer | Not Started
Testing | Security Testing | 3 days | [START_DATE+64] | [START_DATE+67] | Performance Testing | EO Security Engineer | Not Started
Testing | User Acceptance Testing | 4 days | [START_DATE+66] | [START_DATE+70] | Security Testing | Client DevOps Team | Not Started
Rollout | Pilot Team Deployment (2 teams) | 3 days | [START_DATE+70] | [START_DATE+73] | Testing Complete | EO DevOps Engineer | Not Started
Rollout | Wave 1: 5 Teams | 4 days | [START_DATE+73] | [START_DATE+77] | Pilot Complete | EO DevOps Engineer | Not Started
Rollout | Wave 2: 8 Teams | 4 days | [START_DATE+77] | [START_DATE+81] | Wave 1 Complete | EO DevOps Engineer | Not Started
Training | Network Engineer Training | 8 hours | [START_DATE+78] | [START_DATE+79] | Wave 1 Complete | EO DevOps Architect | Not Started
Training | DevOps Engineer Training | 8 hours | [START_DATE+79] | [START_DATE+80] | Network Training | EO DevOps Architect | Not Started
Training | Developer Training | 4 hours | [START_DATE+80] | [START_DATE+81] | DevOps Training | EO DevOps Engineer | Not Started
Training | Operations Training | 8 hours | [START_DATE+81] | [START_DATE+82] | Developer Training | EO DevOps Architect | Not Started
Go-Live | Production Go-Live | 2 days | [START_DATE+82] | [START_DATE+84] | Training Complete | EO Project Manager | Not Started
Support | Hypercare Week 1 | 7 days | [START_DATE+84] | [START_DATE+91] | Go-Live | EO DevOps Engineer | Not Started
Support | Hypercare Week 2 | 7 days | [START_DATE+91] | [START_DATE+98] | Hypercare Week 1 | EO DevOps Engineer | Not Started
Closure | Pipeline Optimization | 3 days | [START_DATE+95] | [START_DATE+98] | Hypercare Week 2 | EO DevOps Architect | Not Started
Closure | Knowledge Transfer | 2 days | [START_DATE+98] | [START_DATE+100] | Optimization | EO Project Manager | Not Started
Closure | Documentation Delivery | 2 days | [START_DATE+100] | [START_DATE+102] | Knowledge Transfer | EO DevOps Architect | Not Started
Closure | Project Closure | 1 day | [START_DATE+102] | [START_DATE+103] | Documentation | EO Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Design Complete | [START_DATE+11] | Automation architecture approved; Platform integrations designed; Pipeline framework defined | EO DevOps Architect | Not Started
M2 | Platform Deployed | [START_DATE+28] | DNA Center configured; NSO operational; GitLab integrated; API framework ready | EO DevOps Engineer | Not Started
M3 | Automation Complete | [START_DATE+46] | 50 Ansible playbooks; 25 Terraform modules; 15 CI/CD pipelines; Self-service portal live | EO DevOps Engineer | Not Started
M4 | Integration Complete | [START_DATE+59] | 200+ devices onboarded; 15 teams integrated; SIEM connected; ITSM workflows active | EO DevOps Engineer | Not Started
M5 | Testing Complete | [START_DATE+70] | Functional tests passed; Performance validated; Security cleared; UAT approved | EO QA Engineer | Not Started
M6 | Go-Live | [START_DATE+84] | All teams onboarded; Production operational; 24/7 monitoring active | EO Project Manager | Not Started
M7 | Hypercare Complete | [START_DATE+103] | Support transition done; Teams trained (2400 hrs); Documentation delivered | EO Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | DevArch | DevEng | NetEng | SecEng | QA | AppTeams | Client
Project Charter and Kickoff | A | C | I | I | I | I | I | C
Automation Architecture Design | A | R | C | C | C | I | I | I
Cisco DNA Center Configuration | A | C | R | C | I | I | I | I
Cisco NSO Setup | A | C | R | C | I | I | I | I
GitLab Enterprise Integration | A | C | R | I | I | I | I | I
API Framework Development | A | C | R | I | I | I | I | I
Terraform Module Library | A | C | R | I | I | I | I | I
Ansible Playbook Development | A | C | R | C | I | I | I | I
CI/CD Pipeline Configuration | A | C | R | I | I | C | I | I
Self-Service Portal Development | A | C | R | I | I | I | C | I
Network Device Onboarding | A | C | C | R | I | I | I | I
Application Team Integration | A | C | R | I | I | I | R | I
Security Integration | A | C | C | I | R | I | I | I
SIEM and Monitoring Setup | A | C | C | I | R | I | I | I
Functional Testing | A | I | C | C | I | R | I | I
Performance Testing | A | I | C | I | I | R | I | I
Security Testing | A | I | C | I | R | C | I | I
User Acceptance Testing | A | I | C | I | I | C | R | A
Team Training Delivery | A | R | C | C | C | I | I | I
Production Go-Live | A | C | R | C | C | C | I | R
Hypercare Support | A | C | R | C | C | C | I | I
Knowledge Transfer | A | R | C | C | C | I | I | C
Documentation Delivery | A | R | C | C | C | I | I | I
Legend:
R | A A A A A A A A A A A A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on DevOps automation objectives | EO Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and IT leadership | Strategic direction and automation investment decisions | EO Project Manager | Alternate Tuesdays
Project Status Meeting | Weekly | Core project team | Review progress and address blockers across workstreams | EO Project Manager | Mondays 10:00
Architecture Review | Weekly | DevOps and network architects | Automation architecture decisions and platform design | EO DevOps Architect | Wednesdays 14:00
Pipeline Development Standup | Daily | Development team | Pipeline development progress and technical issues | EO DevOps Engineer | Daily 09:30
Integration Sync | Weekly | Integration and app teams | Application team onboarding progress and issues | EO DevOps Engineer | Thursdays 11:00
Security Review | Bi-weekly | Security and DevOps teams | Security controls and compliance validation | EO Security Engineer | Alternate Fridays
Training Coordination | Weekly | Training and operations | Training schedule and competency tracking | EO Project Manager | Fridays 14:00
Risk and Issue Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | EO Project Manager | Alternate Fridays
Go-Live Readiness | Daily (2 wks pre) | Go-live team | Deployment preparation and rollout checklist | EO Project Manager | Daily 09:00
Hypercare Review | Daily (hypercare) | Support and operations | Production stability and issue resolution | EO DevOps Engineer | Daily 10:00
Project Closeout | Once | All stakeholders | Hypercare completion and operational handoff | EO Project Manager | Week 15