## Cover
[DOCUMENT TITLE]
Level of Effort
GOOGLE - Cloud - Landing Zone
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Number of GCP Projects | 10 projects managed | 10 projects | 30 projects | 75+ projects | Projects within landing zone organization
Solution Scope | Team Count | 5 application teams | 3-5 teams | 6-15 teams | 20+ teams | Teams using the platform
Integration | Hybrid Connectivity | Dedicated Interconnect 10 Gbps | Cloud VPN 1 Gbps | Interconnect 10 Gbps | Interconnect 100 Gbps | On-premises connectivity bandwidth
Integration | Network Architecture | Shared VPC hub-spoke | Single hub-spoke | Multi-hub regional | Global multi-region | Network complexity and scale
User Base | Platform Admins | 8 administrators | 5-8 admins | 10-15 admins | 20+ admins | Cloud platform operations team
User Base | Folder Structure | By environment (dev/staging/prod) | Simple structure | Multi-level hierarchy | Complex matrix structure | Organization folder design
Data Volume | Logging Volume | 500 GB/month centralized | 500 GB/month | 2 TB/month | 10+ TB/month | Cloud Logging ingestion volume
Data Volume | Project Provisioning | Manual with Terraform modules | Manual provisioning | Self-service with approval | Fully automated platform | Project creation approach
Technical Environment | Deployment Regions | 3 GCP regions (multi-regional) | Single region | 2-3 regions | Global multi-region | Geographic distribution
Technical Environment | Availability Requirements | Standard (99.9%) | Standard (99.9%) | High availability (99.95%) | Mission critical (99.99%+) | Platform SLA requirements
Technical Environment | Infrastructure Complexity | Hub-spoke VPC with Interconnect | Basic networking | Standard hub-spoke | Complex multi-cloud hybrid | GCP landing zone architecture
Security & Compliance | Security Requirements | SCC Premium Chronicle SIEM | Basic security | Industry standard (SOC2) | Advanced (FedRAMP multi-jurisdiction) | Security monitoring and controls
Security & Compliance | Compliance Frameworks | SOC 2 PCI-DSS | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Regulatory compliance requirements
Performance | Project Provisioning Time | 1 hour with automation | Manual (days) | Automated (hours) | Self-service (minutes) | Project deployment speed
Performance | Security Baseline | Cloud Foundation Toolkit | Basic baseline | Standard baseline | Advanced custom baseline | Security control enforcement
Environment | Shared Services | Logging Monitoring Security VPN | Basic services | Standard services | Comprehensive platform | Centralized service offerings

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Environment Assessment, GCP Services Assessment, Compliance Review)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Landing Zone Design, Identity and Access Design, Network Architecture Design, Project Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Organization Setup, Cloud Foundation Toolkit, Network Infrastructure, Security Baseline, Monitoring Setup)
Testing | TESTING_MX | 1 | All Testing phase tasks (Infrastructure Testing, Policy Testing, Security Testing, Automation Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Foundation Deployment, Team Onboarding, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Platform User Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, FinOps Setup)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 20% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 25% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews for GCP landing zone requirements | EO Engineer | 40 |  |  | 200 |  |  | Includes organization structure governance and team requirements
Discovery | Environment Assessment | Analyze existing GCP setup and on-premises infrastructure | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide GCP Organization ID and current project inventory
Discovery | GCP Services Assessment | Evaluate GCP services networking and landing zone requirements | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide service enablement requirements and quotas
Discovery | Compliance Review | Assess governance security and regulatory requirements | EO Engineer | 16 |  |  | 175 |  |  | Identifies compliance standards and organization policy constraints
Planning | Landing Zone Design | Design GCP landing zone architecture with Cloud Foundation Toolkit | EO Engineer | 48 |  |  | 200 |  | Requirements Gathering | Deliverable: Organization hierarchy folder structure and Terraform modules
Planning | Identity and Access Design | Design Cloud Identity integration and IAM access management | EO Engineer | 32 |  |  | 180 |  | Landing Zone Design | Includes SSO organization policies and service account design
Planning | Network Architecture Design | Design Shared VPC hub-spoke with Dedicated Interconnect | EO Engineer | 40 |  |  | 175 |  | Landing Zone Design | Deliverable: Network topology VPC design and hybrid connectivity architecture
Planning | Project Planning | Develop implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | Landing Zone Design | Deliverable: Project plan with phased team onboarding schedule
Development | Organization and Billing Setup | Configure GCP Organization folders and billing accounts | EO Engineer | 24 |  |  | 160 |  | Landing Zone Design | Includes organization hierarchy billing account structure and IAM
Development | Cloud Foundation Toolkit Implementation | Build Terraform modules for project provisioning and governance | EO Engineer | 72 |  |  | 150 |  | Organization and Billing Setup | Deliverable: Terraform modules for repeatable project deployment
Development | Shared VPC Network Infrastructure | Build hub-spoke VPC with Cloud NAT and load balancers | EO Engineer | 48 |  |  | 140 |  | Network Architecture Design | Includes VPC subnets firewall rules and Cloud NAT gateways
Development | Dedicated Interconnect Setup | Configure Dedicated Interconnect 10 Gbps to on-premises | EO Engineer | 40 |  |  | 175 |  | Shared VPC Network Infrastructure | Customer must coordinate on-premises network team and ISP
Development | Security Baseline Implementation | Deploy Security Command Center Chronicle and Cloud Armor | EO Engineer | 56 |  |  | 160 |  | Cloud Foundation Toolkit Implementation | Includes Cloud IDS SCC Premium and organization policy enforcement
Development | Organization Policy Configuration | Implement organization policies and resource constraints | EO Engineer | 32 |  |  | 155 |  | Security Baseline Implementation | Policy constraints for data residency resource locations and services
Development | Identity and Access Implementation | Configure Cloud Identity SSO and directory sync | EO Engineer | 32 |  |  | 155 |  | Identity and Access Design | Includes SAML SSO setup Google Cloud Directory Sync (GCDS) configuration
Development | Centralized Logging Setup | Configure Cloud Logging sinks and BigQuery exports | EO Engineer | 32 |  |  | 130 |  | Cloud Foundation Toolkit Implementation | Includes log aggregation long-term storage and compliance exports
Development | Monitoring and Alerting | Build Cloud Monitoring dashboards and alerting policies | EO Engineer | 24 |  |  | 130 |  | Centralized Logging Setup | Includes SLO dashboards budget alerts and operational monitoring
Testing | Infrastructure Testing | Test Terraform modules project provisioning and network connectivity | EO Engineer | 32 |  |  | 120 |  | Monitoring and Alerting | Includes automated testing with Terratest and validation scripts
Testing | Policy and Compliance Testing | Validate organization policies and security controls | EO Engineer | 24 |  |  | 140 |  | Organization Policy Configuration | Verify policy enforcement and compliance with security baseline
Testing | Security Testing | Perform security assessments and penetration testing | EO Engineer | 16 |  |  | 175 |  | Security Baseline Implementation | Includes vulnerability scanning and SCC Premium findings review
Testing | Hybrid Connectivity Testing | Test Dedicated Interconnect and on-premises connectivity | EO Engineer | 16 |  |  | 150 |  | Dedicated Interconnect Setup | Customer must coordinate connectivity testing with network team
Deployment | Foundation Deployment | Deploy landing zone foundation to production | EO Engineer | 24 |  |  | 160 |  | Infrastructure Testing | Includes production deployment validation and smoke testing
Deployment | Pilot Team Onboarding | Onboard 2 pilot teams to validate self-service workflows | EO Engineer | 32 |  |  | 130 |  | Foundation Deployment | Includes project provisioning team training and workflow validation
Deployment | Go-Live Support | Provide support during initial platform operations | EO Engineer | 48 |  |  | 110 |  | Pilot Team Onboarding | Includes issue resolution monitoring and operational support
Training | Administrator Training | Train platform admins on Google Admin console and Terraform | EO Engineer | 16 |  |  | 150 |  | Foundation Deployment | Includes hands-on training with Cloud Foundation Toolkit and GAM
Training | Platform User Training | Train application teams on project provisioning and platform usage | EO Engineer | 16 |  |  | 130 |  | Administrator Training | Includes self-service workflows best practices and support procedures
Training | Documentation | Create runbooks user guides and operational documentation | EO Engineer | 24 |  |  | 110 |  | Platform User Training | Deliverable: Administrator runbooks troubleshooting guides platform docs
Closeout | Knowledge Transfer | Transfer platform ownership to operations team | EO Engineer | 16 |  |  | 140 |  | Documentation | Includes operational handoff escalation procedures and maintenance
Closeout | FinOps Dashboards Setup | Establish cost allocation dashboards and budget controls | EO Engineer | 16 |  |  | 130 |  | Knowledge Transfer | Includes BigQuery billing exports cost attribution and forecasting
Management | Project Management | Project coordination status reporting and stakeholder management | EO Project Manager |  |  |  | 150 |  |  | 20% of engineering effort for project management overhead
Management | Technical Leadership | Quarterback oversight architecture review and technical governance | EO Quarterback |  |  |  | 180 |  |  | 25% of engineering effort for technical leadership
|  | TOTAL |  | $E27+$E28+$E29+$E30+$E31+$E32+$E33+$E34+$E35+$E36+$E37+$E38+$E39+$E40+$E41+$E42+$E43+$E44+$E45+$E46+$E47+$E48+$E49+$E50+$E51+$E52+$E53+$E54+$E55 | [5 empty] | Total landing zone implementation

## Credits
Credits
Category | Credit Type | Credit Amount | Credit Comments
Professional Services | Partner Implementation Credit | -5000 | Google Cloud partner implementation services discount
Professional Services | Architecture Credit | 0 | No additional architecture credits
Cloud Infrastructure | Migration Credit | -10000 | 20% Year 1 GCP consumption credit for new customers
Support & Maintenance | Support Credit | 0 | No support credits available