## Cover
[DOCUMENT TITLE]
Level of Effort
NVIDIA - Modern-Workspace - Omniverse Enterprise
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | GPU Workstations | 50x RTX A6000 workstations | 25 workstations | 50 workstations | 100 workstations | Dell Precision 7960 with RTX A6000 48GB
Solution Scope | Nucleus Servers | 2x Nucleus servers (HA) | 1 server | 2 servers (HA) | 4 servers (distributed) | Primary plus replica for high availability
Integration | Design Team Size | 50 designers and engineers | 20-30 users | 50-75 users | 100+ users | Concurrent Omniverse collaboration users
Integration | Storage Infrastructure | 100 TB USD scene storage | 50 TB | 100 TB | 250 TB | NetApp storage for Universal Scene Description files
Data Volume | 3D Scene Data | Multi-TB project files | 25-50 TB | 100-200 TB | 500+ TB | CAD models textures and rendered assets
Data Volume | Rendering Workloads | Interactive + batch rendering | Interactive only | Interactive + batch | Film-quality batch farm | RTX ray tracing requirements
Technical Environment | Network Infrastructure | 100 GbE network | 10 GbE | 100 GbE | 100 GbE + InfiniBand | Scene sync and file transfer performance
Technical Environment | Datacenter Readiness | Standard IT infrastructure | Existing network | Minor upgrades | Purpose-built studio | Nucleus server hosting and network capacity
Technical Environment | Deployment Model | On-premises deployment | Cloud-hosted | Hybrid on-prem | Edge + cloud sync | Nucleus server location
Security & Compliance | Data Classification | Proprietary 3D designs | Internal use | Confidential IP | Export-controlled designs | Design file protection requirements
Security & Compliance | Compliance Requirements | Standard security | Basic controls | SOC2 + IP protection | ITAR + trade secret | Regulatory frameworks for design data
Performance | Real-Time Collaboration | 50 concurrent users | 10 users | 50 users | 100+ users | Simultaneous USD scene editing
Performance | Rendering Performance | RTX ray tracing | Standard rasterization | RTX real-time | Path tracing + denoising | Interactive rendering quality requirements
Environment | CAD Tool Connectors | 5 primary connectors | 2-3 tools | 5-7 tools | 10+ custom connectors | Revit SolidWorks Rhino Blender Maya Unreal integration
Environment | Rendering Farm | 10 GPU render nodes | No farm | 10 nodes | 50+ nodes | Batch rendering for final output

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Design Requirements, Workflow Analysis, Tool Assessment, Team Planning)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Omniverse Architecture, Nucleus Design, Network Design, Connector Strategy)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Nucleus Deployment, Workstation Setup, Connector Integration, USD Pipeline, Rendering)
Testing | TESTING_MX | 1 | All Testing phase tasks (System Validation, Collaboration Testing, Rendering Testing, Performance Tuning)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Handoff, Designer Onboarding, Production Projects)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Designer Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Design Requirements | Conduct stakeholder interviews for 3D design and collaboration requirements | EO Engineer | 24 |  |  | 200 |  |  | Includes USD workflow requirements and rendering needs analysis
Discovery | Workflow Analysis | Analyze current CAD workflows file formats and collaboration pain points | EO Engineer | 32 |  |  | 200 |  |  | Customer must provide current design tools and project examples
Discovery | Tool Assessment | Inventory design tools and assess connector requirements | EO Engineer | 24 |  |  | 200 |  |  | Identifies Revit SolidWorks Rhino Blender Maya Unreal integration needs
Discovery | Team Planning | Assess design team size roles and concurrent collaboration requirements | EO Engineer | 16 |  |  | 175 |  |  | Identifies multi-user USD scene editing patterns and access needs
Planning | Omniverse Architecture | Design Omniverse Enterprise architecture with Nucleus and workstations | EO Engineer | 40 |  |  | 225 |  | Design Requirements | Deliverable: Omniverse architecture diagram with USD collaboration workflow
Planning | Nucleus Server Design | Design Nucleus server configuration with HA and storage backend | EO Engineer | 32 |  |  | 225 |  | Omniverse Architecture | Primary replica servers with NetApp storage integration
Planning | Network Design | Design 100 GbE network for USD scene sync and large file transfers | EO Engineer | 24 |  |  | 200 |  | Nucleus Server Design | High-bandwidth network for real-time collaboration
Planning | Connector Strategy | Plan CAD tool connector deployment and USD pipeline integration | EO Engineer | 32 |  |  | 225 |  | Tool Assessment | Connector installation strategy for Revit SolidWorks Rhino Blender Maya
Planning | Rendering Architecture | Design RTX rendering strategy with Omniverse Farm for batch jobs | EO Engineer | 24 |  |  | 200 |  | Omniverse Architecture | Interactive RTX ray tracing plus farm rendering for final output
Development | Storage Deployment | Deploy and configure NetApp storage for USD scene data | EO Engineer | 40 |  |  | 200 |  | Network Design | 100 TB storage cluster NFS configuration and performance tuning
Development | Nucleus Server Deployment | Install and configure 2x Nucleus servers with HA replication | EO Engineer | 48 |  |  | 225 |  | Storage Deployment | Primary replica deployment with automatic failover
Development | Network Configuration | Configure 100 GbE switches and workstation network connectivity | EO Engineer | 32 |  |  | 200 |  | Nucleus Server Deployment | Switch configuration VLAN setup and bandwidth management
Development | Workstation Deployment | Deploy and configure 50x Dell Precision workstations with RTX A6000 | EO Engineer | 80 |  |  | 200 |  | Network Configuration | Workstation imaging driver installation and Omniverse client setup
Development | Revit Connector Integration | Install and configure Autodesk Revit connector for BIM workflows | EO Engineer | 32 |  |  | 225 |  | Workstation Deployment | Revit plugin installation USD export settings and live sync configuration
Development | SolidWorks Connector Integration | Install and configure SolidWorks connector for CAD workflows | EO Engineer | 32 |  |  | 225 |  | Workstation Deployment | SolidWorks plugin installation assembly sync and materials mapping
Development | Rhino Connector Integration | Install and configure Rhino connector for industrial design workflows | EO Engineer | 24 |  |  | 225 |  | Workstation Deployment | Rhino plugin installation NURBS to USD conversion
Development | Blender Integration | Configure Blender USD workflows for 3D modeling and animation | EO Engineer | 16 |  |  | 200 |  | Workstation Deployment | Blender USD native support and Omniverse connector setup
Development | Maya Integration | Install and configure Autodesk Maya connector for animation workflows | EO Engineer | 24 |  |  | 225 |  | Workstation Deployment | Maya plugin installation scene sync and rendering integration
Development | Unreal Engine Integration | Configure Unreal Engine for real-time visualization and VR walkthroughs | EO Engineer | 32 |  |  | 225 |  | Workstation Deployment | Unreal USD import live link and RTX ray tracing setup
Development | USD Pipeline Setup | Configure custom USD pipeline with layers variants and references | EO Engineer | 40 |  |  | 250 |  | Unreal Engine Integration | Studio-specific USD schema asset structure and version control
Development | Rendering Farm Setup | Deploy 10x GPU render nodes for Omniverse Farm batch rendering | EO Engineer | 40 |  |  | 225 |  | USD Pipeline Setup | Farm controller configuration job queuing and render output management
Development | RTX Rendering Configuration | Configure RTX ray tracing settings materials and lighting for quality | EO Engineer | 24 |  |  | 200 |  | Rendering Farm Setup | RTX settings MDL materials and physically-based rendering optimization
Development | Security Configuration | Configure user authentication access controls and project permissions | EO Engineer | 24 |  |  | 200 |  | RTX Rendering Configuration | SSO integration role-based access and IP protection
Testing | System Validation | Validate Nucleus servers workstations and RTX GPU functionality | EO Engineer | 24 |  |  | 175 |  | Security Configuration | Server health checks GPU diagnostics and storage validation
Testing | Collaboration Testing | Test multi-user USD scene editing with concurrent designer access | EO Engineer | 32 |  |  | 200 |  | System Validation | Real-time sync conflict resolution and version control testing
Testing | Connector Testing | Validate all CAD tool connectors with representative design files | EO Engineer | 40 |  |  | 225 |  | Collaboration Testing | Customer must provide sample Revit SolidWorks Rhino and Maya files
Testing | Rendering Testing | Test RTX interactive rendering and Farm batch job performance | EO Engineer | 24 |  |  | 200 |  | Connector Testing | Ray tracing quality benchmarks and render farm throughput validation
Testing | Performance Tuning | Optimize USD scene performance RTX settings and network throughput | EO Engineer | 24 |  |  | 225 |  | Rendering Testing | Tune scene complexity LOD settings and collaboration performance
Deployment | Production Handoff | Transition Omniverse platform to production with monitoring and support | EO Engineer | 16 |  |  | 200 |  | Performance Tuning | Production readiness validation and operational procedures documentation
Deployment | Designer Onboarding | Onboard design teams with Nucleus access connector setup and projects | EO Engineer | 40 |  |  | 175 |  | Production Handoff | User account setup project workspace creation and initial collaboration support
Deployment | Production Project Migration | Migrate first production design projects to Omniverse workflows | EO Engineer | 48 |  |  | 200 |  | Designer Onboarding | Assist with CAD model import USD conversion and collaborative editing
Training | Administrator Training | Train IT administrators on Nucleus server management and troubleshooting | EO Engineer | 24 |  |  | 200 |  | Production Handoff | Nucleus administration user management storage monitoring and backup
Training | Designer Training | Train designers on Omniverse workflows USD collaboration and rendering | EO Engineer | 40 |  |  | 200 |  | Administrator Training | CAD connector usage live sync version control RTX rendering and best practices
Training | Advanced USD Training | Train power users on custom USD pipeline materials and automation | EO Engineer | 24 |  |  | 225 |  | Designer Training | USD composition scripting MDL materials and pipeline customization
Training | Documentation | Create technical documentation workflow guides and best practices | EO Engineer | 32 |  |  | 150 |  | Advanced USD Training | Deliverable: Operations runbook connector guides USD workflow documentation
Closeout | Knowledge Transfer | Transfer Omniverse platform ownership to client IT and design teams | EO Engineer | 16 |  |  | 200 |  | Documentation | Comprehensive handover including architecture Nucleus management and support
Closeout | Performance Baseline | Establish collaboration metrics rendering performance and user adoption KPIs | EO Engineer | 16 |  |  | 175 |  | Knowledge Transfer | Establishes concurrent users rendering time and ROI metrics
Management | Technical Leadership | NVIDIA Omniverse technical oversight and USD architecture review | EO Quarterback |  |  |  | 250 |  |  | Omniverse expertise USD pipeline design and technical escalation
Management | Project Management | Project coordination planning and stakeholder management | EO Project Manager |  |  |  | 175 |  |  | Includes weekly status Dell/NVIDIA coordination and risk management
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase multipliers in Estimate Settings based on deployment scope

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
NVIDIA Partner Services Credit | -12000 | NVIDIA Partner Network credit for Omniverse Enterprise deployment and connector integration
Implementation Discount | 0 | No implementation discount applicable
TOTAL