## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Vxrail Hyperconverged
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | Week 1 Day 1 | Week 1 Day 1 | None | Project Manager | Not Started
Planning | Current State Assessment | 2 days | Week 1 Day 1 | Week 1 Day 2 | Project Kickoff | VMware Architect | Not Started
Planning | Database Workload Analysis | 2 days | Week 1 Day 2 | Week 1 Day 3 | Assessment Start | DBA Lead | Not Started
Planning | Network Requirements Review | 2 days | Week 1 Day 3 | Week 1 Day 4 | Workload Analysis | Network Engineer | Not Started
Planning | VxRail P570 Configuration Design | 2 days | Week 1 Day 4 | Week 2 Day 1 | All Assessments | VMware Architect | Not Started
Planning | Dell Hardware Order Submission | 1 day | Week 2 Day 1 | Week 2 Day 1 | Design Approved | Procurement | Not Started
Planning | Data Center Preparation | 5 days | Week 2 Day 1 | Week 2 Day 5 | Order Submitted | Facilities Team | Not Started
Planning | 100GbE Spine-Leaf Configuration | 3 days | Week 2 Day 3 | Week 2 Day 5 | Data Center Prep | Network Engineer | Not Started
Deployment | Hardware Delivery and Rack | 1 day | Week 3 Day 1 | Week 3 Day 1 | Dell Delivery | Dell ProDeploy | Not Started
Deployment | VxRail P570 Node Cabling | 1 day | Week 3 Day 1 | Week 3 Day 1 | Hardware Racked | Dell ProDeploy | Not Started
Deployment | VxRail Manager Initialization | 1 day | Week 3 Day 2 | Week 3 Day 2 | Cabling Complete | VMware Architect | Not Started
Deployment | 8-Node Cluster Creation | 2 days | Week 3 Day 2 | Week 3 Day 3 | VxRail Init | VMware Architect | Not Started
Deployment | vSAN 8 All-NVMe Configuration | 2 days | Week 3 Day 3 | Week 3 Day 4 | Cluster Created | VMware Architect | Not Started
Deployment | NSX-T Microsegmentation Setup | 2 days | Week 3 Day 4 | Week 3 Day 5 | vSAN Configured | Network Engineer | Not Started
Deployment | External KMS Integration | 1 day | Week 4 Day 1 | Week 4 Day 1 | NSX Complete | Security Team | Not Started
Deployment | VMware SRM Configuration | 2 days | Week 4 Day 1 | Week 4 Day 2 | KMS Integrated | VMware Architect | Not Started
Migration | Database Migration Planning | 1 day | Week 4 Day 2 | Week 4 Day 2 | SRM Ready | DBA Lead | Not Started
Migration | Oracle RAC Migration | 3 days | Week 4 Day 3 | Week 5 Day 1 | Migration Planning | DBA Lead | Not Started
Migration | SQL Server Always-On Migration | 2 days | Week 5 Day 1 | Week 5 Day 2 | Oracle Complete | DBA Lead | Not Started
Migration | SAP HANA Migration | 2 days | Week 5 Day 2 | Week 5 Day 3 | SQL Complete | DBA Lead | Not Started
Migration | General VM Migration (800 VMs) | 3 days | Week 5 Day 3 | Week 6 Day 1 | Databases Complete | VMware Admin | Not Started
Validation | HCIBench Performance Testing | 1 day | Week 6 Day 1 | Week 6 Day 1 | Migration Complete | VMware Architect | Not Started
Validation | Database Performance Validation | 1 day | Week 6 Day 2 | Week 6 Day 2 | HCIBench Complete | DBA Lead | Not Started
Validation | DR Failover Testing | 1 day | Week 6 Day 2 | Week 6 Day 2 | Performance Testing | VMware Architect | Not Started
Training | VxRail Administration Training | 1 day | Week 7 Day 1 | Week 7 Day 1 | Validation Complete | Training Lead | Not Started
Training | vSAN Troubleshooting Training | 0.5 day | Week 7 Day 2 | Week 7 Day 2 | Admin Training | Training Lead | Not Started
Training | NSX-T Operations Training | 0.5 day | Week 7 Day 2 | Week 7 Day 2 | Admin Training | Training Lead | Not Started
Training | SRM DR Procedures Training | 0.5 day | Week 7 Day 3 | Week 7 Day 3 | Admin Training | Training Lead | Not Started
Training | Database on vSAN Training | 0.5 day | Week 7 Day 3 | Week 7 Day 3 | Admin Training | DBA Lead | Not Started
Closure | Documentation Finalization | 2 days | Week 7 Day 4 | Week 8 Day 1 | All Training | Technical Writer | Not Started
Closure | Project Acceptance Sign-off | 1 day | Week 8 Day 1 | Week 8 Day 1 | Documentation | Project Manager | Not Started
Closure | Hypercare Handover | 1 day | Week 8 Day 2 | Week 8 Day 2 | Acceptance | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Hardware Ordered | Week 2 | Dell VxRail P570 purchase order submitted and delivery scheduled | Project Manager | Not Started
M2 | Hardware Delivered | Week 3 | 8 VxRail P570 nodes delivered racked and cabled with 100GbE network | Dell ProDeploy | Not Started
M3 | Cluster Operational | Week 4 | VxRail cluster created with 200TB vSAN NSX-T and SRM configured | VMware Architect | Not Started
M4 | Databases Migrated | Week 6 | Oracle RAC SQL Always-On and SAP HANA migrated with zero data loss | DBA Lead | Not Started
M5 | Validation Complete | Week 7 | HCIBench 125K IOPS and sub-ms latency verified DR failover tested | VMware Architect | Not Started
M6 | Project Closure | Week 8 | Training complete documentation accepted support transitioned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | VMware | NetEng | DBA | Storage | IT | Client
Project Charter and Kickoff | A | C | C | I | I | I | C | I
Current State Assessment | A | R | C | C | C | C | C | C
VxRail P570 Configuration Design | A | R | C | C | C | I | I | I
Dell Hardware Procurement | A | C | I | I | I | I | R | C
VxRail 8-Node Cluster Deployment | A | R | C | C | I | I | C | I
vSAN All-NVMe Configuration | A | R | C | I | C | C | I | I
100GbE Network Configuration | A | C | C | R | I | I | C | I
NSX-T Microsegmentation | A | C | C | R | I | I | C | I
Database Migration Execution | A | C | C | I | R | I | C | I
HCIBench Performance Testing | A | R | C | I | C | I | I | I
DR Failover Testing | A | R | C | C | C | I | C | I
VxRail Administration Training | A | I | R | I | I | I | C | C
Documentation Delivery | A | R | C | C | C | C | C | I
Production Go-Live Approval | A | C | C | C | C | C | C | R
Legend:
R | A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders PM Architect IT Lead DBA | Launch project and align on scope and timeline | Project Manager | Week 1 Day 1
Steering Committee | Weekly | Executive sponsors PM IT Director DBA Lead | Strategic updates budget review issue escalation | Project Manager | Fridays 10:00
Daily Standup | Daily | Core project team | Review progress blockers and daily priorities | Project Manager | Daily 09:00
Technical Review | Weekly | Architect VMware Admin Network DBA Storage | Technical decisions and implementation progress | VMware Architect | Wednesdays 14:00
Database Migration Checkpoint | Daily | DBA Lead VMware Admin Architect | Database migration progress and issue resolution | DBA Lead | Week 4-6 Daily
Validation Review | Daily | Architect VMware Admin DBA QA | Benchmark results and health check findings | VMware Architect | Week 7 Daily
Training Coordination | Once | Training Lead VMware Admin DBA IT Team | Training schedule and logistics confirmation | Training Lead | Week 6 Day 5
Go-Live Readiness | Daily | All stakeholders | Go-live checklist and final preparation | Project Manager | Week 8 Daily