## Cover
Test Plan
Generated: | November 28, 2025
Solution: | Vxrail Hyperconverged
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | VxRail P570 Node Power-On | Validate all 8 VxRail P570 nodes power on and complete POST | Hardware racked and cabled | 1. Power on each node; 2. Verify POST completes; 3. Check iDRAC status; 4. Verify all NVMe drives detected | All nodes POST with 16TB NVMe storage detected per node | High | Not Started
FT-002 | Unit | ESXi 8 Host Detection | Validate ESXi 8 installed and operational on each P570 node | VxRail Manager initialized | 1. Access VxRail Manager; 2. Verify each host status; 3. Check ESXi version; 4. Validate 2TB RAM per node | All 8 ESXi hosts showing online with 16TB total RAM | High | Not Started
FT-003 | Unit | vSAN 8 All-NVMe Disk Groups | Validate vSAN disk groups created with all-NVMe storage | ESXi hosts operational | 1. Access vCenter vSAN UI; 2. Verify disk groups per host; 3. Check NVMe tier; 4. Verify erasure coding | Each node shows NVMe disk group with FTT=2 policy | High | Not Started
FT-004 | Integration | 8-Node vSphere Cluster | Validate vSphere cluster created with all VxRail P570 hosts | vCenter deployed | 1. Access vCenter; 2. Navigate to cluster; 3. Verify all 8 hosts; 4. Check HA and DRS status | Cluster shows 8 hosts with HA DRS and vSAN enabled | High | Not Started
FT-005 | Integration | vSAN 200TB Datastore | Validate 200TB vSAN datastore available to all hosts | vSAN disk groups created | 1. Check vSAN datastore; 2. Verify 200TB capacity; 3. Check mount status; 4. Test write operation | 200TB vSAN datastore accessible from all 8 hosts | High | Not Started
FT-006 | Integration | NSX-T Microsegmentation | Validate NSX-T configured with security policies | Network VLANs configured | 1. Check NSX Manager; 2. Verify distributed firewall; 3. Test microsegmentation rules; 4. Validate logging | NSX-T DFW active with database security zones | High | Not Started
FT-007 | System | Oracle RAC Deployment | Validate Oracle RAC deploys and operates on vSAN | vSAN datastore available | 1. Deploy Oracle RAC VMs; 2. Configure ASM on vSAN; 3. Test RAC failover; 4. Validate witness placement | Oracle RAC operational with sub-ms storage latency | Critical | Not Started
FT-008 | System | VMware SRM Configuration | Validate SRM configured with RecoverPoint for VMs | SRM server connected | 1. Configure SRM pairing; 2. Create protection groups; 3. Create recovery plans; 4. Verify replication | SRM shows protection groups with RPO <5 min | High | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | vSAN IOPS Benchmark | Validate vSAN cluster achieves 125000+ IOPS performance | Cluster operational with test VMs | 1. Deploy HCIBench appliance; 2. Configure 4K random workload; 3. Run 60-minute test; 4. Record results | vSAN achieves 125000+ IOPS with all-NVMe storage | Critical | Not Started
NFT-002 | Performance | vSAN Sub-ms Latency | Validate vSAN read and write latency under 1ms | HCIBench deployed | 1. Configure latency-focused workload; 2. Run 70% read 30% write; 3. Measure average latency; 4. Check 99th percentile | Average latency 0.4ms with 99th percentile under 0.8ms | Critical | Not Started
NFT-003 | Performance | Oracle RAC Performance | Validate Oracle database performance on vSAN | Oracle RAC deployed | 1. Run SLOB benchmark; 2. Measure transaction throughput; 3. Check wait events; 4. Compare to legacy | Oracle achieves 45000 IOPS per database instance | Critical | Not Started
NFT-004 | Performance | 100GbE Network Throughput | Validate 100GbE network achieves expected throughput | Network cabling complete | 1. Run iperf3 between hosts; 2. Test vSAN network bandwidth; 3. Measure aggregate throughput; 4. Check packet loss | 100GbE links achieve 95+ Gbps with zero packet loss | High | Not Started
NFT-005 | Reliability | vSphere HA Failover | Validate HA restarts VMs after simulated host failure | HA enabled on cluster | 1. Power off one ESXi host; 2. Monitor VM restart; 3. Measure failover time; 4. Verify accessibility | VMs restart on remaining hosts within 90 seconds | Critical | Not Started
NFT-006 | Reliability | vSAN N+2 Rebuild | Validate vSAN rebuilds data after dual disk failure | vSAN healthy with FTT=2 | 1. Simulate dual disk failure; 2. Monitor rebuild progress; 3. Verify data integrity; 4. Confirm capacity | vSAN rebuilds data automatically with zero data loss | High | Not Started
NFT-007 | Reliability | DR Failover Test | Validate SRM failover completes within RTO target | SRM configured and tested | 1. Initiate planned failover; 2. Monitor recovery progress; 3. Measure RTO; 4. Validate application access | DR failover completes within 15 minutes RTO target | Critical | Not Started
NFT-008 | Security | vSAN Encryption Verify | Validate vSAN encryption at rest with external KMS | KMS integration complete | 1. Check vSAN encryption status; 2. Verify KMS integration; 3. Test key rotation; 4. Validate audit logging | vSAN encryption operational with external KMS | High | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Business Process | Database Migration Workflow | Validate end-to-end database migration from legacy SAN | Legacy and VxRail connected | 1. Select production database; 2. Initiate Oracle Data Guard; 3. Monitor sync; 4. Perform switchover | Database migrates to vSAN with zero data loss | Critical | Not Started
UAT-002 | Business Process | Multi-Database Migration | Validate batch migration of Oracle SQL and SAP HANA | Migration scripts ready | 1. Execute migration runbook; 2. Monitor all databases; 3. Track completion; 4. Verify all operational | All databases migrate successfully within maintenance window | Critical | Not Started
UAT-003 | Business Process | Database Performance Validation | Validate database performance after migration to VxRail | Databases migrated to VxRail | 1. Run production queries; 2. Compare to legacy baseline; 3. Check response times; 4. Validate user experience | Database performance 2.5x better than legacy SAN | High | Not Started
UAT-004 | User Interface | vCenter Database Management | Validate DBAs can manage database VMs via vCenter | vCenter access granted | 1. Log in to vCenter; 2. Access database VM; 3. Modify resources; 4. Take snapshot; 5. Check vSAN policy | All database VM operations complete successfully | Medium | Not Started
UAT-005 | User Interface | VxRail Manager Operations | Validate VxRail Manager lifecycle management functions | VxRail Manager access | 1. Access VxRail Manager; 2. View cluster health; 3. Check software versions; 4. Review support status | VxRail Manager displays health and enables LCM | Medium | Not Started
UAT-006 | Business Process | DR Failover and Failback | Validate complete DR cycle with database recovery | SRM recovery plans ready | 1. Initiate DR failover; 2. Validate databases online; 3. Run application tests; 4. Execute failback | Complete DR cycle with RPO <5min and RTO <15min | Critical | Not Started