## Slide 1
Project Closeout
Dell SafeID Enterprise Authentication
Project Manager | November 28, 2025

## Slide 2
Executive Summary
Project Duration: 6 weeks, on schedule
Budget: $185,000 delivered on budget
Go-Live Date: Week 6 as planned
Quality: Zero security incidents
Users Enrolled: 500 with YubiKey tokens
Compliance: CMMC Level 2 achieved
Authentication: <2 second tap response
Dell SafeID Enterprise Authentication
Notes: *Opening Statement:*
Good [morning/afternoon]. Today we're celebrating the successful completion of the Dell SafeID Enterprise Authentication implementation. This project has transformed [Client Name]'s identity security from password-based authentication to phishing-resistant FIDO2 hardware tokens.
*Key Talking Points:*
**Project Duration - 6 Weeks:**
- Phase 1 (Weeks 1-2): Infrastructure setup, AD integration
- Phase 2 (Weeks 3-4): Pilot rollout, VPN integration
- Phase 3 (Weeks 5-6): Full deployment, training
- All milestones achieved on schedule
**Phishing-Resistant Security:**
- YubiKey 5 NFC hardware tokens for all 500 users
- FIDO2 WebAuthn eliminates phishing attacks
- No more password resets or credential theft
- Separate admin YubiKeys for privileged access
**Compliance Achievement:**
- CMMC Level 2 MFA requirements met
- 3-year audit log retention configured
- NIST 800-63B AAL2 compliance
- Ready for DoD contract requirements
**User Experience:**
- <2 second authentication with tap
- <5 minute self-service enrollment
- Mobile and desktop support
- Works offline with FIDO2
*Transition:*
"Let me walk you through what we deployed..."

## Slide 3
Solution Architecture
Identity Layer
  Dell SafeID Enterprise server
  Active Directory integration
  LDAP/RADIUS authentication
Token Layer
  500x YubiKey 5 NFC tokens
  FIDO2 phishing-resistant auth
  Backup tokens for recovery
Integration Layer
  Cisco AnyConnect VPN MFA
  Microsoft 365 SAML SSO
  AWS IAM Identity Center
Dell SafeID Enterprise Authentication
Notes: *Architecture Overview:*
**Identity Layer - Dell SafeID Enterprise:**
- High-availability authentication servers
- Active Directory sync for user provisioning
- RADIUS integration for VPN authentication
- SAML IdP for cloud SSO
- Audit logging with 3-year retention
**Token Layer - YubiKey 5 NFC:**
- Hardware security key for each user
- FIDO2/WebAuthn phishing-resistant protocol
- NFC for mobile authentication
- USB-A and USB-C support
- PIV smart card capability (future)
**Integration Points:**
- Cisco AnyConnect: RADIUS MFA
- Microsoft 365: SAML SSO with YubiKey
- AWS: IAM Identity Center federation
- Windows logon: Smart card ready
**Key Architecture Decisions:**
1. YubiKey 5 NFC for mobile flexibility
2. FIDO2 over TOTP for phishing resistance
3. Separate admin tokens for privileged access
4. Self-service portal for enrollment
*Transition:*
"Now let me show you the complete deliverables..."

## Slide 4
Deliverables Inventory
Deliverable | Purpose | Location
Solution Architecture | SafeID design and integrations | `/delivery/detailed-design.docx`
Implementation Guide | Deployment and enrollment runbooks | `/delivery/implementation-guide.docx`
Project Plan | Timeline, milestones, RACI matrix | `/delivery/project-plan.xlsx`
Test Results | Security validation and UAT | `/delivery/test-plan.xlsx`
Configuration Guide | SafeID and RADIUS parameters | `/delivery/configuration.xlsx`
User Enrollment Guide | Self-service enrollment steps | `/delivery/user-guide.pdf`
Admin Operations Guide | Token management procedures | `/delivery/admin-guide.docx`
Compliance Evidence | CMMC Level 2 artifacts | Compliance portal
Dell SafeID Enterprise Authentication
Notes: *Deliverables Deep Dive:*
**1. Solution Architecture Document:**
- Dell SafeID server configuration
- Active Directory integration design
- RADIUS and SAML configuration
- YubiKey enrollment workflow
- Backup and recovery procedures
**2. User Enrollment Guide:**
- Self-service portal instructions
- YubiKey registration steps
- Mobile NFC setup for Android/iOS
- Troubleshooting common issues
- Available in print and digital
**3. Admin Operations Guide:**
- User provisioning procedures
- Token replacement process
- Lost token recovery workflow
- Audit log review procedures
- CMMC compliance reporting
**4. Training Delivered:**
- Help desk training: 4 hours
- IT admin training: 8 hours
- User awareness sessions: 1 hour each
- Total: 500+ users trained
*Transition:*
"Let's look at security and performance..."

## Slide 5
Quality & Performance
Security Metrics
  Phishing Resistance: 100%
  Password Resets: 0 required
  Account Takeovers: 0 incidents
  Credential Theft: Eliminated
  Audit Coverage: 100%
Performance Metrics
  Auth Time: 1.8s (target: <2s)
  Enrollment Time: 4 min avg
  Availability: 99.99% uptime
  Daily Auths: 10,000+ handled
  User Satisfaction: 94%
Dell SafeID Enterprise Authentication
Notes: *Security Deep Dive:*
**Phishing Resistance - 100%:**
- FIDO2 WebAuthn prevents credential theft
- Origin-bound keys cannot be phished
- No shared secrets to intercept
- Hardware attestation verifies genuine keys
**Zero Password Resets:**
- Eliminated #1 help desk call reason
- No forgotten passwords with YubiKey
- Self-service enrollment reduces IT burden
- PIN recovery available if needed
**Compliance Evidence:**
- CMMC Level 2 IA.2.078: MFA for network access
- CMMC Level 2 IA.2.079: MFA for privileged users
- NIST 800-63B AAL2: Hardware token requirement
- Audit logs: 3 years retained
**Performance Metrics:**
*Authentication Time - 1.8 seconds:*
- User taps YubiKey
- FIDO2 challenge/response
- Authentication complete
- Faster than TOTP or SMS
*Enrollment - 4 minutes average:*
- User receives YubiKey
- Scans QR code to enroll
- Taps key to confirm
- Immediate access enabled
**User Satisfaction Survey:**
- 94% prefer YubiKey to passwords
- 89% find enrollment easy
- 96% would recommend to colleagues
*Transition:*
"These improvements deliver significant value..."

## Slide 6
Benefits Realized
Benefit Category | SOW Target | Achieved | Business Impact
Phishing Protection | 95% | 100% | Zero credential theft
Password Resets | 50% reduction | 100% eliminated | Help desk savings
CMMC Compliance | Level 2 | Level 2 | DoD contract ready
User Experience | <5s auth | 1.8s auth | Higher productivity
Privileged Access | MFA required | YubiKey enforced | Reduced admin risk
Audit Capability | 1 year | 3 years | Extended compliance
Dell SafeID Enterprise Authentication
Notes: *Benefits Analysis:*
**Phishing Protection - 100%:**
- Legacy: Passwords phished via email attacks
- New: FIDO2 cannot be phished (cryptographic)
- Business impact: Zero credential theft incidents
- Estimated annual savings: $150K (breach prevention)
**Password Reset Elimination:**
- Previous: 50 password resets/month
- Current: 0 password resets (no passwords)
- Help desk time saved: 25 hours/month
- Annual savings: $15,000 in labor
**CMMC Level 2 Compliance:**
- All MFA requirements met
- Audit artifacts generated automatically
- Ready for DoD assessor review
- Enables $5M+ contract eligibility
**User Experience:**
- 1.8 second authentication
- No password memorization
- Works across VPN, M365, AWS
- Mobile support with NFC
**3-Year TCO Analysis:**
| Cost Category | Year 1 | Year 2 | Year 3 | Total |
|---------------|--------|--------|--------|-------|
| Hardware | $75,000 | $5,000 | $5,000 | $85,000 |
| Software | $50,000 | $30,000 | $30,000 | $110,000 |
| Services | $60,000 | $10,000 | $10,000 | $80,000 |
| **Total** | **$185,000** | **$45,000** | **$45,000** | **$275,000** |
*Transition:*
"We learned valuable lessons..."

## Slide 7
Lessons Learned & Recommendations
What Worked Well
  Self-service enrollment portal
  Department-by-department rollout
  YubiKey 5 NFC flexibility
  Executive champion support
  Pre-registration communication
Challenges Overcome
  Legacy app compatibility
  Remote worker enrollment
  USB-C adapter needs
  Mobile app configuration
  Backup token logistics
Recommendations
  Expand to contractors
  Add passwordless Windows
  Implement PIV capability
  Consider YubiKey Bio
  Annual security training
Dell SafeID Enterprise Authentication
Notes: *Lessons Learned Details:*
**What Worked Well:**
*1. Self-Service Enrollment:*
- Users enroll their own YubiKeys
- Reduces IT burden significantly
- 4-minute average enrollment time
- Help desk calls minimized
*2. Phased Department Rollout:*
- Started with IT department
- Expanded to finance, then engineering
- Each wave learned from previous
- Final wave to field workers
*3. Executive Support:*
- CEO enrolled first publicly
- Set example for organization
- Reinforced security culture
- Helped with change management
**Challenges Overcome:**
*1. Legacy App Compatibility:*
- Challenge: Some apps don't support FIDO2
- Resolution: RADIUS bridge for legacy systems
- Lesson: Inventory apps early in planning
*2. Remote Worker Enrollment:*
- Challenge: Shipping YubiKeys securely
- Resolution: Registered mail with tracking
- Lesson: Plan logistics for remote users
**Recommendations:**
*1. Expand to Contractors (Priority: High):*
- Extend MFA to contractor population
- Separate enrollment workflow
- Investment: $20K for 100 contractors
*2. Passwordless Windows Logon:*
- Use YubiKey for Windows sign-in
- Eliminate domain passwords entirely
- Timeline: Phase 2 consideration
*Transition:*
"Let me walk through support..."

## Slide 8
Support Transition
Hypercare Complete (6 weeks)
  Daily enrollment support
  0 security incidents
  All users trained
  Help desk certified
  Runbooks validated
Steady State Support
  Dell SafeID support contract
  Yubico technical support
  Help desk Tier 1 handling
  Monthly security reviews
  Quarterly audit reports
Escalation Path
  L1: Internal Help Desk
  L2: IT Security Team
  L3: Dell SafeID Support
  Token Issues: Yubico Support
  Compliance: Security Officer
Dell SafeID Enterprise Authentication
Notes: *Support Transition Details:*
**Help Desk Procedures:**
*Common Scenarios:*
1. Lost YubiKey: Issue temp token, order replacement
2. Damaged YubiKey: Same-day replacement from stock
3. New hire: Add to SafeID, ship YubiKey
4. Termination: Disable user, recover token
5. PIN forgotten: Self-service PIN reset
**Training Delivered:**
| Session | Attendees | Duration |
|---------|-----------|----------|
| Help Desk Training | 8 staff | 4 hours |
| IT Admin Training | 4 staff | 8 hours |
| Security Team | 3 staff | 4 hours |
| User Awareness | 500 users | 1 hour |
**Spare Token Inventory:**
- 25 YubiKey 5 NFC spares on-hand
- 5 admin YubiKeys in reserve
- Reorder threshold: 10 remaining
- Yubico ships within 48 hours
**Monthly Operational Tasks:**
- Week 1: Review failed auth attempts
- Week 2: Check token inventory levels
- Week 3: Audit privileged user access
- Week 4: Generate compliance reports
*Transition:*
"Let me recognize the team..."

## Slide 9
Acknowledgments & Next Steps
Client Team: CISO, IT security, help desk, HR for communications
Vendor Team: Project manager, security architect, deployment engineer
Special Recognition: Help desk team for excellent user support
This Week: Final user enrollment, documentation handover
Next 30 Days: Contractor expansion planning, audit preparation
Next Quarter: Passwordless Windows evaluation, PIV assessment
Dell SafeID Enterprise Authentication
Notes: *Acknowledgments:*
**Client Team:**
- CISO: Executive sponsorship and security vision
- IT Security Lead: Technical implementation ownership
- Help Desk Manager: User support coordination
- HR Communications: Employee messaging
**Vendor Team:**
- Project Manager: Delivery accountability
- Security Architect: SafeID and FIDO2 design
- Deployment Engineer: Rollout execution
**Immediate Next Steps:**
| Task | Owner | Due |
|------|-------|-----|
| Final enrollment completion | IT Security | This week |
| Documentation archive | PM | This week |
| CMMC assessor scheduling | CISO | Week 2 |
| Contractor scope definition | Security | Week 4 |
**Phase 2 Considerations:**
| Enhancement | Investment | Benefit |
|-------------|------------|---------|
| Contractor MFA | $20K | Supply chain security |
| Passwordless Windows | $15K | Complete password elimination |
| YubiKey Bio | $25K | Biometric for high-security |
| PIV Smart Card | $10K | Government requirements |
*Transition:*
"Thank you for your partnership..."

## Slide 10
Thank You
Notes: *Closing:*
"Thank you for your partnership. The Dell SafeID platform with YubiKey hardware tokens provides phishing-resistant authentication that meets CMMC Level 2 requirements and significantly improves your security posture.
Questions?"
**Anticipated Questions:**
*Q: What if someone loses their YubiKey?*
A: Help desk issues temporary token, orders replacement. User re-enrolls new key in 4 minutes. Lost key cannot be used without PIN.
*Q: Can we use YubiKey for more applications?*
A: Yes, YubiKey supports many protocols. We can add SSH, code signing, and additional SAML apps.
*Q: What about mobile-only users?*
A: YubiKey 5 NFC works with iOS and Android via NFC. Also supports mobile authenticator app as backup.
*Q: How long do YubiKeys last?*
A: No battery, no moving parts. Yubico warrants 2 years, but keys typically last 5+ years.