## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Safeid Authentication
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | Week 1 Day 1 | Week 1 Day 1 | None | Project Manager | Not Started
Planning | Current Authentication Assessment | 2 days | Week 1 Day 1 | Week 1 Day 2 | Project Kickoff | Security Architect | Not Started
Planning | User Inventory and Grouping | 2 days | Week 1 Day 2 | Week 1 Day 3 | Assessment Start | IT Security | Not Started
Planning | Integration Requirements Review | 2 days | Week 1 Day 3 | Week 1 Day 4 | User Inventory | Security Architect | Not Started
Planning | SafeID Configuration Design | 2 days | Week 1 Day 4 | Week 2 Day 1 | All Assessments | Security Architect | Not Started
Planning | Dell Hardware Order Submission | 1 day | Week 2 Day 1 | Week 2 Day 1 | Design Approved | Procurement | Not Started
Planning | YubiKey Token Ordering | 1 day | Week 2 Day 1 | Week 2 Day 1 | User Count Finalized | Procurement | Not Started
Planning | Active Directory Preparation | 3 days | Week 2 Day 2 | Week 2 Day 4 | Design Approved | AD Admin | Not Started
Deployment | SafeID Server Installation | 2 days | Week 3 Day 1 | Week 3 Day 2 | AD Prep Complete | Security Architect | Not Started
Deployment | Active Directory Integration | 1 day | Week 3 Day 2 | Week 3 Day 2 | Server Installed | AD Admin | Not Started
Deployment | LDAP and RADIUS Configuration | 2 days | Week 3 Day 3 | Week 3 Day 4 | AD Integrated | Security Architect | Not Started
Deployment | SAML IdP Configuration | 1 day | Week 3 Day 4 | Week 3 Day 4 | RADIUS Complete | Security Architect | Not Started
Deployment | Self-Service Portal Setup | 1 day | Week 3 Day 5 | Week 3 Day 5 | SAML Complete | Security Architect | Not Started
Deployment | Cisco AnyConnect VPN Integration | 2 days | Week 4 Day 1 | Week 4 Day 2 | Portal Ready | Network Engineer | Not Started
Deployment | Microsoft 365 SAML SSO | 1 day | Week 4 Day 2 | Week 4 Day 2 | SAML IdP Ready | Security Architect | Not Started
Deployment | AWS IAM Identity Center | 1 day | Week 4 Day 3 | Week 4 Day 3 | M365 Complete | Cloud Engineer | Not Started
Rollout | IT Department Pilot (25 users) | 2 days | Week 4 Day 3 | Week 4 Day 4 | Integrations Complete | IT Security | Not Started
Rollout | Finance Department (75 users) | 2 days | Week 4 Day 4 | Week 4 Day 5 | Pilot Success | IT Security | Not Started
Rollout | Engineering Department (150 users) | 3 days | Week 5 Day 1 | Week 5 Day 3 | Finance Complete | IT Security | Not Started
Rollout | Operations Department (150 users) | 2 days | Week 5 Day 3 | Week 5 Day 4 | Engineering Complete | IT Security | Not Started
Rollout | Field Workers (100 users) | 2 days | Week 5 Day 4 | Week 6 Day 1 | Operations Complete | IT Security | Not Started
Validation | FIDO2 Authentication Testing | 1 day | Week 6 Day 1 | Week 6 Day 1 | All Users Enrolled | Security Architect | Not Started
Validation | VPN MFA Validation | 0.5 day | Week 6 Day 2 | Week 6 Day 2 | FIDO2 Testing | Network Engineer | Not Started
Validation | Cloud SSO Validation | 0.5 day | Week 6 Day 2 | Week 6 Day 2 | VPN Testing | Cloud Engineer | Not Started
Training | Help Desk Training | 0.5 day | Week 6 Day 3 | Week 6 Day 3 | Validation Complete | Training Lead | Not Started
Training | IT Admin Training | 1 day | Week 6 Day 3 | Week 6 Day 3 | Validation Complete | Training Lead | Not Started
Training | User Awareness Sessions | 1 day | Week 6 Day 4 | Week 6 Day 4 | Admin Training | Training Lead | Not Started
Closure | Documentation Finalization | 1 day | Week 6 Day 4 | Week 6 Day 4 | All Training | Technical Writer | Not Started
Closure | CMMC Compliance Evidence | 1 day | Week 6 Day 5 | Week 6 Day 5 | Documentation | Security Architect | Not Started
Closure | Project Acceptance Sign-off | 1 day | Week 6 Day 5 | Week 6 Day 5 | Compliance Evidence | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Hardware Ordered | Week 2 | Dell SafeID server and 500 YubiKey 5 NFC tokens ordered | Project Manager | Not Started
M2 | Platform Deployed | Week 3 | SafeID server operational with AD LDAP and RADIUS integration | Security Architect | Not Started
M3 | Integrations Complete | Week 4 | VPN M365 and AWS SSO configured with FIDO2 authentication | Security Architect | Not Started
M4 | Pilot Complete | Week 4 | IT department (25 users) successfully using YubiKey MFA | IT Security | Not Started
M5 | Full Rollout Complete | Week 6 | All 500 users enrolled with YubiKey FIDO2 tokens | IT Security | Not Started
M6 | Project Closure | Week 6 | CMMC Level 2 evidence collected training complete support transitioned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | SecOps | NetEng | Cloud | AD | IT | Client
Project Charter and Kickoff | A | C | C | I | I | I | C | I
Current Authentication Assessment | A | R | C | C | C | C | C | C
SafeID Configuration Design | A | R | C | C | C | C | I | I
YubiKey Token Procurement | A | C | I | I | I | I | R | C
SafeID Server Deployment | A | R | C | I | I | C | C | I
Active Directory Integration | A | C | C | I | I | R | C | I
RADIUS VPN Integration | A | C | C | R | I | I | C | I
SAML SSO Configuration | A | R | C | I | C | I | C | I
User Enrollment Rollout | A | C | R | I | I | I | C | I
FIDO2 Authentication Testing | A | R | C | C | C | I | I | I
CMMC Compliance Documentation | A | R | C | I | I | I | C | I
Help Desk Training | A | I | C | I | I | I | R | C
Production Go-Live Approval | A | C | C | C | C | C | C | R
Legend:
R | A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders PM Architect CISO IT Lead | Launch project and align on scope and timeline | Project Manager | Week 1 Day 1
Steering Committee | Weekly | Executive sponsors PM CISO IT Director | Strategic updates budget review issue escalation | Project Manager | Fridays 10:00
Daily Standup | Daily | Core project team | Review progress blockers and daily priorities | Project Manager | Daily 09:00
Technical Review | Weekly | Architect Security Ops Network AD Admin | Technical decisions and implementation progress | Security Architect | Wednesdays 14:00
Enrollment Checkpoint | Daily | IT Security Architect Help Desk | User enrollment progress and issue resolution | IT Security | Week 4-6 Daily
Validation Review | Daily | Architect Security Ops QA | Authentication testing and compliance findings | Security Architect | Week 6 Daily
Training Coordination | Once | Training Lead Help Desk IT Team | Training schedule and logistics confirmation | Training Lead | Week 5 Day 5
Go-Live Readiness | Daily | All stakeholders | Go-live checklist and final preparation | Project Manager | Week 6 Daily